## Questions
ID | Domain | Question | Answer_A | Answer_B | Answer_C | Answer_D | Correct | Explanation
1 | Scope | Define Project Scope. | It is the description of the required work that is necessary to complete the project. | It is the description of the required work and resources that are needed to complete the project. | It is the design of experiments that are used to complete the project work. | It is the combination of the cost and the schedule which is required to complete the project work. | A
2 | General | Which of the following comprises the Project Life Cycle? | Milestones | Estimates | Phases | Activities | C
3 | General | Being the project manager of the ABC Project, you have allowed subsequent project phase to begin even before the predecessor phase completes. Which of the following relates to this scenario? | Fast-tracking | Tandem scheduling | Crashing | Risk management | A
4 | Resource | The person or group providing the resources and support for the project, program or portfolio and is also responsible for enabling success is called the: | Project Manager | Sponsor | Senior Management | Client | B
5 | General | Which of the following cannot be the part of Group creativity techniques: | Affinity Diagram | Nominal Group Technique | Vendor Bid Analysis | Brainstorming | C
6 | General | Being the project manager of a thermal power plant project you need to manage the construction of an administrative unit building. Which of the following technique will you use to quickly estimate and decide the use of historic estimate and expert judgement? | Historical Estimating | Analogous Estimating | Parametric Estimating | Expert Judgement | B
7 | Cost | What is the acceptable range used for determining the realistic activity cost estimates? | Units of Measure | Level of Precision | Level of Accuracy | Cost Management Plan | C
8 | Schedule | What is the SPI of a Software development Project where EV = $6,000, PV = $5,000, AC = $4,000? | 0.8 | 1 | 1.2 | 0.73 | C
9 | Cost | Cost baseline is the output of which of the following? | Control costs | Estimate Costs | Plan Cost Management | Determine Budget | D
10 | Resource | Suppose you are the project manager on a thermal power plant project. How will you manage your team members, if there is a difference of opinion over the design of turbine? | Organize meetings to resolve the misunderstanding and agree on a common solution. | Copy the design of turbine from a similar past project. | Defer the decision to procure turbine components as much as possible. | Procure the turbine parts from the nearest located vendor. | A
11 | Risk | You find that activity in your project is very risky. How will you estimate the duration of this activity when your team member has given the optimistic, most likely and pessimistic duration for the activity? | Using variance analysis | Using PERT formula | Using Sensitivity analysis | Using Performance Reports | B
12 | General | Which of the following is not valid according to McGreger’s Theory X? | Employees are self-centered. | Employees seek to be directed. | Employees are self-motivated. | Employees avoid work. | C
13 | Procurement | You are the project manager for a software development project. Your CPI drops to 0.93 when one of your key developers suddenly falls ill. To make up for your affected work, you have decided to outsource it to a vendor. What will be the most appropriate contract type in this case: | Letter of Intent | FPEPA | Cost Reimbursable Contract | Retainage | C
14 | Stakeholder | Who among the following said, “People will be interested in their safety needs only after their physiological needs have been fulfilled.”: | Ouchi | Herzberg | Maslow | McGregor | C
15 | Scope | WBS is an excellent and most effective tool that is used for tracking of: | Project Scope | Project Schedule | Project Resources | Project Risks | A
16 | Business Environment | The best project organization structure for a small but highly technical project will be: | Projectized Organization | Mixed Organization | Functional Organization | Matrix Organization | C
17 | Resource | Being a project manager is you need to manage a project where there will be a number of persons working together. If you want to enhance the ability of the team to work together and perform as a team which one of the following things you need to do to maximize the ability of the team? | Colocation | Work breakdown structure | Cohabitation | Staffing Plan | A
18 | Integration | What is the role of the change control board? | Defining requirements for the customer. | Doing performance appraisal for team members involved in implementing changes. | Encouraging team members to raise more change requests. | Assessing the impact of the change on Project objectives. | D
19 | Risk | Being the project manager on a STP project, you decide to respond to an identified risk by contracting out work. Which of the following will lead to the minimum risk of the buyer? | FFP (Firm Fixed Price) | CPPC (Cost Plus Percentage of Cost) | T&M (Time & Material) | CPFF (Cost Plus Fixed Fee) | A
20 | Stakeholder | For which process the stakeholderâ€™s engagement assessment matrix is prepared as a part? | Plan Stakeholder management | Identify Stakeholders | Manage Stakeholder Engagement | Control Stakeholder Engagement | A
21 | Resource | Being a project manager you need to spend a significant amount of time in communications. Which of the following option contains the three basic elements of a communications mode? | Sender, receiver, and message | Manager, worker, and instructions | Verbal, Nonverbal and Written | Text, drawing, and picture | A
22 | People | Suppose you are assigned as the project manager of a 30 months project which is in the executing phase. What will be the best way to resolve a conflict among the technical experts in your team? | Remove this technical work from the scope of project work. | Find the root cause of the disagreement. | Resolve the conflict in favor of the senior most technical expert. | Hire an external consultant to enforce his decision. | B
23 | Resource | What should be your primary concern while adding resources to your project? | Effect of adding resources on Cost and Schedule. | Effect of adding resources on project end date. | Effect of adding resources on S curve. | Effect of adding resources on RAM. | A
24 | Cost | If John is working with his team to decide the degree to which cost estimates should be rounded up or down, then he is working to establish which of the following: | Level of accuracy | Units of measure | Level of Precision | Control Thresholds | C
25 | Stakeholder | Being a Project Manager, how will you deal with a stakeholder who has high power and high interest? | Keep Informed | Monitor | Manage Closely | Keep Satisfied | C
26 | Cost | While estimating the cost of work in a very new technology, being a project manager which of the following will concern you the most? | Internet connection not reliable | Lack of Historical Information | Lack of Quality Policy | Lack of Communications management plan | B
27 | Cost | A road project was planned to be completed in 8 months. Calculate the SV when the earned value information at the end of six months is given as: BAC = $8000 , AC = $12000, % complete = 100%. | $4,000 | $8,000 | $6,000 | $2,000 | D
28 | Cost | What will be incentive amount for a contractor, who is working on a cost plus incentive fee contract? The project’s target cost is $5,000 with a target fee of $800, the minimum fee is $500 & the maximum fee is $1,000. Also, the buyer-seller share ratio is 80:20 with an actual cost of $6000. | ($200) | $600 | ($600) | $200 | A
29 | Resource | Which of the following a resource histogram shows but a responsibility assignment matrix does not? | Activities assigned to | Time | Activities | Interrelationship | B
30 | General | Which of the following is used to display sensitivity analysis? | Sensitivity Diagram | Tornado Diagram | Decision Tree | Data Flow Diagram | B
31 | Cost | If SPI = 0.75 and CPI = 0.8, then which of the following reports is correct? | SV = $3750 | TCPI = 0.8 | CV = $4000 | The project likely needs more money than planned to complete | D
32 | Process | According to PMBOK, project management processes are organized into which of the following order of process groups? | Initiating, designing, planning, executing, controlling, and closing | Designing, developing, testing, and implementing | Initiating, planning, executing, monitoring and controlling, and closing | Initiating, planning, executing, monitoring, and closing | C
33 | Schedule | Which of the following statements is true regarding negative float? | The project manager should try to remove negative float by reducing scope. | The project manager should try to remove negative float by crashing or fast- tracking. | It is desirable to have the negative float in the project. | There cannot be any negative float in the project. | B
34 | Scope | Which of the following represents a set of conditions that should be satisfied before deliverables are accepted? | Acceptance Criteria | Punch List | Deliverables List | Test Plan | A
35 | General | How will a Pareto Chart help in a project with a lot of identified action items? | Complete all activities on time | Identify root causes | Understand the trend of deviations | Prioritization | D
36 | General | The activity relationship between the start of cleaning and the start of digging is represented by which of the following? | Finish-to-Finish | Finish-to-Start | Start-to-Start | Start-to-Finish | C
37 | Schedule | Schedule Variance is: | A positive value means that the project will likely be delayed. | A negative value means that the project will likely be delayed. | This always affects the CV. | This never affects the CV. | B
38 | Stakeholder | You are currently working as a Project Manager in Realty Logistics. You have been given responsibility for moving Infrastructure of ABC Software LTD to a new location. For that, you need to identify the stakeholders of your project. Based on the Power/Interest Grid that you have created, which of the following types of stakeholders’ expectation should be managed closely? | Low Power – High Interest | High Power – Low Interest | High Power – High Interest | Low Power – Low Interest | C
39 | Quality | What is the company-wide policy which mandates all project quality known as? | Quality policy | ISO 9000 | Quality control | Quality planning | A
40 | General | Which one of the following describes the difference between a Standard and a Deviation accurately? | Regulations are mandatory but standards may be seen as guidelines. | Standards are optional but regulations are not. | Standards are mandatory but regulations are not. | Regulations and Standards are essentially the same. | A
41 | Cost | What will be the BAC of your project, if it has a CPI of 0.80 and an EAC of $ 1265825? | $1,582,281.00 | None of the above | $1,012,660.00 | $1,000,000.00 | C
42 | General | The BEST way of making an accurate forecasting of ETC is: | EAC – AC | (BAC EV) / CPI | Manual Forecasting of the cost of remaining work | BAC – AC | C
43 | General | How will you assess a situation where six observations are within the UPPER CONTROL LIMIT and control line while the seventh observation is observed within UPPER CONTROL LIMIT and Control line? | There are no defects. | The process is out of control. | The process is in control. | Project Manager should move to the next process as everything is ok. | B
44 | General | Which of the following can be used for Trend Analysis? | Cause and Effect Diagram | Control Charts | Run Chart | Pareto Chart | C
45 | General | In which of theory, Douglas McGregor has defined two models of worker behavior? | Contingency Theory | Theory Z | Theory X and Theory Y | Expectancy Theory | C
46 | Resource | What are the three ‘I’s’ of stakeholders? | Importance, inquiry, and influence | Interest, influence, and involvement | Interest, influence, and importance | Interest, influence, and impact | D
47 | General | Which of the following is the objective of conducting Bidder Conferences? | To ensure that all parties get answers to their questions. | To make sure that potential sellers are treated as per the type of questions asked. | To make sure that all questions from potential sellers are answered privately. | To make sure that all potential sellers are treated equally and have access to the same information. | D
48 | Quality | What is the Japanese method of modern quality management called, which relies on continuous small improvements involving everyone from the top management to the lowest level worker in the organization? | Kaizen | PDCA | Deming Cycle | Kanban | A
49 | People | Herzberg divided motivation factors into two classes: satisfiers and dissatisfies. Which of the following are the examples of satisfiers then? | Vacation time, assignment of a personal staff assistant. PMP Math Questions For the first three questions, assume you are managing the following project: You are the project manager of a project that is budgeted to cost $1 million at completion. The project will last ten months and its budget is spread evenly across each month. It is currently 50% complete and has so far cost $750K but only produced value of $500K. | The sense of personal achievement, work satisfaction. | Work satisfaction, a fringe benefit. | Plush office space, performance-based salary raise. | B
50 | Resource | While working on a project, the project manager notices that most of their time is spent resolving conflicts between members of the project team. What is the best tool the project manager can use to resolve the problems amongst the team members? | Expert judgement | Colocation | Training | Interpersonal and team skills | D | Resolving team conflicts is done through the manage team process. This process includes interpersonal and team skills tools, of which conflict management is a subset.
51 | Resource | The project manager has met with the project team and has informed them that his team performance assessments are done, and he would like to speak with each of them individually about the results. What process group is this? | Monitoring and controlling | Planning | Initiating | Executing | D | During the executing process group, the project manager will assess the team's performance and try to improve it through the process of developing and managing the team.
52 | Scope | While planning a major network upgrade project, one stakeholder has given a requirement to upgrade the switches. The project manager has determined that this would be too costly to be included in the project and has decided to exclude it. What process will the project manager use to document this exclusion? | Collect requirements | Close project or phase | Define Scope | Create WBS | C | The project scope statement would have a list of deliverables and include things such as acceptance criteria, exclusions, constraints, and assumptions. The scope statement is created in the process of define the scope.
53 | Procurement | While conducting procurement on a project, the project manager has received many different bids with a wide variance of estimated cost for the work. What can the project manager use to best determine which vendor has given a realistic price? | Weighing system | Screening system | Inspection and audits | Independent estimate | D | An independent estimate is usually done by an outside entity to help give the project manager a more independent understanding of what certain project work will cost.
54 | Cost | The project manager has been informed that the cost of building a new room in the office will be $15,000, +/- 65%. The project manager wants to know why there is such a large variance in the estimate. The builder said they have not seen the space and it's just a high-level estimate. What kind of estimate does this best represent? | Rough order of magnitude estimate | Materials estimate | Definitive estimate | Detail estimate | A | A rough order of magnitude estimate has a variance of -25% to +75%. It is usually done in the early phases of the project.
55 | Cost | While working on a project, the project manager asks the team to incorporate more of the user feedback into the deliverables. In an agile project, where do the customers give the team feedback on the product? | Retrospective | Sprint planning meeting | Sprint review | Release feedback | C | During a sprint review, the customers review the partially finished product and give the team their feedback.
56 | Risk | The project manager and team have decided to hire a contractor to complete building out the remaining section of the datacenter. They have the requirements listed in detail and would like to use a contract that would present the smallest amount of risk to the project. The project team members would like to purchase the materials themselves since there are very familiar with the work. What contract is best for this project? | Cost plus contractor fee | Cost plus fixed fee | Time and materials | Cost plus project fee | B | A cost-plus-fixed-fee contract is where the buyer pays all the work expenses and then pays a fixed price for the work.
57 | Resource | Which of the following is an XP practice that helps to create a shared vision between the developers and the customers? | Iteration review meeting | Retrospectives | Daily standup meetings | Metaphors | D | A metaphor is using XP to explain designs and create a shared vision between customers and the development team.
58 | Risk | A team member is working on upgrading the network server while another team member is painting the server room. The outcomes of these two events will not affect each other. What best describes the relationship between these two events? | They are not statistically independent | They are statistically insignificant | There are statistically independent | They are mutually exclusive | C | Statistical independence is a term used in probability that means one event cannot affect the other event.
59 | Risk | The project manager has to present a risk assessment to senior management and has decided to take the most graphical representation of the probability and impact assessment. What tool should the project manager use? | Pareto chart | Bubble chart | Risk summary chart | Risk register | B | Bubble charts are tools in the perform quantitative risk analysis process and can show the probability, impact, and ranking of risk.
60 | Scope | While building an agile space, the project manager would like to implement a tool that will allow the team to keep track of the flow of work while limiting the work in progress. What tool best meets these requirements? | Burndown charts | Kanban development | Gantt chart | Whiteboard | B | Kanban development involves the use of a signboard that is used to help track the work in progress and limit the work in progress.
61 | Resource | Which of the following is not a principle of agile planning? | Engage the project team | Conduct most of the planning at the beginning | Engage stakeholders | Conduct planning throughout the project | B | On the traditional project most of the planning is done on the beginning, while agile projects are planned throughout the project with the help of all stakeholders.
62 | Resource | The sponsor makes it clear that he does not want any of the team members to be overworked while working on a project. This means that no team member is allowed to work overtime. The sponsor is okay with the project being delayed due to this. What technique can the project manager best implement to ensure that no team member is overworked? | Resource smoothing | Resource leveling | Free float | Lag | B | Resource leveling is a technique used when resources are limited or over-allocated. Resource leveling ensures that no resource is assigned to more than one activity at a time, ensuring that no resource is overworked.
63 | Risk | While conducting a risk assessment on a project, the project manager has identified a new regulatory risk. If the project is not completed by July 31, the company will have to scrap the project. What best describes this? | Project requirement | Project constraint | Project work | Project scope | B | There are 6 constraints on a project,: scope, cost, time, resources, risk, and quality. This project is constrained by time.
64 | Cost | The project manager has brought the project team together to explain what the project will be about and what their roles will be. The team members introduce themselves and learn about the different skill sets each of them brings to the project. What stage on Tuckman's ladder best represents this? | Norming | Performing | Forming | Storming | C | In the forming stage of Tuckman's ladder, the team is formed and learns about each other.
65 | People | Two team members were having a conflict over what programming method should be used on the new application. They have resolved the conflict. What would be their next step? | Implement the new method and verify that it solves the actual problem. | Confirm that the sponsor agrees to the solution. | Confirm that the project manager has agreed to the solutions. | Nothing, since the conflict has been resolved. | A | When a problem has been solved, the next step would be to confirm that the solution has actually solved the problem after it has been implemented.
66 | Resource | While building the agile space for new agile team, which of the following tools should the project manager ensure is available to all of them? | A big screen monitor with the latest Kanban software | A whiteboard | A network enabled project management software | Private offices with virtual meeting software | B | The use of high-touch low-tech tools, such as a whiteboard, is vital in an agile environment to ensure collaboration and engagement of all team members.
67 | Cost | As an agile project manager, you have encountered many issues with the product owner. The product owner has refused to prioritize the product backlog, stating that all items are equally important. After educating the product owner about the value of prioritization, he still refuses. What should the agile project manager do? | Continue to educate the product owner | Prioritize the product backlog for the product owner | Replace the product owner | Have the team prioritize the product backlog | A | One of the core task of being an agile project manager is to educate and promote the values of agile practices even when stakeholders are reluctant to follow those principles.
68 | Scope | While developing a new smartphone, the project team has identified a specific set of performance measurements that the phone should meet when it is complete. The measurement looks at how fast the phone can boot up and how fast it can shut down. Where should the project team document these measurements? | Quality checklist | Quality management plan | Quality metrics | Requirements traceability Matrix | C | Quality metrics are used to measure the project deliverables.
69 | Cost | While compiling all the work performance information into the work performance report, a project manager notices that the SPI of the project is .6 and the CPI is .7. What action should the project manager take next on this project? | None since the project is on the budget and ahead of schedule. | Inform the sponsor of a major delay. | Create a change request to correct the project. | Inform the sponsor the project is over budget. | C | In this scenario, an SPI of .6 and a CPI of .7 indicate that the project is behind schedule and over budget. The project manager should initiate change requests to correct the budget and schedule of the project.
70 | Cost | The project team has completed the scope baseline and has started to break down each of the work packages into individual activities. What process should the team do next? | Develop Schedule | Sequence Activity | Create WBS | Define Scope | B | After the team has created the activity list in the process of define activity, the next process should be sequencing the activities.
71 | Cost | The agile project team has decided to do one of the features from the product backlog. The single feature will take six weeks to complete and will be reviewed by the customer. What actions should the agile project manager take next? | Inform the customers of the six weeks duration | Inform the team they need to conduct the daily standup meetings | Informed the team six weeks is too long and they will need to decomposed that feature into smaller increments | Arrange the workspace for the team members to get started | C | In agile, iterations should be no more than one to four weeks. Features that take longer than should be decomposed into smaller features that can be completed within one to four weeks.
72 | Risk | The project manager and the project team are currently assessing various ways of responding to a particular risk. The project involves reconstructing part of their current office building, and they're worried about a hurricane hitting and damaging the materials or parts of the unfinished building. The best response they came up with was to purchase insurance in case a hurricane does hit. What kind of strategy is this? | Avoidance | Mitigate | Acceptance | Transfer | D | When a risk is transferred, it is usually transferred to another company, such as by purchasing insurance or hiring a consultant.
73 | Scope | Senior management has requested an update to the current product upgrade project. The project manager knows she has to keep the information high- level, and as short as possible. Which resource would be the best to show senior management? | Project schedule network diagram | WBS dictionary | Milestone chart | WBS | C | A milestone chart shows only the timeframes of the major deliverables. All other choices such as the WBS, WBS dictionary, and the network diagram are very detailed.
74 | Resource | There have been many disputes on the project with the current contractor. The contractor claims the project team is always asking that work not be listed in the contract, and the team claims that the contractor has not been doing the work listed in the contract. What should the project manager do first? | Contact claims administration | Review the contract | Meet with the project team members to understand why they feel the contractor has not been doing the work in the contract | Meet with the contractor to understand why the team continually asks that the work not be listed in the contract | B | The first step would be to review the contract to ensure he understands what the original agreement was, and then he should meet with the team and contractor.
75 | General | Which of the following is a method that will be used to conduct frequent verification and validation that can be done every second on the project? | Pair programming | Unit testing | Integration testing | Acceptance testing | A | Pair programming is defined as when one programmer writes the code and another inspects the code as it's being written. This leads to the code being inspected in seconds.
76 | Resource | While monitoring and controlling the project, the project manager and the team have consistently received broken equipment from a particular vendor. They have spoken with the vendor and implemented a new process that will ensure the equipment does not show up broken. This seems to have solved the problem. What is the next step the project manager should take? | Investigate the problem | Check the solution | Solve the problem | Analyze the problem | B | When encountering any problem on a project, the project manager should first identify the problem, define the problem, investigate, analyze, solve, and then check the solution. In this situation, the problem has already been solved, so the next step would be to check the solution to ensure the problem has actually been solved.
77 | Scope | The project sponsor has signed off on the project charter and has spoken to the project manager, who then has to keep the cost down on the project. The project manager agrees to try his best to keep cost down and to finish the project under budget. What should the project manager do next? | Create the WBS | Implement the project cost reduction program | Meet with the stakeholders to gather their requirements | Meet with the team to determine where money can be saved on the project | C | Once the project charter is created, the next step would be to collect the requirements and then create the scope statement and the WBS. You cannot meet with the team to reduce cost if you don't know the requirements.
78 | Communications | The project manager has reviewed all the work performance information that has been created so far on the project. He has started to create the overall project status report to present to the project stakeholders. What process is the project manager conducting? | Develop project report | Direct and manage project work | Monitor and control project work | Develop project management plan | C | Monitor and control project work process has an input of work performance information and an output of work performance report. No other choice has the output of work performance report.
79 | Schedule | Mark is currently working on the workstation upgrade project. He has noticed there are three activities on the critical path, which are activity A, C, and D. Activity B has a slack of 2 and a duration of 4 days. Activity C has a duration of 3 days, and activity D has a duration of 6 days. What is the slack on activity A? | 4 days | 2 days- | Cannot be determined | 0 days | D | Activities on a critical path have zero slack. The question is trying to mislead you into drawing a network diagram that is not needed to determine the slack.
80 | Schedule | While working on a new server upgrade project, the project manager calculates the SPI of the project to be 1.3. The project sponsor would like an explanation for why the SPI is that high. What would be the project manager's best response? | The project contained a lot of work that took more time than anticipated and is now completely behind schedule | The project is currently on schedule due to the level of details that was covered during the planning processes | The project team were able to finish the work faster than anticipated and this is what led to the project being ahead of schedule | The project had too many critical paths on it this led to a large delay on the project | C | An SPI of 1.3 shows that the project is ahead of schedule by 30%. This could be because the project team is finishing the work faster than originally scheduled.
81 | Resource | While working on an agile project, the project manager met with the project team members to discuss what they did the day before and what they plan to do today. What is the name of this meeting? | Sprint planning meeting | Sprint review meeting | Daily stand-up meeting | Project review meeting | C | A daily stand-up meeting is done on a daily basis to answer 3 questions: What have you done since yesterday? What will you do today? Are there any roadblocks?
82 | Scope | The project manager is having a very difficult time collecting the requirements from the customers. The customers are having a difficult time putting the requirements into logical groupings. What tool can best help them group the requirements? | Requirements Documentation | Decomposition | Affinity Diagram | Prototype | C | An affinity diagram is used to group large numbers of ideas to be analyzed.
83 | Integration | While working on a web design project, the change control board approved a change to the layout of the menu. What process should the project manager conduct next to ensure the change is implemented? | Update change log | Verify scope | Update project management plan | Direct and manage project work | D | Once a change has been approved, it is then moved to the direct and manage project work process for implementation.
84 | General | The project manager has just spoken to one of the software developers, Bill, about the project and has asked for an estimate of how long it will take to code a specific function. Bill said that it would take a maximum of 10 days, but that most likely it will be 6 days. The project manager has calculated the PERT estimated duration of this activity to be 6 days. What is the least amount of days it will take to complete this activity? | 4 | 2 | 3 | 1 | B | Using the PERT formula (O+4*R+P)/6 = 6, we can solve for O (optimistic estimate) to get 2 days.
85 | Scope | The project planning has been completed for the office renovation project. The project management plan has been approved by the sponsor and senior management. What should the project manager do next? | Update the functional managers | Hold a kickoff meeting | Inform senior management | Get all deliverables accepted | B | A project kickoff meeting is generally done after planning a large project to bring the team together and inform them of the project requirements.
86 | Resource | While working on an agile project, the team receives a request from the customer to deploy the software as soon as the iteration is done. The customer has already checked the completed part of the software and has accepted it. The team has refused to deploy the software. What best explains the team's refusal? | The iteration needs to be closed | The iteration took too long | The iteration has many errors | The iteration is part of a release | D | Iterations are part of a product that is inspected by the customers. An iteration may not be something that can be released to users since it only represents a few weeks' worth of work.
87 | Scope | The project manager is having a difficult time keeping the project on plan. There are many changes regarding the project scope, which has led to an increase in the project budget. Management would like a reason why there have been so many scope changes on this project. What would most likely cause many scope changes on a project? | Management did not approve the project | The project manager does not have enough training | Did not gather detailed requirements | Spent too long creating the project schedule and not enough time on the scope | C | Generally, if a project manager finds themselves with many scope changes when the project is executed, it's most likely that they did not gather the requirements adequately from the customers.
88 | Risk | While planning the risk responses for a construction project, the project manager and project team have decided they will have to choose a new electrical contractor due to the fact that the recommended contractor has legal issues with the local building department. The legal issues could cause the project to be delayed. What risk response does this represent? | Mitigate | Avoid | Accept | Exploit | B | Avoidance is when you go down a different path altogether. The risk is eliminated and cannot happen. Since they chose another contractor, they cannot get delayed by that particular contractor.
89 | Risk | The project team has identified a number of risks that could affect the project. One risk in particular is that the permit to build the foundation has shown up late. They have ranked this risk as the most important in the project since it will cause the largest delay. What process best describes this ranking? | Qualitative risk analysis | Quantitative risk analysis | Identify risk | Plan risk management | A | A qualitative risk process is done to rank the risk that has been identified in the identify risk process.
90 | Communications | While working on a large project, the project manager originally counted 12 stakeholders. A new requirement and six more stakeholders were added to the project. How many communication channels are on this project? | 153 | 360 | 306 | 160 | A | Using the communications channels formula N(N-1)/2, with 18 stakeholders, we get 18(18-1)/2 = 153.
91 | Communications | The project manager is informed that a manager in the finance department has requested to be included in the weekly status updates on the project. What document should the project manager update immediately? | Issue log | Risk register | Stakeholder register | Project communications | C | The stakeholder register can be updated at any point during the project. It contains a list of all stakeholders and their contact information, communication requirements, and impact on the project.
92 | Resource | The project manager and team are currently working to create a list of activities needed to complete the project. They have come to one particular work package that they cannot decompose because they do not know enough about the work yet. They have decided that midway through the project, they will decompose this particular work package. What tool or technique are they using? | Decomposition | Rolling Wave Planning | Forward Planning | Requirements Future Planning | B | Rolling wave planning is a tool used in the process of define activities to break work down in the future.
93 | Resource | The work the project will contain and the velocity of the team is currently at 14 points. What is the total size of the project in terms of story points? | 110 | 130 | 140 | 150 | C | Total size of the project will be 10 iterations x 14 points = 140 Points.
94 | Stakeholder | In what process does a project manager determine the approach they will use to involve the stakeholders to meet their expectations? | Plan stakeholders engagement | Manage stakeholders engagements | Identify stakeholders | Plan communications | A | During the process of plan stakeholder engagement, the project manager will develop an approach to involve the stakeholders to meet their expectations, interest, and potential impact on the project.
95 | General | When using different prioritization techniques what is the most important aspect that the agile project manager should communicate to the customers? | Don't worry too much about the specifics it's more important to get the relative prioritization correct | Make sure to include cost in the use of any prioritization technique | Make sure to include timing in the use of any prioritization technique | Prioritization techniques are not needed on agile projects | A | When using any prioritization technique, it is important the customer understands not to worry too much about the specifics of the technique but rather to prioritize the features based on relative value.
96 | Communications | Managing a project can be a very complex task that involves identifying and managing all the stakeholders on the project. The project manager spends 90% of their time doing what important task? | Determining the needs of the stakeholders | Communications | Determining how long it will take to finish an activity | Determining how much an activity will cost | B | Communications generally take up 90% of the project manager's time. This generally includes various types of meetings, discussions, negotiation, and problem solving.
97 | Process | Your company has just started a project to allow remote workers to join the network using a virtual private network (VPN). During the execution of the project, one of the VPN servers completely fails, and the team will need to replace it as soon as possible. Fortunately, the project team anticipated that this might happen and has a plan for replacing the server. What should the project manager do next? | Perform qualitative risk analysis | Implement risk response | Plan risk response | Conduct risk response | B | Implement risk response is a process in the executing process group, where the project manager implements the preplanned responses to any risks that may have taken place.
98 | Cost | After the iteration has completed, where will the team inspect the methods they used to build that increment? | Iteration backlog | Retrospective | Iteration planning | Iteration review | B | A retrospective is done after each iteration so the team can reflect and plan improvements for the next iteration.
99 | People | While managing the project team the agile project manager is having a very difficult time understanding why team members are always frustrated when communicating with him. What critical soft skills does this project manager lack? | Facilitation | Emotional intelligence | Negotiation | Active listening | B | Emotional intelligence is defined as the ability to identify, assess, and influence emotions of ourselves and others around us.
100 | Risk | The risk management plan generally outlines the steps the project will take to conduct risk management processes on the project. Which of the following will the risk management plan not include? | Positive risks that could affect the project | The methodology used to manage risks | A way to categorize the risks | Roles and responsibilities for the project team concerning risks processes | A | The risk register lists both positive and negative risks, not the risk management plan.
101 | Resource | A project manager is having a very difficult time negotiating with a functional manager. The project manager would like to have Peter, the system administrator, work on the project full time, but the functional manager needs Peter full time to work on the servers throughout the day in case one goes down. After a few days of negotiating, the project manager has determined that he will have Peter from Monday to Wednesday, and the functional manager can have Peter on Thursday and Friday. Although this solution is not the most ideal scenario for the project manager and functional manager, it will have to work for now. What conflict resolution technique was used? | Forcing | Problem solving | Smoothing | Compromising | D | Compromising is when both sides in a conflict give up something to come up with a solution.
102 | Cost | A large development company has just initiated a project to build a 60-story building. The project will take approximately 3 years to complete with a cost of $550 million. The development company has started to facilitate funding for the project by asking private equity firms and banks. What tools does this best represent? | Financing | Funding limit reconciliation | Analogous estimates | Parametric estimates | A | Financing is a tool used in the process of determine budget. This is when a company looks at external sources to fund the project.
103 | General | While working on the network upgrade project, the project manager receives many ideas about what to include in the project. The ideas seem to be very scattered and not logically grouped. What tool can best help the project manager group these ideas? | Ideas Matrix | Flowchart | Histograms | Affinity diagrams | D | An affinity diagram is used to group a large number of ideas to review and analyze.
104 | Communications | The project team has just started to code a redesigned accounting application when a key stakeholder asks for the application to include a very specific report on the company's expenses. The stakeholder has submitted a change request to the project manager. What would be the most important input to consider for this change request? | Work performance information | Accepted deliverables | Work performance reports | Work performance data | C | Work performance reports are an input to the process of performing integrated change control, as it will show the overall status of the project.
105 | Cost | The project manager, Mark, overheard that the project team is not satisfied with the way the budget was created. They strongly believe the project will be over budget at the end. What is the next best step for Mark? | Review how the budget was created | Bring the team together and attempt to understand why they feel this way | Ask the sponsor for approval to increase the budget | Do nothing, because the team didn't speak to Mark about it | B | A project manager should not take action on issues they overhear without first finding out why stakeholders feel a certain way. This ensures that the project manager has a detailed understanding of the issues
106 | Cost | The agile project team has completed the Sprint planning meeting. What would be the output of this meeting? | Sprint backlog | Product backlog | Sprint requirements | User backlog | A | The output of the Sprint planning meeting is the Sprint backlog which will outline all work to be done in the next Sprint. The product backlog is a list of all features for the entire project, not just for a single Sprint. User backlog and Sprint requirements are not standard Agile terms.
107 | Scope | While developing very complex software, the project manager met with some of the industry's top subject matter experts to understand their perspectives on solving some of the problems in the software. What tool best describes these meetings? | Brainstorming | Focus groups | Questionnaires and surveys | Checklists | B | A focus group brings together subject matter experts to understand their perspectives and how they would go about solving problems. Brainstorming is done by a group of stakeholders to gather ideas. Checklists and questionnaires are typically used to gather requirements from a broader group of stakeholders.
108 | Quality | While managing a product development project, the project manager met with the team to determine some of the key tasks that will ensure they produce a high-quality product. What should they consider the most important concept in quality? | Quality is about more inspection than prevention | Cost of quality only includes the inspection cost | High-grade is more important than high-quality | Quality is about prevention | D | Quality management is primarily about preventing defects from occurring in the first place, rather than finding and fixing them later. Prevention is more cost-effective and efficient than inspection and rework.
109 | General | The product owner would like to see how much work remains to be done on a project. What would be the best agile tool to display this? | Burnup chart | Cumulative flow diagram | Burndown chart | Velocity chart | C | A burndown chart displays work that remains to be done on a project over time. It's an effective tool for showing progress and estimating completion dates in Agile projects.
110 | Scope | The project manager is currently analyzing the requirements for the project. He has been informed that the stakeholders will be very disappointed if there are defects in the deliverables. He decides to ensure that the project team receives the right training and the best equipment available to build the deliverables correctly. This will in turn increase the overall cost of the project, but stakeholders do not mind the increase in cost. What best describes this increase in cost? | Activities cost | Cost of the requirements | Cost of quality | Expert judgement | C | The cost of quality includes the cost of conformance, which includes funds spent to ensure the project meets the quality requirements. This generally includes the cost of better materials, more expert team members, and better equipment.
111 | Schedule | The project manager has been informed that the company's senior management would like a meeting about the status of the project. What should the project manager take to display the current schedule of the project? | Milestone chart | Gantt chart | WBS | Network diagram | A | A milestone chart is a high-level view of major accomplishments on a project. These are best used when presenting a quick view of data and the project schedule to management personnel.
112 | Cost | The project team has just assigned costs to all activities on a project. They will now use these costs to find the overall budget of the project. What tool can the project team use to complete this task? | Parametric estimation | Bottom-up estimation | Expert judgment | Cost aggregation | D | If the activities have been assigned costs, then the process of estimate costs has been completed. The next process would be to determine budget and use the cost aggregation tool to integrate all the activities into the overall budget of the project.
113 | Resource | A project manager is currently working with the team to complete the office redesign project when a sponsor tells him to finish it 2 weeks sooner than planned. The project manager will need 4 new people to join the team to complete the work by the new deadline. What technique is best described in this scenario? | Fast tracking | Schedule variance | Crashing | Critical path method | C | Crashing is a scheduled compression method where you add more resources to complete the project sooner.
114 | Resource | The project team has completed a bidder conference for the office renovation project. Over 15 different construction companies came to the conference. Directly after the conference, all the companies submitted their bids immediately. What is the next step the project team should take? | Update the scope baseline | Rewrite the statement of work | Update the agreement | Select the seller | D | A bidder conference is a tool used for conduct procurement, and the output of this process is to select the seller and receive an agreement.
115 | Scope | While working on a complex web design project, the manager has received a change request from a senior stakeholder to fix a problem with the current intranet server. The project manager has determined that this change is outside the scope of the project and is not covered by the work listed in the project charter. What should the project manager do next? | Inform the stakeholder that this change request should be considered a new project | Inform the stakeholder that the change will incur a significant cost and time increase | Ignore the change request | Pass the change to change control board | A | Although all change requests should be considered by the project manager, they should be related to the project work. No change should be approved if it is outside the scope of the project charter, since that would not be considered work within the current project.
116 | Communications | The project manager is conducting a presentation with a few of the senior stakeholders, and they are not happy with the progress of the project. The project manager has informed them that the delay is due to a contractor that was affected by a major flood a few weeks ago. What process does this best describe? | Manage communication | Control communication | Conduct communication | Plan communication management | A | Manage communication is done in the executing section of the project to update the stakeholders on the project's progress.
117 | Communications | The project manager has decided that most of the stakeholders on the project would like to reference the status reports for the project on the company's internal website on their own time. This would make it easier for them, as it is very difficult to schedule a meeting with all of them at once. What type of communication best describes this? | Interactive communication | Push communication | Technical communication | Pull communication | D | Pull communication is done when stakeholders access the communications on their own time, usually through a web portal.
118 | Stakeholder | After a project manager is assigned to the project with the project charter, he continues to identify the stakeholders on the project. In this process, he creates the stakeholder register. Which of the following statements about the stakeholder register is false? | It's only updated in the initiating phase of the project | It classifies the stakeholders | It contains a list of all stakeholders on the project | It's updated throughout the project | A | The stakeholder register is updated throughout the project, not just during the initiation phase of the project.
119 | Business Environment | What is the main benefit for conducting the project using agile methodology versus traditional methodology? | Traditional delivers values all up front | Traditional delivers value at the beginning | Agile delivers value incrementally | Agile project requires funding up front | C | One of the main benefits of using agile over traditional project management, is that agile delivers value incrementally compared to traditional where you get the value only at the end of the project.
120 | People | A project manager is having difficulties communicating with the project team; there always seem to be misunderstandings and conflicts. What interpersonal and team skills should the project manager improve on? | Active listening | Lessons learned register | Passive listening | Selective listening | A | Active listening helps to reduce misunderstandings and improves communications and knowledge sharing.
121 | General | You are having an issue with the software crashing consistently on the project. What should you use to identify the cause of this issue and the effect it may have on your project? | Histogram | Ishikawa Diagram | Continuous improvement | Flowchart | B | Ishikawa diagrams, or cause-and-effect diagrams, are used to identify probable causes and sub-causes of a particular problem.
122 | Cost | The project has managed to build about half of the deliverables needed to complete the project. The project has spent $50,000 on materials and labor. This money that has already been spent is generally referred to as what? | Project budget | Sunk cost | Spent cost | Opportunity cost | B | Sunk cost is the money that has already been spent on the project.
123 | Schedule | While working on a project, you realize that you will not be able to install the server and the workstations at the same time. In fact, the team has alerted you that after the server installation is done, you should wait an additional 4 days before installing the workstations. This is due to the updates the server will need, which is an automated process. What do you need to add to the schedule in order to account for this delay? | Lead | Float | Lag | Slack | C | A lag is a delay between activities.
124 | Risk | When managing risks on a project, the project manager should be aware of the individual project risks and which other project risks? | Group project risks | Overall project risks | High-probability risks | High-level risks | B | Risk generally falls into two levels on a project: individual project risks and overall project risks.
125 | Stakeholder | While working on a project, the CEO of the company has informed you that he would like to terminate the project and have you work on a few other projects. What kind of influence does this best represent? | Downwards | Upwards | Sideways | Outwards | B | Upwards influence is for stakeholders above you such as senior management.
126 | Cost | The project manager is currently assigning costs to each individual activity on the project. A team member has informed the project manager that he should include additional cost just in case the software needs more testing. What best describes this additional cost? | Testing reserve | Project reserve | Management reserve | Contingency reserve | D | Contingency reserve is what a project manager adds to the project cost baseline due to risk.
127 | Resource | When deciding which user stories can be done in the next iteration what should the project team consider? | Which story is most valuable to the customer | How large is the story | Which story has the least risks | How many points the team completed in the past iterations | D | When determining how much story work can get done in an iteration, the team should look at its velocity, which is based on how many points they were able to get done in previous iterations.
128 | Cost | During a new workstation rollout project, a stakeholder asked for a change to some of the software being installed. The change was submitted to the Change Control Board but was rejected due to the high increase in cost of the software being requested. What should the project manager do next? | Resubmit the change request for additional consideration | Update the change log | Update the issue log | Perform additional analysis on the requested change | B | Once a change has been denied, the next step is to update the change log with the status of the change.
129 | Process | While working on a large multinational project, you identify some of the positive and negative stakeholders. What process group are you currently engaged in? | Communications management | Initiating | Stakeholder management | Planning | B | The process of identifying stakeholders is part of the initiating process group.
130 | Cost | The deliverables for the office relocation project were accepted by the company stakeholders, and all office staff were very happy with the work of the movers. The office manager requested the project be closed immediately due to year-end budgetary closeouts. The movers filed a claim for an additional $300 for moving a copier that was not part of the plan. What should the project manager do next? | Keep the project open and inform claims administration. | Close the project immediately and update the accounting department to pay the claim. | Keep the project open and pay the claim. | Close the project immediately and inform the office manager. | A | A project can only be closed once all claims have been settled. Claims should be sent to claims administration, where negotiation would be the preferred way to resolve them.
131 | Scope | While planning a project, the project manager is given many requirements that the customers would like to add to the project. Upon further investigation, the project manager decides that a few of the requirements will not be feasible within the limited time and cost allocated to the project. What document would best list the requirements that will not be added to this project? | Project scope statement | Work breakdown structure | Project Charter | Requirements documentation | A | The project scope statement includes a list of all the project deliverables as well as any requirements that should be excluded from the scope.
132 | Cost | While monitoring the status of an agile project, what numerical analysis can the project team use to help determine if the project is on schedule? | Earned value management | Net present value | Scheduling management values | Return on investment | A | Earned value management is a series of formulas that monitor the value of the project as it's progressing and generally track cost and schedule.
133 | Cost | The project manager has calculated the SPI of the project to be .7 and the CPI to be .9. When reporting the progress of the project to the company stakeholders, what should the project manager say about the project to the stakeholders? | A delay from a few vendors has delayed the project | The project is progressing on schedule and budget | A few project expenses cost more than the budget of the project | The project is delayed and over budget | D | A CPI and SPI of under 1 are bad. A CPI of under 1 represents a project that is over budget. An SPI of under 1 represents a project that is behind schedule.
134 | Scope | What is the main difference between the product scope and the project scope? | The project manager plans product scope, and the project team plans the project scope. | The project scope describes the features and functionality of the product, whereas the product scope describes how to get the features and functionality from the product. | There is no difference. | The product scope describes the features and functionality of a product, whereas the project scope describes how to get the features and functionality from the product. | D | The product scope describes the features and functionality of the product, whereas the project scope describes how to get the features and functionality from that product.
135 | Cost | The project team has been brought together for the first time to work on a network upgrade project. They were able to learn about the functions they will doing on the project and what their roles will be. What will the team do next, according to Tuckman's ladder? | Forming | Storming | Performing | Norming | B | The cost of quality includes the cost of conformance, which includes funds spent to ensure the project meets the quality requirements. This generally includes the cost of better materials, more expert team members, and better equipment.
136 | Scope | You are currently working on a large building demolition project. There are many requirements for the potential vendors on the project, and you would like to ensure that they all receive the same information. What is the best tool or technique to ensure all vendors receive the same information about the project? | Bidder Conference | Scope statement | Requirements traceability Matrix | Requirements documentation | A | A bidder conference is held by inviting all the potential sellers and reviewing the requirements for the project with them. This will ensure that no vendor receives more or less information than the others. The scope statement, requirements traceability matrix, and requirements documentation are generally written before vendors are invited to learn about the project.
137 | Communications | The project team is currently working on an advertising project. They have completed a few of the activities, which includes writing the script for the commercial. Once the team completes an activity, what should they do next? | Update the project manager | Update work performance data | Close project or phase | Update project sponsor | B | Once work is done on a project, the team should update the work performance data. This will include the status on the work, such as when it was completed or started. The project manager will take the work performance data and create the work performance information and report, which will then be given to all the other stakeholders.
138 | Cost | The project manager is currently working on a large building renovation project. The project team is almost done with planning when the project sponsor informs the project manager that due to new regulations, the project will need to be completed within 6 months; if not, they will not be able to open the building to the public. What best represents this? | Work packages | Deliverables | Constraints | Assumptions | C | A constraint is something that limits a project, which can include time or cost. In this question, the constraint is a limitation on the time available to get the project done. Deliverables, assumptions, and work packages are not constraints on a project.
139 | People | Team members Mark and Bill are currently experiencing conflict in the office move project. Mark believes that it would be best if they moved the furniture first and then the computers, whereas Bill believes it's best to move the computers and then the furniture. This conflict is causing a serious delay to the project, and both Mark and Bill have decided they will make a decision on what to move first at a later date. What conflict resolution technique best describes this scenario? | Postponing | Withdrawal | Compromise | Accommodating | B | The conflict resolution technique illustrated in this question is withdrawal, which is when they postpone the issue to a later date to be better prepared. Compromise is when the two sides reach an agreement but both sides have to give up something. Postponing is a made-up term.
140 | General | Which of the following is not a characteristic of a project? | Progressive elaboration | Temporary | Ongoing operations | Unique | C | Projects are temporary endeavors, not ongoing operations. The other options are characteristics of projects.
141 | Quality | What is the purpose of the control quality process? | To monitor specific project results to determine if they comply with relevant quality standards | To audit quality requirements and the results from quality control measurements | To identify ways to eliminate causes of unsatisfactory performance | To validate that the project deliverables meet the quality requirements specified for the deliverables | A | Control quality is the process of monitoring and recording results of executing the quality activities to assess performance and recommend necessary changes.
142 | Stakeholder | What is the main purpose of the lessons learned register? | To record project team performance | To document project successes and failures | To monitor project costs and schedule | To track project issues and risks | B | The lessons learned register is used to record knowledge gained during a project to be used in future projects.
143 | Business Environment | Which of the following is not a type of organizational structure? | Hierarchical | Matrix | Functional | Projectized | A | Hierarchical is not a type of organizational structure in project management. The other options are recognized organizational structures.
144 | Resource | What is the purpose of a project charter? | To define the project scope | To assign project resources | To create the project schedule | To formally authorize the project | D | The project charter formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities.
145 | Risk | What is the primary purpose of the risk management plan? | To identify all potential risks in a project | To develop response strategies for all identified risks | To define how risks will be managed throughout the project | To prioritize risks based on their impact and probability | C | The risk management plan outlines how risk management activities will be structured and performed on the project.
146 | Cost | Which of the following is not a type of cost estimate? | Top-down | Analogous | Bottom-up | Parametric | A | Top-down is not a recognized type of cost estimate in project management. The other options are valid cost estimation techniques.
147 | Stakeholder | What is the purpose of the stakeholder register? | To identify and document all project stakeholders | To communicate with stakeholders | To prioritize stakeholder requirements | To manage stakeholder expectations | A | The stakeholder register is used to identify and document information about project stakeholders.
148 | General | Which of the following is not a type of project life cycle? | Iterative | Predictive | Incremental | Continuous | D | Continuous is not a recognized project life cycle. The other options are valid project life cycle types.
149 | Scope | What is the primary purpose of the work breakdown structure (WBS)? | To define the project scope | To estimate project costs | To assign project resources | To create the project schedule | A | The WBS is a deliverable-oriented hierarchical decomposition of the work to be executed by the project team to accomplish the project objectives and create the required deliverables.
150 | Cost | Which of the following is not a type of project constraint? | Time | Scope | Cost | Quality | D | Quality is not typically considered a project constraint in the traditional "triple constraint" model. Scope, time, and cost are the primary constraints.
151 | Integration | What is the purpose of the change control board? | To document project changes | To implement approved changes | To review and approve or reject change requests | To communicate changes to stakeholders | C | The change control board is responsible for reviewing, evaluating, approving, delaying, or rejecting changes to the project.
152 | Communications | Which of the following is not a type of project communication? | Formal written | Informal written | Informal verbal | Formal verbal | B | Informal written is not typically categorized as a distinct type of project communication. The other options are recognized communication types.
153 | General | What is the primary purpose of the project management plan? | To define how the project will be executed, monitored, and controlled | To define the project scope | To assign project resources | To authorize the project | A | The project management plan is the document that describes how the project will be executed, monitored, and controlled.
154 | Procurement | Which of the following is not a type of project procurement? | Cost-reimbursable contracts | Performance-based contracts | Fixed-price contracts | Time and materials contracts | B | Performance-based contracts are not a standard type of project procurement. The other options are recognized procurement types.
155 | Cost | What is the purpose of the requirements traceability matrix? | To document project assumptions and constraints | To manage stakeholder expectations | To prioritize project requirements | To link product requirements to their origin and track them throughout the project lifecycle | D | The requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives.
156 | Schedule | Which of the following is not a type of project schedule network diagram? | Critical path method (CPM) | Activity-on-arrow (AOA) | Activity-on-node (AON) | Precedence diagramming method (PDM) | A | CPM is a method for calculating the critical path, not a type of network diagram. The other options are types of network diagrams.
157 | Risk | What is the primary purpose of the risk register? | To develop response strategies for all identified risks | To document identified risks and their characteristics | To prioritize risks based on their impact and probability | To monitor and control risks throughout the project | B | The risk register is used to record details of identified risks and their characteristics.
158 | Cost | Which of the following is not a type of project cost? | Fixed costs | Variable costs | Indirect costs | Direct costs | A | Fixed costs are not typically categorized as a distinct type of project cost. Direct, indirect, and variable costs are more commonly used categories.
159 | Resource | What is the purpose of the responsibility assignment matrix (RAM)? | To create the project schedule | To define project roles and responsibilities | To estimate project costs | To assign project resources | B | The RAM is used to illustrate the connections between work packages or activities and project team members.
160 | Quality | Which of the following is not a type of project quality tool? | Control chart | Gantt chart | Histogram | Cause-and-effect diagram | B | A Gantt chart is a scheduling tool, not a quality tool. The other options are recognized quality tools.
161 | Scope | What is the primary purpose of the project scope statement? | To define the project deliverables and work required to create those deliverables | To assign project resources | To authorize the project | To create the project schedule | A | The project scope statement describes the project's deliverables and the work required to create those deliverables.
162 | Risk | Which of the following is not a type of project risk response strategy? | Mitigate | Avoid | Ignore | Transfer | C | Ignoring risks is not a recognized risk response strategy. The other options are valid risk response strategies.
163 | Cost | What is the purpose of the project management information system (PMIS)? | To assign project resources | To estimate project costs | To create the project schedule | To provide a standardized set of tools for the project manager to collect, store, and distribute project information | D | The PMIS provides tools for the project manager to collect, store, and distribute information to stakeholders about the project's cost, schedule, and performance.
164 | Procurement | Which of the following is not a type of project closure? | Administrative closure | Financial closure | Contract closure | Technical closure | B | Financial closure is not typically categorized as a distinct type of project closure. Administrative and contract closures are more common terms.
165 | Communications | What is the primary purpose of the project communications management plan? | To identify all project stakeholders | To manage stakeholder expectations | To document project changes | To define how project communications will be planned, structured, monitored, and controlled | D | The communications management plan describes how project communications will be planned, structured, monitored, and controlled.
166 | Resource | Which of the following is not a type of project resource? | Material resources | Human resources | Equipment resources | Financial resources | D | Financial resources are not typically categorized as a distinct type of project resource. Human, material, and equipment resources are more common categories.
167 | Communications | What is the purpose of the project performance reports? | To authorize the project | To assign project resources | To provide information on project progress and performance | To define the project scope | C | Project performance reports provide information on the project's progress and performance.
168 | Resource | Which of the following is not a type of project team development technique? | Recognition and rewards | Training | Performance appraisals | Team-building activities | C | Performance appraisals are not typically considered a team development technique. The other options are recognized team development methods.
169 | Procurement | What is the primary purpose of the project procurement management plan? | To identify potential sellers | To define how procurement activities will be managed throughout the project | To evaluate seller proposals | To create procurement documents | B | The procurement management plan describes how procurement processes will be managed from developing procurement documents through contract closure.
170 | Resource | While working with the project team and conducting a brainstorming session, the project manager noticed that a lot of the ideas the team was coming up with were not organized. What tool can be used by the team to best visually organize their ideas? | Matrix diagram | Pareto diagram | Flowchart | Mind mapping | D | Mind mapping is a way to visually organize data.
171 | Quality | The project manager has noticed that a few team members are having a difficult time following the inspection process to check the quality of new software. What is the best tool to help them see the process, making it easier to follow? | Histogram | Flowchart | Process design chart | Control Chart | B | A flowchart is used to visually follow the steps in a process or multiple processes.
172 | Schedule | While working on an agile project, the sponsor would like to know how much work remains to be completed on the project. The project manager has scheduled a meeting with the sponsor for the next day. What tool would be best for the project manager to take to the meeting? | Project calendar | Burndown chart | Pareto chart | Earned value charts | B | A burndown chart is used on agile projects to show work that remains to be completed.
173 | Scope | The project team has finished 60% of the deliverables when management informs the project manager that the project will be canceled immediately and the team will be reassigned to work on a new project that management feels is more important. What should the project manager do right away? | Immediately released the team and start working on the new project | Return to planning to understand why the project might have been terminated | Inform the project team, conduct a lesson learned session, and formally release the team from the project | Inform management that the project cannot stop because the deliverables are 60% done | C | If a project is terminated before completion, the project manager should immediately move to the close project or phase process and formally close the project.
174 | Stakeholder | While managing the stakeholders' engagement, the project manager notices that some of the team members are not respectful to other team members. This has led to a few conflicts between the members. What can the project manager best do about this? | Implement ground rules | Release the team | Inform the sponsor | Stop the project | A | Ground rules are usually set within the team charter and are the general rules that the team will follow in order to effectively work with each other.
175 | Stakeholder | When an organization is considering a project, what are some of the factors that can influence why a project should get done? | Hiring new personnel | Making the company shareholders happy | Meeting regulatory, legal, or social requirements | Continuing the day-to-day work in a particular department | C | Reasons a project should get done include meeting regulatory, legal, or social requirements, satisfying stakeholders' needs, and implementing business changes.
176 | Cost | While attempting to determine the schedule for the project, the project manager has been informed from the team that each line of code will take about 15-45 minutes to write and debug. There will be about 1 million lines of code in the application. What schedule-estimating technique best describes this estimate? | Parametric | Top-down | Bottom-up | Analogous | A | Parametric estimates are based on a data set such as cost per feet or time per task.
177 | Resource | Project manager Mary was informed by the team that the constant conflicts in the project have slowed down the team so that they are now behind in the work. Mary is not sure what she did wrong while planning the project. She used a RACI chart to assign roles to each team member. She has assigned each activity to at least two people who will be held accountable for the work. What best explains the conflicts in the project? | Only one person should be held accountable for an activity when using a RACI chart. | A RACI chart is not a tool that you can use to assign work. | The team misread the RACI chart. | Mary should have used more than just an RACI. | A | When using a RACI chart, only one person should be held accountable per task on the chart.
178 | Quality | The datacenter redesign project is currently 30% complete. The project manager is not happy with the way processes are being followed by the team in ensuring that the network wiring will meet its quality requirements. What should the project manager do to improve the processes so as to meet the quality requirements with the network wiring? | Monitor and control project work | Control quality | Manage quality | Control scope | C | Manage quality is an executing process where you will improve processes by conducting audits and process analysis.
179 | Resource | The sponsor would like a report about the resources that are being used on the project. He would like to see them broken down by different categories to make them easier to understand. What process will the project manager use to create this? | Define activities | Develop schedule | Estimate activity resources | Sequence activities | C | The process of estimate activity resources will output the resource breakdown structure, which is a hierarchal breakdown of resources by their categories and types.
180 | Integration | A company has completed building a new datacenter. The project has many changes that were submitted to the change control board. Most changes were approved, and some were not. Which of the following is not a purpose of the change control board? | Deny changes whenever possible | Stop unnecessary changes | Assess changes | Manage the change control process | A | The change control board is not there to deny changes unless it has been assessed and deemed unnecessary in the project.
181 | Communications | What is considered the single most important skill a project manager should have? | Expert judgment | Technology | Communication | Business | C | Effective communication is the single most important skill a project manager should have.
182 | Resource | The project team is working with the customers to write the user stories. The customers have refused as they claim this would add no value to the project. What would be the best step to resolve this? | Have the team write the user stories | Ask the agile project manager to write the user stories | Educate the users why the user stories are valuable | Inform them user stories may not be needed | C | When managing an agile project, user stories will produce a lot of value to both the team members and the customers, as such it would be best to educate them on the value of the user stories.
183 | Resource | The project manager is currently estimating how many programmers will be needed to complete the financial software upgrade project. What document can the project manager use to determine who is available to work on the project? | Lessons learned register | Resource calendar | Availability calendar | Project team calendar | B | The resource calendar shows the availability of resources, both physical and team.
184 | Risk | While constructing a roof for a large building, the project team has identified the risk of a snowstorm. Due to the region in the country and the time of the year, the team has decided to take no action or preparations for the snowstorm. What risk response strategy is the team using? | Acceptance | Mitigation | Enhance | Avoid | A | Acceptance is a risk response where you will take no action against the risk.
185 | Resource | The product owner has added three new changes to the product backlog. The agile project manager has met with the team and they have decided immediately how to implement these new changes, although these changes will be implemented until three iterations from now. The product owner informs the agile project manager that he is not happy about this. What should the agile project manager do? | Inform the product owner of the potential risk of each change | Tell the team they should not have committed to doing these changes until they were ready to implement them | Ask the team members to implement the change right away | Ask the product owner when he would like the changes to be implemented | B | One of the core principles of agile is to defer decisions. This means not making decisions about potential changes or features until the very last minute.
186 | Scope | The project manager and the project team are reviewing the completed deliverables to see if they meet the performance requirements outlined in the requirements documentation. This is done so that when the customers are invited to inspect the deliverable, there will be no issues. What is the best output of this process? | Project management plan | Verified deliverables | Requirements documentation | Accepted deliverables | B | The process of quality control is when the deliverables are inspected to see if they meet the quality requirements. The output of this process is verified deliverables.
187 | Schedule | While working on a project, the project manager has been inspiring the team members to do the best they can, while also regularly communicating the project's vision to the team. What skill does this best describe? | Networking | Leadership | Active listening | Facilitation | B | Leadership skill is part of interpersonal and team skills. It is used to inspire people and to communicate the project's vision.
188 | Cost | Your company has decided to roll out a new Wi-Fi network for the staff. The sponsor has informed you that encryption on the network is mandatory. Where will the project manager document that the encryption was mandated by the sponsor? | Requirements traceability Matrix | Scope Baseline | Project scope statement | Requirements documentation | A | The requirements traceability matrix will trace the requirements back to their origins.
189 | Cost | A project has completed 60% of all the work. The team has spent 55% of the project budget. The budget is currently set at $180,000. The sponsor has requested the project's CPI. What CPI figure should the project manager provide? | $18,000 | 1.1 | .99 | $108,000 | B | CPI is equal to EV/AC. To find the CPI, you must first find EV and AC. EV is equal to the percentage of actual work completed x BAC (budget at completion), which is 60% x $180,000 = $108,000. AC (actual cost) is just the amount of money already spent on the project, which is 55% x $180,000 = $99,000. So, CPI is $108,000/$90,000 = 1.1.
190 | Cost | While managing a datacenter project, a few customers requested a feature be added to the project that will enhance the security system in the datacenter. The change was submitted to the change control board and was denied due to the high cost of the security system. A few months later another customer submitted the same change back to the project manager. What is the best step the project manager can take in this scenario? | Inform the customers the change cannot be done | Add the security system to the datacenter | Assess how this change impacts the project management plan | Inform the change control board | A | The best thing to do in this scenario would be to inform the customer that the change cannot be added due to the fact that it was already rejected by the change control board.
191 | Resource | Which technique should the agile team use to list the reasons for why a particular process was failing during iteration? | Short subjects | SMART goals | Check-in analysis | Fishbone analysis | D | A Fishbone analysis is done during the generate insight step in a retrospective to show the reasons for why something failed.
192 | Communications | The project manager is working on a top-secret company project and would like to ensure all the correct security measures are in place for communications regarding the project. What tool should the project manager use? | Access controls | Communication technology | Encryption | Communication models | B | Communication technology factors include sensitivity and confidentiality of the information on the project, which will require the project manager to assess the security needs of the project information.
193 | People | While managing a datacenter development project, the project manager has noticed there are many conflicts between the team members on the project. When managing a conflict in a project, what would be the best role for the project manager? | Facilitator | Advisor | Direct | Dictator | A | When managing conflicts in a project, the project manager should facilitate a satisfactory resolution for the conflict.
194 | Risk | Senior management would like your project to have as few risks as possible. Which of the following contracts best meets their criteria? | Cost plus fixed fee | Fixed price | Time and material | Cost reimbursable | B | A fixed price contract will have the lowest risk for the project, since the costs of the labor and material are known up front.
195 | Cost | The product owner has informed the project manager that all items in the product backlog are valuable and they should all get done. How should the agile project manager respond? | Inform the project team that all items should get done immediately | Prioritize the items himself | Educate the product owner on the benefits of prioritizing the product backlog | Agree with the product owner and try to immediately complete as many of the backlog items as possible | C | Part of being an agile project manager is to be an advocate for agile processes. This includes educating and teaching stakeholders on the benefits of agile.
196 | Process | The project team has been working very hard over the last 4 months to program the financial application and has completed it. The project manager has informed the team that the quality control team will be inspecting it next. What process group best describes what the team has done so far? | Planning | Monitoring and controlling | Closing | Executing | D | In the executing process group, the team completes the deliverables.
197 | Resource | The agile project team has determined that many of its processes have a lot of waiting and would like to remove all of the waste in the processes. What would be the best tool the agile team can use to improve their processes? | Fishbone analysis | Triple nickel | Value stream map | Process tailoring | C | A value stream map is a visual representation of the flow of information through a process in which you can identify waste, such as waiting time, and optimize the process.
198 | Schedule | While monitoring a large construction project, the project manager has calculated the SPI of the project to be 1.2. A contractor has informed the project manager that a delivery will be 1 week late. The 1-week delay is 10% of the project schedule. What would mostly likely happen to this project? | The project will finish behind schedule | The project will finish over budget | The project will finish ahead of schedule | The project will finish under budget | C | The current SPI is 1.2, which means the project is 20% ahead of schedule. A 10% delay should not cause this project to finish behind schedule.
199 | Quality | A project manager wants to ensure that the new cell phone the project is creating will beat or match the performance of new cell projects by other companies. What tool would be the best for the project? | Collect requirements | Meetings | Plan quality management | Benchmark | D | Benchmarking is a tool in plan quality management that is used to compare best practices to other projects, either within or outside of the organization.
200 | Cost | Which of the following is the best tool or technique for handling a multinational project team in a cost-effective way? | Visiting each functional manager to collect their requirements in person | Using collocation | Requesting a meeting with all functional managers in one location | Using virtual teams | D | Virtual teams are a cost-effective way to build multinational teams, allowing for collaboration across different countries without the need for expensive travel or relocation.
201 | Resource | When a project team implements new methods in addition to agile methods to increase efficiency, it is known as: | Process tailoring | Process analysis | Non-agile processes | Hybrid processes | A | Process tailoring refers to adapting or customizing existing processes, in this case, agile methods, to better fit the project environment and increase efficiency.
202 | Resource | What is the output of the process where a project manager utilizes rewards and recognition theories to keep the team motivated? | Team performance assessments | Individual and team assessments | Training | Virtual teams | A | The output of the process where a project manager uses rewards and recognition theories is team performance assessments, which evaluate the effectiveness of the team.
203 | Integration | What should a project manager do when there is no change control board to approve changes for a large utility project? | Approve the changes himself with the help of the project team | Ask the project sponsor to approve or deny the changes | Approve the changes himself | Establish a change control board for the project | D | For a large utility project, establishing a change control board is the best approach to ensure proper review and approval of changes.
204 | Scope | Which statement about quality management is true? | High-grade, low quality is okay | Low-grade, low quality is okay | Inspection leads to less prevention | Low-grade, high quality is okay | D | A low-grade (fewer features) product can still be of high quality, meaning it meets the specified requirements effectively.
205 | Communications | What should a project manager do when a project is terminated and a new project is to start immediately? | Write the charter for the new project | Get an authorized project charter for the new project | Inform the sponsor that the new project plan will take more than 2 days | Conduct the close project or phase process for the current project and write the final report | D | When a project is terminated, it's essential to formally close the current project before starting a new one, including documenting lessons learned and completing a final report.
206 | Cost | What is the difference between the product backlog and the iteration backlog? | The product backlog contains all project work, and the iteration backlog contains work for the next iteration | Both backlogs outline steps to manage the product and iteration | The product backlog contains all project work, and the iteration backlog contains steps to complete the work | The product backlog contains the work for the next iteration, and the iteration backlog contains all steps to complete the work | A | The product backlog contains all work needed for the entire project, while the iteration backlog focuses on work planned for the upcoming iteration.
207 | Resource | What technique describes assigning team members to no more than one activity at a time to prevent burnout? | Resource equalization | Resource movement | Resource crashing | Resource leveling | D | Resource leveling is the technique of adjusting the project schedule to prevent overallocation of resources, such as assigning team members to no more than one activity at a time.
208 | Schedule | What is the slack on a critical path activity? | Cannot be determined | 0 days | 1 day | 2 days | B | Activities on the critical path have zero slack (or float) because any delay in these activities will directly impact the project completion date.
209 | Stakeholder | Where should new knowledge gained on a project be documented? | Lessons learned register | Knowledge management register | Risk register | Opportunity register | A | The lessons learned register is used to document new knowledge gained during a project for use in current and future projects.
210 | Procurement | During which process are contractor payments made for a project with monthly payment terms? | Manage procurement | Plan procurement management | Control procurement | Conduct procurement | C | Control procurement is the process where payments are made to contractors according to the terms of the contract, which in this case is on a monthly basis.
211 | Resource | Where can a project manager best document different types of resources required for a project? | Resource requirements | Resource breakdown structure | Resource register | Resource category matrix | B | A resource breakdown structure is a hierarchical representation of resources by category and type, making it the best tool for documenting different types of project resources.
212 | Procurement | What should a project team do when they encounter a problem they cannot solve and want an outside company to finish the project? | Conduct a bidder conference | Rewrite the scope statement | Create a request for quotation | Create a request for proposal | D | A request for proposal (RFP) is used when seeking solutions to complex problems from external vendors, allowing them to propose how they would complete the project.
213 | Risk | What factors are considered when prioritizing risks during qualitative risk analysis? | Probability only | Impact only | Source of risks and impact | Probability and impact | D | Qualitative risk analysis prioritizes risks based on their probability of occurrence and potential impact on the project.
214 | People | What process is a project manager performing when resolving conflicts among team members? | Control Scope | Acquire Team | Manage Team | Control Resources | C | The Manage Team process involves resolving conflicts, improving team performance, and addressing interpersonal issues among team members.
215 | Cost | How should a project manager interpret and report a CPI of 1.1 and an SPI of 1.14? | The project is behind schedule and over budget due to scope creep | The project is progressing on schedule and budget | There have been many changes to the scope that have caused the project to be behind schedule | There have been many changes to the scope that have caused the project to be over budget | B | A CPI and SPI greater than 1 indicate that the project is under budget and ahead of schedule, respectively.
216 | Resource | What mistake did a project manager make when closing a project? | Not informing the PMO about releasing the team | Writing the final report after the lessons learned | Releasing the team and then doing lessons learned | Nothing, these are the normal steps to closing a project | C | Lessons learned should be conducted with the team before releasing them, to capture their insights and experiences from the project.
217 | Procurement | What should a project manager do when a contractor asks for more money for additional work not listed in the agreement? | Contact claims administration | Inform the sponsor | Tell the contractor they should not have done additional work | Inform the contractor that the project does not have the additional funds to cover the work | A | When there's a dispute over additional funds for work not in the original agreement, claims administration should be contacted to facilitate resolution.
218 | Cost | Which process describes consulting with banks and lending institutions to obtain project funds? | Plan cost management | Develop project charter | Determine budget | Determine project financing | C | The process of determining the budget includes activities such as consulting with financial institutions to secure project funding.
219 | Process | What is it called when planning is done at multiple points in time as data becomes available on an agile project? | Agile project planning | Progressive planning | Rolling wave planning | Elaborate planning | C | Rolling wave planning is an iterative approach where planning is done progressively as more information becomes available, which is common in agile projects.
220 | Scope | What should a project manager do after a change request is declined by the change control board? | Update the project management plan | Update the lessons learned register | Update the change log | Conduct perform integrated control | C | After a change request is declined, the change log should be updated to record the status and decision regarding the proposed change.
221 | General | What tool is best for visualizing a complex process with many paths and if/then scenarios? | Flowchart | Fishbone diagram | Histogram | Scatter diagram | A | A flowchart is an ideal tool for visualizing complex processes with multiple paths and decision points.
222 | General | Where should assumptions and constraints related to activity duration estimates be documented? | Basis of estimates | Project schedule | Cost estimates | Duration estimates | A | The basis of estimates document includes assumptions, constraints, and other factors considered when creating activity duration estimates.
223 | General | What can a project manager do to complete a project sooner by allowing some work to start before predecessor work is done? | Add reserves to each project activity | Add lead times between project activities | Add lag times between project activities | Add slack times between project activities | B | Adding lead times allows successor activities to start before their predecessors are completely finished, potentially shortening the overall project duration.
224 | Resource | What could a project manager have done to prevent miscommunication about resolved issues in a meeting? | Ensured that the meeting stayed on topic | Distributed detailed meeting minutes | Distributed a meeting agenda | Made sure the meeting was timed | B | Distributing detailed meeting minutes ensures all team members are informed about decisions and resolutions made during the meeting, preventing miscommunication.
225 | General | What estimation technique is used when providing a high-level estimate based on experience from a similar project? | Bottom-up estimates | Expert judgement | Analogous estimates | Parametric estimates | C | Analogous estimating uses parameters from similar past projects to provide a high-level estimate for the current project.
226 | Scope | What process should follow the approval of the scope statement? | Sequence activities | Define activities | Create scope baseline | Create WBS | D | After the scope statement is approved, the next logical step is to create the Work Breakdown Structure (WBS) to decompose the project scope into manageable work packages.
227 | Scope | What should a project manager do after receiving a completed deliverable from the project team? | Get acceptance from the project sponsor | Ask the team to review the deliverable | Close the project | Check the deliverable for quality requirements | D | Before accepting a deliverable, the project manager should verify that it meets the specified quality requirements.
228 | Cost | How should a customer add a new component to an Agile project? | Add it to the product backlog | Ask the agile project manager for permission to add it to the product backlog | Changes are not allowed on agile projects | Fill out a change request form | A | In Agile projects, new features or components are typically added directly to the product backlog for prioritization and future implementation.
229 | Resource | What is the purpose of a resource breakdown structure? | To estimate resource costs | To assign resources to project tasks | To list all project activities | To categorize project resources by type | D | A resource breakdown structure is used to categorize and organize project resources by type, such as labor, materials, and equipment.
230 | Stakeholder | A project manager realizes that stakeholder interests will conflict on a project and decides to utilize a stakeholder engagement assessment matrix. The matrix pinpoints an influential stakeholder who is resistant to the project. The project manager must align this stakeholder's expectations with the project's goals. How can the project manager accomplish this goal? | Gain consensus on project objectives by meeting with all stakeholders | Produce a stakeholder engagement plan | Convey the stakeholder engagement plan | Ensure that the stakeholder register is complete and updated | B | Plan Stakeholder Engagement is the process of developing approaches to involve project stakeholders based on their needs, expectations, interests, and potential impact on the project. The key benefit is that it provides an actionable plan to interact effectively with stakeholders.
231 | Stakeholder | A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across the globe. How can the project manager facilitate and optimize stakeholder engagement? | Create slides for the kick-off meeting to address stakeholder involvement | Verify that all required participants or their delegates will be available to attend | Survey stakeholders' preferred meeting dates and times to accommodate the teams in different time zones | Review the kick-off meeting agenda and materials for overall clarity and concision | C | Assuming a particular solution does NOT empower the team. Surveying the team and finding common consensus is a key part of servant leadership.
232 | Stakeholder | A project has the following characteristics: A functional manager is also a project stakeholder The functional manager has time constraints and delegates project responsibilities to someone else on the functional team. This person becomes a new stakeholder The new stakeholder is NOT attending meetings How should the project manager engage this new stakeholder? | Examine the stakeholder engagement plan with the new stakeholder and assess their level of engagement | Ask the new stakeholder to pair with a more experienced stakeholder to learn responsibilities | Present the project schedule and the specific, assigned tasks to the new stakeholder | Request that the functional manager brief this new stakeholder and ask that they send them to all relevant meetings | A | The f i rst version of the stakeholder engagement plan is developed after the Identify Stakeholder process has identified the initial stakeholder community. The stakeholder engagement plan is updated regularly to re f l ect changes to the stakeholder community.
233 | Cost | A project manager is working with three (3) key stakeholders. Each has a different vision regarding the project and its goal. They each feel strongly about their opinion. How should the project manager obtain approval of the project charter? | Use the project kick-off meeting to settle the project goals | Conduct a stakeholder analysis | Use facilitation and conflict management techniques to help the three (3) stakeholders find consensus | Request that the project sponsor resolve the conflict | C | To facilitate timely, productive discussion and decision making, the project manager should use their facilitation skills as well as conflict management to help the stakeholders agree on a shared vision of the project goals.
234 | Stakeholder | A small group of users complains during a project's user acceptance stage, stating that their expectations are NOT met. Which action could help avoid this issue on future projects? | Engage in risk assessments throughout the project | Send more frequent updates to stakeholders | Make use of stakeholder feedback during the project | Make use of conflict management techniques | C | Managing stakeholder engagement helps to ensure that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement.
235 | Stakeholder | A global organization sponsors a project that involves six (6) different companies. When the project is partially complete, the project manager learns that one stakeholder is ill and needs to decrease their level of involvement. What should the project manager do? | Update the stakeholder register and then the stakeholder engagement plan | Revise the project charter with the new stakeholder information | Ask the project sponsor to replace the stakeholder | Update the stakeholder engagement plan | A | Both the stakeholder register and the stakeholder engagement plan need updating. The stakeholder register identifies all stakeholders and their involvement in the project. The stakeholder engagement plan is updated to reflect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution.
236 | Resource | During work on a government project, stakeholders exert pressure on the project manager to comply with their preferred actions because they have extremely complex regulations and constraints. The project manager wants to build a successful relationship with these stakeholders because the company hopes to win more contracts with the government. Which two approaches should the project manager take? | Use servant leadership to build a relationship based on stakeholder needs E) Share the stakeholder engagement matrix with the team | Invite these stakeholders to team meetings to assure them that the project team takes their work seriously | Send a questionnaire out to this stakeholder group, asking about their needs | Assess and categorize these stakeholders using the Salience model | D | Both leadership and analytical project management tools are important in this scenario. The stakeholders need to earn trust in your team, but you—NOT the team—are the main point of contact. The best choice to facilitate trust is an effective leadership style that emphasizes the needs of your stakeholders. In a complex environment such as this one, the salience model of categorization is a good cho
237 | Stakeholder | Two (2) users complain during the project's user acceptance stage, saying that their expectations were NOT met. How could the project manager avoid this issue in the future? | Assess risks more thoroughly | Nurture a professional relationship with the users | Enable efficient stakeholder management | Employ conflict management techniques | C | Managing stakeholder engagement efficiently is key to ensuring that stakeholders clearly understand the project goals, objectives, benefits, and risks for the project, as well as how their contribution will enhance project success. Listening to their feedback is an important part of this engagement.
238 | Stakeholder | A project involves six different companies, and the project sponsor is a global organization. At the midpoint of the project, the project manager learns that one stakeholder is experiencing difficulties and CANNOT provide their former level of involvement. The project manager needs to __________ and then __________. (Fill in the blanks with the correct pair of answers.) | avoid the risk; update the stakeholder engagement plan | mitigate the risk; update the stakeholder register | avoid the risk; update the stakeholder register | mitigate the risk; update the stakeholder engagement plan | D | The first step is mitigating the risk presented by the stakeholder's diminished involvement. Then, the stakeholder engagement plan is updated to reflect any processes, procedures, tools, or techniques that affect the engagement of stakeholders in project decisions and execution.
239 | Scope | A company is struggling to define the scope of a new project that has multiple phases with a high level of dependency between the phases. How should the project manager approach this challenge? | Contract with a third-party consultant that specializes in helping businesses define scope of work on large projects | Review the project management plan to ensure that it provides extra time within the schedule, then revise the scope of work | Work with project stakeholders to recommend an iterative approach that will then help to define the project's scope | Move forward with the project but keep a daily check on the schedule to prioritize the dependency issues | C | A corrective action, such as the iterative approach, is required here. Introducing adaptive steps in a heavily predictive environment is never easy and the stakeholders should be involved in this process.
240 | Resource | Several new members are added to an ongoing project. Although all original team members received basic training on the specifics of the business operation that the project supports, the new members do NOT have the same basic understanding. This lack of understanding results in decreased productivity. How should the project manager respond to this issue? | Assure all new team members that they should feel comfortable asking for help from both the long-term members and project manager | Recognize that this is a common occurrence when teams experience changes and revise the schedule to allow for the slight decrease in productivity | Revise the team, so that the newer resources are moved to other projects and resources with relevant experience are added, then log lessons learned | Ask the original team members to provide support and training and schedule a second kick-off meeting for new team members | D | It is the project manager's responsibility to make sure that the new members are adequately trained. This approach provides that training.
241 | Schedule | A product owner in an agile project complains of too many meetings in their monthly schedule. There is NOT enough time for project work. They instruct the project manager to prioritize some meetings and decrease the frequency of others. Which two of the product owner's meetings could the project manager deprioritize so that they attend less frequently? | Sprint retrospectives | Product SME consultations | Daily standup meetings | Team performance reviews E) End-user feedback sessions | C | In agile projects, the customer is the highest priority, because this leads to end-user satisfaction and focus on delivery; administrative processes such as performance reviews are a lower priority. The product owner is NOT needed at every daily meeting.
242 | Cost | A deliverable on the project's critical path is behind schedule. The cost performance index (CPI) is 1.3. The project manager is able to put the project back on schedule. Which three results are the most likely for this project? | Costs will increase E) The team should expect rework | Project scope will be revised | Associated risks will increase | Activities will be performed in parallel | D | The cost performance index (CPI) is above 1; therefore, the project is spending money at a rate lower than planned. Since the project is behind schedule, its schedule performance index (SPI) is less than 1. In order to increase the SPI to 1, there will most likely be an increase in costs, perhaps from crashing activities on the critical path that will lower the CPI towards 1. This will most likely
243 | Cost | A project is 7 months into execution. The project manager determines that the cost performance index (CPI) is .80. According to a trend analysis, the CPI has a downward trend. What should the project manager do next? | Utilize the management reserve | Ask for additional resources | Crash the project schedule | Issue a change request to redo the cost baseline | D | Since the project is over budget and the trend analysis shows that this will continue, the best course of action is to redo the cost baseline of the project and manage it.
244 | Cost | A project has the following characteristics: US$3 million budget Planned value of US$630,000 Actual cost of US$650,000 Earned value of US$540,000 Which statement is true about the current status of the project? | The project is behind schedule and over budget | The project is ahead of schedule and under budget | The project is ahead of schedule and over budget | The project is behind schedule and under budget | A | CV = EV - AC: 540 - 650 = -110 (negative cost variance) SV = EV - PV: 540 - 630 = -90 (negative schedule variance) Negative cost variance means the project is over budget. Negative schedule variance means project is behind schedule.
245 | Resource | The project manager learns that one team member needs to complete a critical task that is outside of the project, resulting in a scheduling risk for the project. How can the project manager eliminate this risk? | Send a report to the project sponsor, documenting noncompliance from the member's manager | Tell the team member's manger to release the team member from outside activities until the scheduled project activity is complete | Meet with the team member's manager and negotiate for an alternative time to complete the other task | Ask the team member to focus on the critical task and obtain an additional resource from another department | C | The resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. This will provide guidance as to how the project manager can negotiate with the resource's manager.
246 | Cost | Over the past six months, the cost per story in agile project A has risen by more than 250% due to a faulty platform which is no longer supported. The project will exceed the budget increment threshold at the next iteration. Who should decide if the project should be cancelled? | The head of business control | The project manager | The product owner | The procurement manager | C | The product owner acts as the sponsor in agile projects and therefore has the authority to decide if conditions warrant termination of a project.
247 | Resource | A new product development project has the following characteristics: There are three (3) main tasks Task A must be delivered four (4) weeks before task C starts Once task B is finished, task C will start What is the relationship between tasks A and B? | Finish-to-start (FS) | Finish-to-finish (FF) | Start-to-start (SS) | Start-to-finish (SF) | B | While there is no direct relationship between A and B, both must be completed before C can start. So, of the choices, the only response that makes sense is FF.
248 | Resource | A team decides that an agile approach fits the needs of the next phase in their project. Unfortunately, some team members have NOT had the appropriate agile training. How should the project manager respond to the lack of agile training? | Transition some of these team members to other teams and replace them with resources with agile training | Ensure the project's contingency reserve can cover agile training for all team members | Create virtual training sessions for key team members, covering the main agile topics | Identify and implement the most cost-effective agile training for the team members | D | Training for project team members can result in added skills that could be useful for future phases or projects. The project manager should identify and implement agile training for team members. Training lessons and related costs should be evaluated and included in the resource management plan and cost and schedule baselines.
249 | Cost | A company is planning to utilize a new product that leverages innovative technologies and processes. The project manager has verified that the component work packages have been defined, and constraints for each component have been identified. Which estimating technique should the project manager use to obtain a precise cost estimate of the project? | Analogous | Bottom-up | Three-point | Parametric | B | Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower-level components of the WBS.
250 | Risk | A project manager is uncertain about the duration of a project for a new product and consults several groups of subject matter experts (SMEs). The first group advises that development can be finished in 40 days. The second group identifies some risks that could make the duration up to 60 days. The third group proposes a new development method that can shorten the time to 20 days. What is the estimated development duration for the new product? | 40 days | 30 days | 20 days | 60 days | A | Using three-point estimating (Triangular Estimate) = (Optimistic + Most Likely + Pessimistic)/3 = (20 + 40 + 60)/3 = 120/3 = 40 days Beta Estimate = (Optimistic + (4 X Most Likely) + Pessimistic)/6 = (20 + (4*40) + 60)/6 = 240/6 = 40 days
251 | Risk | A retiring project manager hands over all materials to a new project manager. The project appears to be running smoothly until a critical component fails during testing. What is the appropriate first step when responding to this issue? | Review the risk management plan to identify whether this risk and accompanying response strategies have been captured | Revise the timeline to account for slippage due to the additional time needed to implement mitigation | Communicate with stakeholders, describing the issue, proposed costs, and potential changes to delivery dates related to the project | Check with other local team project managers to see how they would respond to the issue | A | Risk responses to identified risks should be outlined as part of the risk management plan.
252 | Risk | A team member has taken unplanned leave during the execution of a project, causing the project team to reschedule some tasks. As a result, critical activities are now occurring at the same time. What is the first thing the project manager should do? | Mitigate risks by reverting to the original schedule | Identify suitable responses for the newly introduced risks | Revise the risk register and then rank the project's risks | Assess the newly introduced risks with the project team | D | The project manager and the project team should evaluate the newly discovered risk. The project manager should also update the risk register, analyze and prioritize the risk, and plan the response.
253 | Risk | A project sponsor is risk-averse and is therefore concerned about negative impacts on the project. To help with this concern, the project team identifies four (4) project risks and then evaluates both the probability of occurrence and the impact of the risk if it occurs. The team uses a 1-5 scale (1 is the lowest, and 5 is the highest). Based on the above information, in what order should the project manager rank these risks for risk management purposes? | C, D, A, B | A, C, B, D | D, A, C, B | B, A, D, C | B | The risk ranking is devised by multiplying the probability by the impact factors. Larger numbers indicate higher risks. Therefore, these risks are ranked in the following order: A, C, B, and D.
254 | Communications | While a project manager is preparing the monthly project status report, four (4) new risks are identified. These four (4) risks could affect key milestones. What should the project manager do before presenting this new risk information? | Review the organizational process assets and risk register | Refer to the risk management plan and the risk report | Review the risk report and lessons learned repository | Add risks to the risk register, analyze them for impact on the project, and identify response plans | D | The first step is to update the risk register and then analyze the new risks. This information can then be presented to stakeholders to help determine a response plan for each risk.
255 | Risk | Project C is a partnership between a major city and a government contractor. Each of these entities has a different risk threshold, so the project manager must ensure a risk approach that will satisfy both parties. Project C has a realistic schedule and an adequate budget; however, the project manager worries that unplanned events could threaten the project's success and cause the city sponsor to be concerned. How should the project manager handle this situation? | Ask the city sponsor for additional funding to uncover additional unplanned risks during planning | List and assess any project risks and present them to the city sponsor | Work with representatives from both sides of the partnership to address the potential impact of unplanned risks | Focus on the original project plan and focus on completing the plan on schedule | C | The project manager needs to be proactive and work with both partners to identify risks and their mitigation strategies. Even when one party has a higher risk threshold than the other, both parties should be consulted because they are in a partnership.
256 | Risk | After the start of a project, the project manager learns that an expected governmental subsidy may NOT be available. How should the project manager address this issue? | Make a change request | Raise the project's risk level | Log the risk | Make up any project deficit using the contingency reserve | C | While this is NOT an issue yet, it is a risk that should be entered into the risk log and managed appropriately.
257 | Resource | In order to speed the completion of project Z, a project sponsor requisitions a project team that can work a full 24-hour day, in three (3) shifts, in hazardous conditions. Team A: 02:00h – 10:00h Team B: 10:00h – 18:00h Team C: 18:00 – 02:00h To work nighttime hours safely, teams A and C will need to receive overtime pay, and the company will need to increase security measures and insurance coverage. Where should the project manager document this request in the project charter? | Work exclusions | Key stakeholder list | Overall project risks | High-level requirements | C | Speeding up a project does NOT come without risks. In this case, work may be completed much more quickly, but these risks need to be identified in the risk log for the project.
258 | Risk | After missing two (2) consecutive major deadlines because of delayed glass deliveries, a manufacturing company changed its glass supplier to meet production deadlines. Three (3) months later, production reports quality problems with the new glass. The project manager determines that the supplier change caused quality problems. How should the project manager avoid this issue in the future? | Evaluate new risks and update the probability and impact matrix | Confirm that an implemented risk response is effective | Review the assumption log to revisit or change current assumptions | Update the risk information to the lessons learned register | B | In this case, the risk was missed deadlines, and the response to the risk was to change suppliers. Part of an effective risk management strategy is ensuring the risk response is effective—in this case, the replacement supplier would supply quality glass on time. The Monitor Risks process uses performance information generated during project execution to determine if the response was effective. In
259 | Risk | A project manager implemented an approved change to manage a risk. Three (3) months after the implemented change, the project manager learns that the change did not produce the desired result, instead producing negative consequences. What should the project manager do FIRST to avoid this problem in future projects? | Update the list on the risk register with the risk. | Update the lessons learned register with the risk information. | Revisit or change existing assumptions after reviewing the assumption log. | Update the probability and impact matrix after assessing any new risks. | A | Updating the risk register with new information helps avoid similar problems in future projects by ensuring that the risk and its consequences are documented for future reference.
260 | Scope | A project is being implemented. The research and development department communicates to the project manager that the product's requirements have changed. These changes were not anticipated, may significantly influence potential sales numbers, and could impact project scope. Which action should the project manager take? | Plan to use the contingency reserve and update the risk mitigation plan. | Revisit the project charter. | Review the risk management plan to understand identify risk responses. | Evaluate the impacts to cost, stakeholders, quality, and risk using the Perform Integrated Change Control process. | D | When requirements change, it's crucial to evaluate the impacts on various aspects of the project using the Integrated Change Control process before taking any action.
261 | Risk | A project is at the planning stage. The project manager realizes that producing a complex, multi-functional application is not feasible with the current number of resources and decides to hire more resources to produce the application. The project manager identifies and contracts temporary resources. Which risk response strategy does this scenario exemplify? | Avoid | Transfer | Accept | Mitigate | D | By hiring additional resources to address the lack of capacity, the project manager is taking action to reduce the probability or impact of the risk, which is a mitigation strategy.
262 | Risk | A project is started with an approved scope. As the team implements the project design, a team member states that the product will not meet the requirements in certain situations. Correcting the issue increases the scope and costs, and the project will miss the deadline. The project sponsors do not have additional funding to support the project. What should the project manager do first? | Perform risk management analysis. | Contact the customer and negotiate for risk acceptance. | Follow the Perform Integrated Change Control process. | Crash the schedule. | A | Before taking any action, the project manager should first analyze the risks associated with the issue to understand its full impact and potential solutions.
263 | Risk | A project is being planned in a remote area with limited access to vehicles and equipment. Additionally, the road to the site goes through a protected area, and the government has required the company to sign a contract that they will protect the environment and road from damage. The project manager decides the best way to manage this risk is to deliver all heavy equipment themselves, despite the significant added expense. What type of risk response is the project manager demonstrating? | Accept | Transfer | Mitigate | Avoid | C | By deciding to deliver the equipment themselves despite the added expense, the project manager is taking action to reduce the probability or impact of the risk, which is a mitigation strategy.
264 | Cost | A company is constructing recycling plants in fifteen (15) countries worldwide. The lead in the project management office (PMO) wants more timely progress reporting and experience sharing between project managers in each geographically distant project. Which two agile methods might the PMO use to fulfill this need? | Definition of Done | Electronic Kanban board | Backlog refinement | Virtual daily standup meetings E) 2-week retrospective | B | An electronic Kanban board provides timely progress reporting, while bi-weekly retrospectives allow for experience sharing between project managers.
265 | Integration | A project manager works for a company preparing to develop a new product. The new product will require skills that are not currently available. To initiate this project, what should the project manager do? | Focus on quality control | Develop detailed project requirements | Document the risk in the project charter | Develop a competitor analysis | C | The lack of required skills is a significant risk that should be documented in the project charter to ensure it's addressed during project planning and execution.
266 | Resource | Before preparing a monthly project status report, a project team brings three risks to the project manager's attention. The project manager wants to reference additional information before presenting this as new risk information. Where can the project manager look to evaluate these risks? | Lessons learned repository | Risk register | Issue log | Risk management plan | B | The risk register is the primary document for recording and tracking project risks, making it the best source for evaluating newly identified risks.
267 | Risk | Although the sponsor and project team say that the new project has an adequate budget and realistic schedule, the project manager worries that unplanned events could threaten the project's success. What should the project manager do first? | Engage in the identification of project risks, then assess those risks. | Schedule a meeting with the functional manager to address the potential impact of unplanned risks. | Ask the project sponsor for additional funding to cover project planning. | Execute the project as planned and handle any risks as they arise. | A | Proactively identifying and assessing risks is the best first step to address potential threats to the project's success.
268 | Risk | A company wants to reduce future operating costs by installing solar panels on the facility being built by using a local government subsidy for energy- efficient projects. They have not yet applied for the subsidy. Before the project starts, the project manager describes project risks. Which statement best describes the risk to the project if the application is not successful? | Increase in scope | Loss of funding for the project | Loss of energy efficiency rating | Increased total cost | D | If the subsidy application is unsuccessful, the project will face increased total costs as it will not receive the expected financial support for the solar panel installation.
269 | Resource | The project sponsor requires a team composed of resources living in four (4) different time zones and working in four (4) different locations. The project sponsor did not consider the challenges created by this requirement and believes that the dispersion will provide an ideal project team that will save costs. Where should the project manager document this in the project charter? | In the overall project risks | In the key stakeholder list | As part of high-level requirements | As part of the resource management plan | A | The challenges created by a dispersed team should be documented as a risk in the project charter to ensure it's addressed during project planning and execution.
270 | Risk | During a conversation with a friend, a project manager hears that union action may occur within the next two (2) weeks. The project manager knows that at this stage of the project, any project delays could cause substantial harm to both the budget and schedule, and any union action will affect the project team. Earlier, the probability of a union action was considered minimal. Thus, it was unanticipated. Also, the project manager has worked successfully in the past with the union. How should the project manager respond to this issue? | Update the risk in the risk register with this new information and notify relevant stakeholders. | Get more information through informal discussion channels and use that information to decide on the next steps. | Plan to reward those who do not participate and identify possible disciplinary actions for those who do participate. | Schedule a meeting with the union's leader and use personal influence to attempt to resolve the problem. | D | Given the project manager's successful past relationship with the union, a proactive approach of meeting with the union leader is the best first step to address the potential issue.
271 | Cost | Due to resource challenges, a contractor is late with a critical project deliverable, even though the work is nearly complete. The project must be delivered on time because the next projects depend on the on-time completion of this one. There is a 22% buffer in the project budget for cost overruns, but only three (3) weeks left in the schedule. How can the project manager resolve this issue? | Escalate this issue to the project sponsor immediately. | Hold a discussion with the vendor regarding the contractual implications of this slippage and negotiate for on-time completion. | Use the buffer to look into alternative vendors that can assist with project deliverables and make use of the buffer. | Hire a new vendor to replace the current vendor. | B | With limited time left and most work completed, negotiating with the current vendor for on-time completion is the most efficient approach. This leverages the existing relationship and work done while addressing the critical timeline.
272 | Resource | A project is in the execution stage, and a change in the market pushes stakeholders to make the due date earlier. The project manager rapidly assigns skilled resources to build and establish the team. Which of the following would NOT be included in the project manager's next steps? | Plan suitable interactions for the team. | Assess the required skills for the project. | Train the new team. | Create a project schedule. | D | The project schedule should already exist at the execution stage. Assessing skills, planning interactions, and training the team are appropriate next steps after rapidly assigning resources.
273 | Risk | A customer's end users have not completed the required training. The project manager must consider the risk it poses to the project's timely completion. End-user training is a required project deliverable. Which action should the project manager perform? | Modify the project schedule to account for the training delay. | Dedicate additional post-implementation support to mitigate the risk. | Update the risk register to document the concerns and then develop a plan to ensure the end users complete their training. | Revise and discuss the risk register at the next project status meeting. | C | Documenting the risk and developing a plan to address it is the most proactive and comprehensive approach to handling the training delay issue.
274 | Scope | A project manager is working on a complex project with multiple stakeholders. The project is facing delays due to conflicting requirements from different stakeholders. What should the project manager do to address this issue? | Conduct a stakeholder analysis and prioritize requirements based on project objectives | Ignore the conflicting requirements and proceed with the original plan | Implement all stakeholder requirements without prioritization | Escalate the issue to senior management immediately | A | This approach allows the project manager to understand stakeholder needs and align them with project objectives, helping to resolve conflicts systematically.
275 | Risk | During the execution phase of a project, a team member identifies a potential risk that was not included in the initial risk register. What should the project manager do first? | Update the risk register and perform a qualitative risk analysis | Escalate the issue to the project sponsor for immediate action | Implement immediate mitigation strategies without analysis | Ignore the risk as it was not part of the initial assessment | A | This is the most appropriate first step as it documents the new risk and assesses its potential impact on the project before taking further action.
276 | Resource | A project team is struggling with communication issues, leading to misunderstandings and delays. What should the project manager do to improve team communication? | Rely solely on written communication to avoid misinterpretations | Implement a strict chain of command for all communications | Encourage open communication and establish clear communication channels | Reduce the frequency of team meetings to avoid information overload | C | This approach promotes transparency and clarity in team interactions, which can help resolve misunderstandings and improve overall communication.
277 | Cost | A project is running over budget, and the project manager needs to reduce costs without compromising quality. Which of the following strategies would be most effective? | Cut team member salaries to reduce labor costs | Extend the project timeline to spread costs over a longer period | Analyze the project for areas of potential cost optimization and efficiency improvements | Reduce the scope of the project without consulting stakeholders | C | This strategy allows for cost reduction without compromising quality or stakeholder relationships, focusing on improving efficiency within the existing project framework.
278 | Resource | During a project, a key team member unexpectedly resigns. What should the project manager do first? | Distribute the workload among remaining team members without analysis | Ignore the resignation and continue with the project as planned | Immediately hire a replacement without considering project needs | Assess the impact on the project schedule and resource allocation | D | Before taking any action, it's crucial to understand how the team member's departure affects the project, allowing for informed decision-making on next steps.
279 | Resource | A project manager is leading a global team across different time zones. What is the best approach to ensure effective collaboration? | Require all team members to work during the project manager's time zone | Rely solely on asynchronous communication methods | Establish a communication plan that accommodates different time zones and uses a mix of synchronous and asynchronous methods | Conduct all meetings during non-business hours for all team members | C | This approach balances the needs of team members across different time zones while ensuring effective collaboration through various communication methods.
280 | Scope | A stakeholder is consistently requesting changes that are out of scope for the project. How should the project manager handle this situation? | Ignore the stakeholder's requests completely | Review the change requests, assess their impact, and communicate the findings to the stakeholder, explaining the change control process | Escalate the issue to senior management without attempting to resolve it | Implement all requested changes without question | B | This approach addresses the stakeholder's requests professionally while maintaining project integrity through proper change control procedures.
281 | Risk | During the execution of a project, the team discovers that a critical assumption made during planning was incorrect. What should the project manager do first? | Blame the team member responsible for the incorrect assumption | Continue with the project as planned, ignoring the incorrect assumption | Assess the impact of the incorrect assumption on the project objectives and develop a mitigation plan | Immediately halt the project until a new plan is developed | C | This approach allows for a thorough understanding of the issue's impact and the development of an appropriate response without unnecessarily halting the project.
282 | Scope | A project is nearing completion, but the quality of deliverables is not meeting the expected standards. What should the project manager do? | Ignore the quality issues and focus on completing the project on time | Reduce the quality standards to match the current deliverables | Extend the project timeline indefinitely until quality standards are met | Conduct a root cause analysis of the quality issues and implement corrective actions | D | This approach addresses the underlying causes of quality issues, allowing for targeted improvements without compromising project timelines or standards.
283 | Resource | A project team is experiencing low morale and decreased productivity. What should the project manager do to address this issue? | Ignore the issue as it's not directly related to project deliverables | Conduct team-building activities and address any underlying issues affecting team performance | Implement stricter work policies and increase monitoring | Replace underperforming team members without investigation | B | This approach focuses on improving team dynamics and addressing root causes of low morale, which can lead to increased productivity and better project outcomes.
284 | Schedule | During a project, a critical vendor fails to deliver on time, jeopardizing the project schedule. What should the project manager do first? | Contact the vendor to understand the reasons for the delay and negotiate a recovery plan | Immediately terminate the vendor contract without discussion | Ignore the delay and hope to make up time elsewhere in the project | Extend the project deadline without consulting stakeholders | A | This approach allows for a collaborative solution with the vendor, potentially resolving the issue without drastic measures that could further delay the project.
285 | Quality | A project is using new technology that the team is unfamiliar with, leading to delays and quality issues. What should the project manager do? | Blame the team for not learning the technology quickly enough | Ignore the issues and hope the team figures it out eventually | Provide additional training and support to the team, and consider bringing in external expertise if needed | Replace the technology with a familiar alternative without analysis | C | This approach addresses the team's skill gap while maintaining project momentum, potentially improving both efficiency and quality.
286 | Cost | A project is facing budget constraints, and the project manager needs to reduce costs. Which of the following is NOT an appropriate cost-cutting measure? | Negotiating better rates with suppliers | Reducing the quality of deliverables without stakeholder approval | Identifying and eliminating non-essential activities | Optimizing resource allocation | B | This is not an appropriate cost-cutting measure as it compromises project quality without stakeholder consent, potentially leading to project failure or stakeholder dissatisfaction.
287 | Risk | During the execution of a project, a team member identifies a potential opportunity that could significantly benefit the project. What should the project manager do? | Implement the opportunity immediately without analysis | Ignore the opportunity as it wasn't part of the original plan | Assess the potential benefits and risks of the opportunity and present findings to stakeholders | Reprimand the team member for not focusing on assigned tasks | C | This approach allows for a thorough evaluation of the opportunity before taking action, ensuring that any potential benefits are weighed against risks and aligned with stakeholder expectations.
288 | Risk | A project manager is managing a software development project. The team has been using a waterfall approach, but they are considering switching to an agile methodology. What should the project manager do first? | Conduct a cost-benefit analysis of the change | Consult with stakeholders about the potential change | Train the team in agile methodologies | Immediately implement Scrum practices | B | Before implementing a significant change in project methodology, it's crucial to consult with stakeholders to ensure their buy-in and understand any potential impacts or concerns.
289 | Schedule | During a project status meeting, a team member reports that a critical task is behind schedule. What should the project manager do first? | Analyze the root cause of the delay | Update the project schedule | Assign additional resources to the task | Inform the project sponsor | A | Before taking any action, it's important to understand why the task is behind schedule. This analysis will inform the most appropriate response.
290 | Resource | A project team is experiencing conflicts due to cultural differences. What is the best approach for the project manager to address this issue? | Organize cultural sensitivity training for the team | Ignore the conflicts and focus on project tasks | Implement strict rules to prevent cultural discussions | Separate team members based on their cultural backgrounds | A | Cultural sensitivity training can help team members understand and appreciate each other's differences, leading to better collaboration and reduced conflicts.
291 | Communications | A stakeholder is consistently missing project meetings and not responding to communications. What should the project manager do? | Escalate the issue to the stakeholder's supervisor | Continue the project without the stakeholder's input | Attempt to understand the reason for the stakeholder's behavior | Remove the stakeholder from the project | C | Before taking any drastic action, it's important to understand why the stakeholder is not engaging. There may be underlying issues that can be addressed.
292 | Risk | During risk identification, a team member suggests a potential risk that seems highly unlikely. How should the project manager respond? | Dismiss the risk as it's unlikely to occur | Assign the team member to manage that specific risk | Ask the team member to provide more evidence | Include the risk in the risk register for further analysis | D | All identified risks should be recorded and analyzed, even if they seem unlikely. Further analysis will help determine the appropriate response.
293 | Risk | A project is nearing completion, but the customer requests a significant change to the project scope. What should the project manager do first? | Ask the team to work overtime to accommodate the change | Implement the change immediately | Reject the change request outright | Assess the impact of the change on the project | D | Before deciding whether to implement a change, it's crucial to understand its impact on the project's scope, schedule, and budget.
294 | Resource | During a project, a team member suggests an innovative solution that could potentially save time and resources. What should the project manager do? | Reject the idea to avoid disrupting the current plan | Evaluate the potential benefits and risks of the solution | Ask the team member to implement the solution independently | Implement the solution immediately | B | While innovation should be encouraged, it's important to carefully evaluate any new ideas to ensure they truly benefit the project without introducing unacceptable risks.
295 | Cost | A project is consistently over budget. What should the project manager do to address this issue? | Cut costs by reducing team size | Ignore the issue and hope it resolves itself | Request additional funding from the sponsor | Analyze the reasons for the budget overrun | D | Understanding why the project is over budget is crucial for developing an effective solution and preventing future overruns.
296 | Resource | A key team member unexpectedly resigns from the project. What should the project manager do first? | Redistribute the work among remaining team members | Inform the project sponsor of the resignation | Immediately hire a replacement | Assess the impact on the project schedule and deliverables | D | Before taking action, it's important to understand how the team member's departure will affect the project. This assessment will inform the best course of action.
297 | Resource | During a project, the project manager notices that team morale is low. What is the best approach to address this issue? | Offer financial incentives to boost morale | Conduct team-building activities | Threaten disciplinary action for poor performance | Ignore the issue as it's not directly related to project tasks | B | Team-building activities can help improve morale by fostering better relationships and communication among team members.
298 | Cost | A project is using earned value management. The Schedule Performance Index (SPI) is 0.8, and the Cost Performance Index (CPI) is 1.2. What does this indicate? | The project is behind schedule and under budget | The project is ahead of schedule and under budget | The project is ahead of schedule and over budget | The project is behind schedule and over budget | A | An SPI of 0.8 indicates the project is behind schedule (as it's less than 1), while a CPI of 1.2 indicates it's under budget (as it's greater than 1).
299 | Risk | A stakeholder is consistently requesting changes to the project scope. What should the project manager do? | Reject all change requests to maintain the original scope | Follow the established change control process for each request | Implement all requested changes without question | Ignore the stakeholder's requests | B | A formal change control process ensures that all changes are properly evaluated for their impact on the project before being approved or rejected.
300 | Resource | During a project, a team member reports a potential ethical violation by another team member. What should the project manager do first? | Immediately fire the accused team member | Investigate the allegation thoroughly | Report the issue to the media | Ignore the report to avoid conflict | B | Ethical violations are serious and should be investigated carefully before any action is taken.
301 | Resource | A project is using agile methodology, and the team is struggling with daily stand-up meetings. What should the Scrum Master do? | Extend the duration of the stand-ups | Reinforce the purpose and format of the stand-ups | Cancel the daily stand-ups | Replace stand-ups with weekly status reports | B | If the team is struggling with stand-ups, revisiting their purpose and format can help improve their effectiveness.
302 | Resource | During a project, the project manager notices that some team members are not following the communication plan. What should be done? | Eliminate the communication plan altogether | Implement stricter penalties for non-compliance | Allow team members to communicate as they see fit | Review and reinforce the importance of the communication plan | D | Reminding the team of the communication plan's importance and reviewing its contents can help improve adherence.
303 | Quality | A project is facing a tight deadline, and the team is considering cutting corners on quality to meet the timeline. What should the project manager do? | Extend the deadline without consulting stakeholders | Allow the team to cut corners to meet the deadline | Communicate the situation to stakeholders and discuss options | Ignore the quality issues and focus solely on the deadline | C | Transparency with stakeholders about project challenges is crucial. Discussing options allows for informed decision-making about how to proceed.
304 | Risk | During a risk assessment, the team identifies a high-impact, low-probability risk. What is the best approach to handle this risk? | Develop a detailed mitigation plan | Ignore the risk due to its low probability | Accept the risk without any action | Transfer the risk to another party | A | For high-impact risks, even if they have a low probability, it's important to have a plan in place to mitigate their potential effects.
305 | Resource | A project team is distributed across different time zones. What is the best way to ensure effective communication? | Use asynchronous communication tools | Eliminate the need for real-time communication | Require all team members to work in the same time zone | Hold meetings only during business hours in one time zone | A | Asynchronous communication tools allow team members in different time zones to collaborate effectively without requiring real-time interaction.
306 | Procurement | During a project, a key vendor fails to deliver a critical component on time. What should the project manager do first? | Blame the vendor publicly for any project delays | Assess the impact on the project schedule and deliverables | Ignore the delay and hope it doesn't impact the project | Immediately terminate the vendor's contract | B | Before taking any action, it's important to understand how the delay will affect the project. This assessment will inform the best course of action.
307 | Cost | A project is using a hybrid approach combining waterfall and agile methodologies. What is a key consideration for the project manager? | Strictly adhere to one methodology throughout the project | Randomly alternate between methodologies | Allow each team to choose their preferred methodology | Ensure clear communication about which methodology is used for each project phase | D | In a hybrid approach, it's crucial that all team members understand which methodology is being used at each stage of the project to avoid confusion.
308 | Risk | During a project, a team member consistently underperforms. What should the project manager do first? | Discuss the performance issues with the team member privately | Ignore the issue to avoid confrontation | Immediately fire the team member | Publicly criticize the team member to motivate improvement | A | Addressing performance issues privately allows for a constructive conversation and gives the team member an opportunity to improve.
309 | General | A project sponsor is pushing for a faster project completion date. What should the project manager do? | Analyze the impact of accelerating the schedule and present options | Agree to the new date without question | Extend the project timeline without informing the sponsor | Refuse to change the project timeline | A | Before agreeing to a faster completion date, it's important to understand the implications and present realistic options to the sponsor.
310 | Resource | During a project, the team discovers that a key assumption made during planning was incorrect. What should the project manager do first? | Immediately halt all project activities | Ignore the discovery and continue with the original plan | Blame the team member who made the assumption | Assess the impact of the incorrect assumption on the project | D | Understanding how the incorrect assumption affects the project is crucial for determining the appropriate response and any necessary adjustments.
311 | Process | A project is using agile methodology, and the product owner is not available for sprint planning sessions. What should the Scrum Master do? | Allow the development team to define sprint goals independently | Work with the product owner to ensure availability or designate a proxy | Proceed with sprint planning without the product owner | Cancel all sprint planning sessions | B | The product owner's involvement is crucial in sprint planning. If they can't be available, a designated proxy can ensure their perspective is represented.
312 | Risk | During a project, a team member suggests using a new technology that could potentially improve efficiency. What should the project manager do? | Implement the new technology immediately | Evaluate the potential benefits and risks of adopting the new technology | Allow the team member to use the technology without informing others | Reject the suggestion to avoid any changes | B | While new technology could improve efficiency, it's important to carefully evaluate its potential impact before implementation.
313 | Cost | A project is consistently delivering high-quality results but is behind schedule. What should the project manager focus on? | Reducing quality to meet the schedule | Extending the project timeline without stakeholder approval | Analyzing the reasons for the schedule delay and developing a recovery plan | Ignoring the schedule delay as long as quality is high | C | Understanding why the project is behind schedule is crucial for developing an effective plan to get back on track without compromising quality.
314 | Communications | During a project, a stakeholder expresses dissatisfaction with the project's progress. What should the project manager do first? | Escalate the issue to senior management without investigation | Listen to the stakeholder's concerns and seek to understand the root cause | Ignore the stakeholder's concerns | Immediately change the project plan to satisfy the stakeholder | B | Understanding the stakeholder's perspective is crucial for addressing their concerns effectively and maintaining positive stakeholder relationships.
315 | Resource | A project team is experiencing burnout due to long working hours. What should the project manager do? | Ignore the issue as burnout is normal in projects | Extend project deadlines without stakeholder approval | Implement mandatory overtime to complete the project faster | Assess workload distribution and consider resource adjustments | D | Addressing burnout is important for maintaining team productivity and morale. Assessing workload and making adjustments can help alleviate the issue.
316 | Risk | During a project, the team discovers a potential opportunity that wasn't identified in the initial planning. What should the project manager do? | Immediately pursue the opportunity without analysis | Ignore the opportunity as it wasn't in the original plan | Evaluate the potential benefits and risks of pursuing the opportunity | Ask the team to pursue the opportunity in their spare time | C | While new opportunities can be beneficial, it's important to carefully evaluate their potential impact on the project before deciding to pursue them.
317 | Resource | An integrated project delivery requires the development of both hardware and software. The project manager has received a customer-approved Gantt chart for the entire product development, and the customer wants to be involved during project execution. However, the software development team would like to introduce agile methodologies. What should the project manager do? | Adopt agile sprints to develop the project within the timeframe | Evaluate customer roles with the project management office (PMO) | Assess the best project methodologies for continued business value | Advise the team to follow the customer-approved Gantt chart strictly | C | Achieving continued business value is more important than choosing to adopt different methodologies. The whole purpose of project management is to execute work that provides identified business value. Thus the project manager should assess the best project methodologies for continued business value.
318 | Risk | Due to market changes, a company decided to speed up its product release schedule, moving from yearly cycles to quarterly cycles. The project manager views this as a great opportunity to use an agile life cycle, but upper management is not sold on the idea. What should the project manager do to increase the chances of success by using this approach? | Review the product backlog to identify some quick wins | Have the team work virtually and use the cost savings to speed up delivery | Seek sponsor approval for additional resources | Invite upper management to a digital transformation workshop | A | "Review the product backlog to identify some quick wins" is the best choice, as ensuring early benefit realization is one of the major benefits of an agile approach and a great way to address stakeholder concerns.
319 | Resource | A project team is in the planning phase of a complex project. The project has an end-date restriction for a new product with which the team has no previous experience. The project sponsor is requesting a detailed schedule, but the team cannot predict when tasks will occur throughout the project, especially because some depend on other business units. What life cycle methodology should the project manager use in this situation? | An agile life cycle including a detailed schedule in agreement with all business units | A predictive life cycle, including a schedule in agreement with all business units | A hybrid life cycle including a prioritized product backlog approved by the sponsor | An iterative life cycle, including task durations and a budget approved by the sponsor | C | Considering that the project has several stages, without full information about the detailed tasks and duration, but with a fixed due date, the project manager would best be advised to choose a hybrid approach and work with the sponsor to prioritize the functionalities or deliverables.
320 | Cost | During an iteration, the team spent twice as much time than expected because one of the product backlog items was complex and could not be split into smaller items. What should the project manager do? | Reprioritize the product backlog | Develop a risk management plan for this sprint | Incorporate a predictive approach for the rest of the project | Incorporate an adaptive approach for the rest of the project | D | The project manager should incorporate an adaptive approach for this project so the team can adapt to working on the complex task.
321 | Schedule | A product development project has run into design issues. As a result, the team has decided to change the approach of the product design phase from a predictive to an iterative approach. What should the project manager do to ensure a smooth transition between approaches? | Work with the team to establish a team site and product artifacts | Work with the product manager to define the number of iterations | Schedule a workshop with the team to plan the upcoming iterations | Schedule a meeting with the product manager to analyze user stories | C | The team must understand the advantages of moving from the existing predictive approach to an iterative approach. The project manager must schedule a workshop to plan for the upcoming iterations at the earliest. Hence this option is the correct answer.
322 | Resource | As an agile project is starting, one of the senior team members proposes using a new tool to store the project documentation. Before joining this group, she used the tool effectively in other jobs. What should the project manager do? | Ask the team to use the new tool for a trial period and then evaluate whether to continue using it | Ask the sponsor for approval and update the project governance guidelines | Ask the team for feedback regarding the tool, and if the team agrees, update the project governance guidelines | Check to see if the OPAs allow it and update the project governance guidelines, if this new tool is used | D | The first thing that the project manager should do is to check the OPAs to see if a tool is allowed. Processes, policies, and procedures are usually established by the project management office (PMO) or another function outside the project. They can be updated only by following the appropriate organizational policies associated with updating them.
323 | Resource | A new project has been assigned to an existing agile team. The previous project the team worked on was so successful that a senior stakeholder requested that the team use the same governance used in the previous project. What should the project manager do next? | Meet with the product owner to determine what project governance to use | Work with senior managers to adapt existing governance | Inform senior management that the same project governance can be used on the new effort | Confer with the project management office (PMO) to gain their insight on governance for the project | B | Regardless of Agile or even waterfall, the governance for an effort needs to be tailored to the project's specific needs, stakeholders, and customers.
324 | Resource | During a one-on-one session, a new team member shared their frustration regarding their inability to complete an assigned task, even after the team member put forth their best effort. What should the project manager do to address the team member's concerns first? | Encourage the team member to keep working hard on their assignments | Authorize additional training for the team member during the next month's educational series opportunities | Identify the root cause for why the team member cannot complete the assigned work and remediate | Adapt their leadership style based on the team member's needs | C | Interpersonal and team-building skills would need to be applied in this scenario because the team member is new, and the project manager should determine why the team member cannot complete the tasks. The project manager should identify the root cause for why the team member cannot complete the assigned work and remediate.
325 | Resource | An agile project team is struggling to keep track of the changes being applied to the product because its process is cumbersome and error-prone. What should the project manager do to address the issue? | Secure funds to acquire a software-based solution to speed up the process and reduce errors | Seek the sponsor's approval to stop following this process and assume the risk of eliminating it | Assign the responsibility for the process to a single person to ensure accountability in case of failure | Use the next retrospective to evaluate the process's effectiveness and determine if changes are needed | D | The project manager's first step is understanding the nature and cause of the problem. Using project retrospectives to evaluate the project process with the team and develop better solutions is a good way to implement continuous improvement and keep the team motivated and engaged. (
326 | Cost | A project manager is leading an agile project. One week into the project, a competitor announced they would launch a similar product soon. What should the project manager do next? | Ensure that the product backlog will deliver the minimum viable product (MVP) first | Hire a subject matter expert (SME) from the competitor company as a consultant | Cancel the sprint immediately and start a new sprint after determining the requirements for the next sprint | Ask the team members to continue delivering and address this issue at the retrospective | A | The project manager should ensure that the product backlog will deliver the minimum viable product (MVP) first. This approach allows the team to focus on delivering the most critical features quickly, which is essential when facing potential competition.
327 | Business Environment | At the beginning of a project, a stakeholder is concerned that the initiative may not deliver value to the organization. What should the project manager do to increase the chances of project success? | Provide continual communication of the project status to stakeholders | Perform an audit to make sure the benefits are realized | Review the business case and benefits management plan | Schedule training for everyone on the use of the new product | C | Reviewing the business case and benefits management plan is the best action to increase the chances of project success. This review will help the project manager understand the expected value and align the project activities accordingly.
328 | Resource | A company is expanding its product manufacturing to a new country. The date the company will start operating is set and broadly communicated, but the project team is unsure if there is enough time to implement all the product features. What should the project manager do to ensure enough time to implement the critical features on the committed date? | Escalate the concern to the executive level and request a new and feasible project due date | Collaborate with the project team to estimate the size of the minimum viable product (MVP) functionalities | Cut operations documentation because this can be completed after product delivery and operation starts | Add resources to the project team, increasing the velocity and enabling the team to deliver more value | B | Collaborating with the project team to estimate the size of the MVP functionalities is the best approach. This will help prioritize critical features and ensure their implementation within the given timeframe.
329 | Communications | A large organization, a project is experiencing communication difficulties. Team members and functional leaders express that they are informed too late, are not included in project discussions, or are unaware of important project delivery information. How should the project manager address this situation? | Send a regular email update to each functional manager regarding the project's status and next steps | Refer to the RACI chart on who needs to know what and when and ensure compliance | Ensure adherence to the agreed process as stated in the communications plan | Coordinate a meeting with the team leaders to find a solution | C | The project manager should ensure adherence to the agreed process as stated in the communications plan. This will address the communication difficulties and ensure that all stakeholders receive timely and relevant information.
330 | Resource | A team is working on an innovation project using an incremental approach. After every status meeting, some key stakeholders complain that they have not been briefed to prepare for the meeting. What should the project manager do to prevent this from occurring again? | Determine the meeting agenda with the key stakeholders, and share it in advance | Send the updated information to key stakeholders one day before the meeting | Ask the sponsor to align key stakeholders with the project's meeting cadence | Meet with the key stakeholders separately in advance before every status meeting | A | Determining the meeting agenda with key stakeholders and sharing it in advance is the best approach. This will allow stakeholders to prepare for the meeting and prevent complaints about lack of briefing.
331 | Communications | A director is acting as the product owner for a government software project. The director repeatedly cannot engage with the team and provide regular and important feedback on project artifacts. What should the project manager do to resolve this? | Recommend an open-door policy for the project | Determine communication preferences and review responsibilities | Obtain alternative feedback from the customer | Adopt a collaborative approach | B | The project manager should determine communication preferences and review responsibilities with the director. This will help establish a more effective communication channel and ensure the director understands their role as the product owner.
332 | Communications | The project manager discovers that one of the stakeholders keeps providing status reports to the steering committee that does not reflect the actual situation. Moreover, the stakeholder does not even have accurate information on the project. What should the project manager do? | Escalate the issue and request that all reports be preapproved before they are sent to the steering committee | Schedule a meeting with the steering committee and the stakeholder to reinforce the communications management plan | Update the communications management plan to ensure the stakeholder receives the necessary information | Send regular updates to the steering committee to inform them about the project | B | Scheduling a meeting with the steering committee and the stakeholder to reinforce the communications management plan is the best approach. This will address the issue of inaccurate reporting and ensure all parties understand the proper communication process.
333 | Communications | A stakeholder is concerned that the project is falling behind schedule based on unofficial information from the project team. Although some tasks have slipped, these tasks have free floats; otherwise, the project is on track. The project manager immediately contacted the stakeholder to show and explain the latest project status reports. What should the project manager do next? | Review the project's communications management plan with the project team and update it as necessary | Revise the status reports to identify delays that should be acted on clearly | Include the stakeholder in the project status mailing list | Issue a memo stating that the project status can only be shared through authorized channels | A | Reviewing and updating the communications management plan with the project team is the best approach. This will help address the issue of unofficial information being shared and ensure that all stakeholders receive accurate and timely project updates.
334 | Communications | During the execution phase of a healthcare IT project, the customer's project manager resigns. The key stakeholders are no longer getting updated information on time. What should the project manager do next? | Inform the key stakeholders directly | Update the project sponsors on the issue | Keep sending the information until a response is received | Update the communications management plan | D | Updating the communications management plan is the most appropriate action when there are changes in key stakeholders or communication channels. This will ensure that all stakeholders continue to receive timely and relevant project information.
335 | Risk | During a project team meeting, team members identify risks that may occur during the project. What analysis should the project manager perform in preparation for a meeting with the sponsor? | Expert judgment analysis | Quantitative risk analysis | Qualitative risk analysis | Monte Carlo risk analysis | C | Qualitative risk analysis is the most appropriate initial step for assessing risks identified by the team. It helps prioritize risks based on their probability and impact, providing a foundation for further analysis or response planning.
336 | Risk | A new product development project has been launched. The project sponsor has reviewed the risk analysis results as documented in the risk register and is confident the project will succeed. However, key investors are not as confident and want more information before investing. What should the project manager do? | Plan development activities to engage stakeholders in various phases of the project | Assess and describe all the risks associated with the product development and launch, then present a detailed risk management plan to the stakeholders | Prepare and present a cost-benefit analysis to investors | Present a detailed market analysis, business plan given by the product owner, and risk management plan to investors | D | Presenting a comprehensive package including market analysis, business plan, and risk management plan provides investors with the most complete information to make an informed decision about investing in the project.
337 | Resource | An agile team created a risk register for a project. All initial risks were identified using stakeholder interviews, workshops, and information from the project charter. What should the project manager do to manage the risk register and the associated risks for the remaining project duration? | Add risks as an agenda topic in daily standup meetings | Assess and prioritize the risks during each sprint retrospective meeting | Update the risk register and review risks with the team regularly | Eliminate all project risks using iterative risk management | C | Regularly updating the risk register and reviewing risks with the team is the best ongoing approach for managing project risks in an agile environment. This ensures that risk management remains an active and continuous process throughout the project.
338 | Risk | An entrepreneur has undertaken a software development project. The project charter was approved, and a project manager was appointed. There is an urgent requirement to deliver the project because of an unforeseen political risk. The sponsor wants to see a report of any expected delays. Which tool should the project manager use to prepare the report? | Milestone list | Quality reports | Root cause analysis | Trend analysis | D | Trend analysis is the most appropriate tool for forecasting potential delays based on past performance data. It can help the project manager identify and report on expected delays as requested by the sponsor.
339 | Risk | While reviewing progress, in the middle of an iteration, the Scrum Master points out a major risk due to a user story dependency. What should the project manager do next? | Update the product backlog to include the dependency | Update the impacted plans and monitor the risk | Involve the team in completing risk analysis | Enter the risk in the iteration's risk register | C | Involving the team in completing risk analysis is the best immediate action when a new risk is identified during a sprint. This collaborative approach leverages the team's expertise to assess and plan for the risk.
340 | Risk | Some of the project's materials have been ordered from overseas. The project team has concerns that the materials may not reach the site on time due to a customs clearance delay that will affect the critical path. How should the project manager handle this concern? | Identify the root cause of the delay and add it to the issue log | Ensure the suppliers cover any additional costs due to the delay | Revisit the risk register and implement the respective risk response | Ask the logistics team to arrange an expedited clearance | C | Revisiting the risk register and implementing the planned risk response is the most appropriate action. This assumes that the risk of customs delays was previously identified and a response plan was developed.
341 | Stakeholder | A large transformation project is in progress. This project requires cross- functional effort from various business teams. Which two actions should the project manager take to complete the stakeholder register? | Break down the project by domain areas | Contact each potential stakeholder directly and ask if they are interested in joining the project E) Discuss the project with team members and assemble the register at a team meeting | Ask for referrals from the business sponsor or senior leadership | Analyze the interest, influence, and impact of potential stakeholders from each business team | D | These actions help systematically identify and analyze stakeholders across all relevant areas of the project, ensuring a comprehensive stakeholder register.
342 | Stakeholder | A project manager is leading a project where a low-level stakeholder has just been promoted to a new position and has become a high-level stakeholder. What should the project manager update to ensure the proper involvement of this stakeholder in the project? | Stakeholder engagement plan | Resource management plan | Communications management plan | Risk management plan | A | The stakeholder engagement plan should be updated to reflect changes in stakeholder positions and influence, ensuring appropriate engagement strategies are in place for each stakeholder.
343 | Stakeholder | At what point in an agile project should a project manager engage stakeholders? | Throughout the project life cycle | At the start of the project | At the end of the project | When challenges are encountered in the project | A | Stakeholder engagement should be an ongoing process throughout the entire project life cycle to ensure continuous alignment and support.
344 | Cost | A project team, who is installing a fiscal metering system for a crude oil terminal, requested a metering system, conducted a factory acceptance test, and delivered meters to the terminal for installation. While onsite, local regulators declined approvals for the meters due to a breach of statutory procedures. The regulators were required to participate in the factory acceptance tests. This issue led to delays in completing testing and overall impacted the project cost and schedule. How could the project manager have prevented this situation? | Notified stakeholders of the factory acceptance tests for meters | Ensured compliance with the stakeholder requirements | Referred to lessons learned from previous projects | Revised the stakeholder engagement plan | B | Ensuring compliance with stakeholder requirements, especially regulatory requirements, is crucial to prevent issues like the one described in the scenario.
345 | Stakeholder | A project manager is managing a construction project that is 40% through the execution phase. The project sponsor has asked the project manager to ensure all key stakeholders are committed. How should the project manager assess the stakeholders' current engagement levels? | By analyzing the most updated issue log | By reviewing and updating the communications management plan | By reviewing the stakeholder engagement assessment matrix | By asking key stakeholders to submit a signed declaration | C | The stakeholder engagement assessment matrix provides a comprehensive view of current and desired stakeholder engagement levels, making it the most appropriate tool for this assessment.
346 | Risk | A project is close to completion when an unidentified and influential stakeholder appears and threatens to jeopardize the project by not approving the closing documents. Which two actions should the project manager have done to avoid this? | The stakeholder should have come forward for proper identification at the beginning of the project | The project manager should have carried out stakeholder identification during the initiation stage of the project | Creating awareness of the stakeholders' concerns should have been continuously occurring throughout the project E) Identifying and analyzing stakeholders should have been performed as an ongoing task throughout the project duration | The project owner should have informed the project manager about the project's stakeholders | B | These actions ensure that stakeholders are identified early and continuously throughout the project, reducing the risk of overlooking influential stakeholders.
347 | Stakeholder | A project manager has recently been assigned to an existing multinational project and is unfamiliar with the key stakeholders. What should the project manager do? | Ask for the opinion or expert judgment of the sponsor | Request a meeting with the resource manager | Identify the communications tool and update the plan | Review and update the stakeholder register | D | Reviewing and updating the stakeholder register is the most appropriate action for a new project manager to familiarize themselves with key stakeholders and their roles in the project.
348 | Cost | A company is transitioning from a predictive approach to a hybrid predictive-agile project implementation. The leadership team is concerned about benefits realization and is closely following up on one of the project iterations with the project manager. What should the project manager do in this situation? | Demonstrate the business value to the leadership team and get their buy- in | Update the leadership team with a quantifiable value report for each iteration | Wait for the leadership team to share the benefits realization updates for each iteration with management | Keep delivering iterations of the solution and show the benefit increments to the leadership team | B | Providing quantifiable value reports for each iteration helps demonstrate the benefits realization to the leadership team in a hybrid agile- predictive environment.
349 | Cost | A project manager has a newly formed team that includes junior members who have not worked on projects before. The product owner wants to ensure that the team works together on the right items in the sprint. What should the project manager do? | Allocate specific times during the project to mentor team members on agile processes | Improve productivity through the use of Scrum techniques | Communicate project information and updates effectively | Emphasize the importance of sprint backlog prioritization to the team and product owner | D | Emphasizing the importance of sprint backlog prioritization ensures that the team focuses on the most important items first, addressing the product owner's concern about working on the right items.
350 | People | An extremely talented and results-oriented team member suddenly struggles with a personal problem. Due to this, there is a change in the team member's behavior, which starts to affect the project deliverables and the morale of other team members. What should the project manager do? | Add the situation to the project issue log | Empathize to help the team member overcome their problem | Assign the team member to another activity | Ask the human resources (HR) manager to handle the issue | B | Empathizing with the team member and helping them overcome their personal problem is the most appropriate initial response, demonstrating emotional intelligence and supporting team morale.
351 | Resource | A project manager handling multiple projects in five countries has issued a new directive on workplace attire and office arrangements. It has been met with resistance in three countries, resulting in misunderstandings with the project manager. What should the project manager have done? | Assessed the cultural and personal traits in the various countries before issuing a general directive | Obtained a list of preferences from the team members before issuing a general directive | Contacted senior management before issuing a general directive | Determined the socioeconomic status of the team members before issuing a general directive | A | Assessing cultural and personal traits before issuing a general directive helps prevent misunderstandings and resistance in a multinational project environment.
352 | Risk | Production of a specific machine in a factory was contracted through a foreign supplier. Before delivering the final two components, the supplier informs the project manager that they must renegotiate prices or the components will not be delivered. What should the project manager do first? | Initiate the response plan for this risk entry based on the trigger | Work with the supplier to negotiate new prices to minimize cost impact | Approach alternative suppliers for the remaining two components | Raise a legal case with the company for breaching the contract | A | Initiating the pre-planned response for this risk is the most appropriate first action, assuming that the risk of supplier issues was previously identified and a response plan was developed.
353 | Quality | A project manager is leading a construction project. The project is in the execution phase, and the project manager notices that the team is not following the quality management plan. What should the project manager do? | Update the quality management plan to reflect the current practices | Conduct a root cause analysis to understand why the plan is not being followed | Implement corrective actions to ensure compliance with the quality management plan | Escalate the issue to senior management for resolution | B | Conducting a root cause analysis is the best initial action to understand why the quality management plan is not being followed, allowing for more effective corrective actions.
354 | Scope | A project team is working on a software development project using an agile methodology. The product owner keeps changing the requirements, causing frustration among team members. How should the project manager address this situation? | Refuse to accept any more changes from the product owner | Ask the team to be more flexible and accommodate all changes requested by the product owner | Educate the product owner about the impact of frequent changes on the team's productivity | Implement a change control process to manage requirement changes | D | Implementing a change control process helps manage requirement changes in an agile environment, balancing flexibility with stability and addressing the team's frustration with frequent changes.
355 | Communications | A project manager is working on a complex project with multiple stakeholders. During a project meeting, two stakeholders have a heated argument about the project direction. What should the project manager do to resolve this conflict? | Ignore the conflict and continue with the meeting agenda | Schedule a separate meeting to address the conflict | Ask the project sponsor to mediate the conflict | Encourage the stakeholders to resolve the conflict themselves | B | Scheduling a separate meeting to address the conflict is the most appropriate action. It allows the project manager to focus on resolving the conflict without disrupting the current meeting, and provides a dedicated time to hear both stakeholders' perspectives and work towards a resolution.
356 | Resource | A project team is experiencing low morale due to long working hours and tight deadlines. What is the best approach for the project manager to improve team morale? | Organize team-building activities outside of work hours | Offer financial incentives for meeting deadlines | Communicate the project's importance and recognize team efforts | Extend project deadlines to reduce pressure on the team | C | Improving team morale is best achieved by acknowledging the team's hard work and helping them understand the significance of their contributions. This approach addresses the root cause of low morale without resorting to unsustainable solutions like extending deadlines or requiring additional time commitments from an already overworked team.
357 | Resource | During a project status meeting, a team member raises concerns about potential risks that were not identified in the initial risk assessment. How should the project manager respond? | Dismiss the concerns as it's too late to add new risks | Thank the team member and add the risks to the risk register | Ask the team member to submit a formal risk report | Consult with the project sponsor before taking any action | B | The project manager should appreciate the team member's proactive approach and incorporate the new risks into the risk register. This ensures that all potential risks are documented and can be properly assessed and managed throughout the project lifecycle.
358 | Schedule | A project is falling behind schedule, and the project manager needs to fast- track some activities. Which of the following is an example of fast- tracking? | Reducing the project scope to meet deadlines | Performing activities in parallel that were originally sequenced linearly | Extending the project deadline to accommodate delays | Adding more resources to critical path activities | B | Fast-tracking involves performing activities in parallel that were originally planned to be done in sequence. This technique can help compress the project schedule without necessarily adding resources or changing the project scope.
359 | Risk | A stakeholder is consistently late in providing crucial feedback, causing delays in the project. What is the most appropriate action for the project manager to take? | Set up a meeting to discuss the impact and find a solution | Proceed with the project without waiting for the stakeholder's input | Remove the stakeholder from the communication list | Escalate the issue to senior management | A | The most appropriate action is to meet with the stakeholder to discuss the impact of their delayed feedback and collaboratively find a solution. This approach addresses the issue directly while maintaining a positive working relationship with the stakeholder.
360 | Resource | Which of the following is NOT a characteristic of a high-performing project team? | Open and effective communication | Shared commitment to project goals | Clear roles and responsibilities | Homogeneous skill sets among team members | D | High-performing teams typically benefit from diverse skill sets, not homogeneous ones. Diversity in skills and experiences allows the team to tackle a wide range of challenges and promotes innovative problem-solving.
361 | Resource | A project manager notices that team members are reluctant to share negative information during status meetings. What should the project manager do to encourage open communication? | Share examples of how addressing issues early benefits the project | Implement an anonymous reporting system | Conduct one-on-one meetings with team members | Penalize team members who withhold information | A | By sharing concrete examples of how early issue identification and resolution benefit the project, the project manager encourages open communication and creates a culture where team members feel safe sharing both positive and negative information.
362 | Resource | Which of the following is an example of a project constraint? | Project objectives | Stakeholder expectations | Team member skills | Available resources | D | Available resources, such as budget, personnel, or equipment, are typical project constraints. These factors limit the options available to the project team and must be considered in project planning and execution.
363 | Resource | A project manager is preparing for a kick-off meeting with a new project team. What should be the primary focus of this meeting? | Establishing team norms and communication protocols | Reviewing the project's risk management plan | Discussing the project budget in detail | Assigning specific tasks to team members | A | The primary focus of a kick-off meeting should be to establish team norms and communication protocols. This sets the foundation for effective teamwork and ensures all team members are aligned on how they will work together throughout the project.
364 | Cost | Which of the following is NOT typically included in a project management plan? | Schedule management plan | Scope management plan | Risk management plan | Detailed project budget | D | While the project management plan includes various subsidiary plans, a detailed project budget is typically part of the cost management plan, not the overall project management plan itself.
365 | Risk | A project manager is working on a project with a fixed deadline. The project is at risk of not meeting this deadline. What is the BEST course of action? | Add more resources to the project team | Extend the deadline without consulting stakeholders | Analyze options and present them to key stakeholders for decision | Reduce the project scope to meet the deadline | C | The best course of action is to analyze the available options (such as reducing scope, adding resources, or extending the deadline) and present these to key stakeholders for a decision. This approach ensures informed decision-making and stakeholder buy-in.
366 | Integration | What is the primary purpose of a lessons learned session at the end of a project? | To improve future project performance | To celebrate project successes | To finalize the project documentation | To assign blame for project failures | A | The primary purpose of a lessons learned session is to identify successes and failures in the project, with the goal of improving performance on future projects. This process contributes to organizational learning and continuous improvement.
367 | Scope | A project manager is working on a project where the stakeholders have conflicting requirements. What is the BEST approach to resolve this issue? | Implement all requirements to satisfy all stakeholders | Choose the requirements of the most influential stakeholder | Ignore conflicting requirements and proceed with the project | Facilitate a meeting to find a compromise solution | D | Facilitating a meeting to find a compromise solution is the best approach to resolving conflicting stakeholder requirements. This allows all parties to express their needs and work together to find a mutually acceptable solution.
368 | Scope | Which of the following is an example of a project deliverable? | Updated risk register | Project status report | Team performance evaluation | Completed software module | D | A completed software module is an example of a project deliverable. Deliverables are tangible or intangible products or results that are produced to complete a project or part of a project.
369 | Schedule | A project team member consistently misses deadlines, affecting the overall project schedule. What should the project manager do FIRST? | Reassign the team member's tasks to others | Report the issue to the team member's functional manager | Meet with the team member to understand the root cause | Remove the team member from the project | C | The first step should be to meet with the team member to understand the root cause of the missed deadlines. This allows the project manager to identify any underlying issues and work with the team member to find an appropriate solution.
370 | Scope | What is the purpose of a Work Breakdown Structure (WBS) in project management? | To assign resources to project activities | To break down the project work into manageable components | To estimate the project budget | To define the project's organizational structure | B | The primary purpose of a Work Breakdown Structure (WBS) is to break down the project work into smaller, more manageable components. This helps in planning, estimating, and controlling project work.
371 | Integration | A project is experiencing scope creep due to constant changes requested by stakeholders. What should the project manager do to address this issue? | Extend the project timeline to accommodate all changes | Implement a formal change control process | Reject all change requests to maintain the original scope | Allow all changes to satisfy stakeholders | B | Implementing a formal change control process is the best way to address scope creep. This ensures that all changes are properly evaluated, approved, and integrated into the project plan before implementation.
372 | Communications | Which of the following is NOT a characteristic of an effective project communication plan? | Outlines procedures for escalating issues | Specifies communication methods and frequency | Identifies key stakeholders and their communication needs | Includes all possible project information in every communication | D | An effective communication plan should not include all possible project information in every communication. Instead, it should tailor the information to the needs of different stakeholders and the purpose of each communication.
373 | Resource | A project manager is working on a project with a diverse team spread across different time zones. What is the BEST approach to ensure effective team collaboration? | Assign a team lead in each time zone to manage local team members | Schedule daily video conferences at a time convenient for the majority | Require all team members to work during the project manager's time zone | Use asynchronous communication tools and set clear expectations | D | For a team spread across different time zones, using asynchronous communication tools (like email, project management software, or shared documents) and setting clear expectations for response times and updates is the most effective approach. This allows team members to collaborate without requiring everyone to be available at the same time.
374 | Resource | What is the primary purpose of a project kick-off meeting? | To finalize the project budget | To assign all project tasks | To complete the project charter | To align the team on project goals and expectations | D | The primary purpose of a project kick-off meeting is to align the team on project goals and expectations. This sets the tone for the project, ensures everyone understands their role, and establishes a shared vision for project success.
375 | Scope | A project is nearing completion, but the project manager notices that the quality of deliverables is not meeting the expected standards. What should the project manager do? | Blame the team for poor performance | Extend the project timeline to improve quality | Accept the lower quality to meet the deadline | Conduct a root cause analysis and implement corrective actions | D | When facing quality issues near project completion, the best approach is to conduct a root cause analysis to understand why the quality is not meeting standards, and then implement corrective actions. This addresses the underlying issues rather than just extending the timeline or accepting lower quality.
376 | Resource | Which of the following is an example of a project assumption? | Key resources will be available when needed | The project sponsor must approve all major decisions | The project must be completed within 12 months | The project budget is $1 million | A | An assumption in project management is a factor that is considered to be true, real, or certain without proof or demonstration. Assuming that key resources will be available when needed is an example of a project assumption.
377 | Resource | A project manager is leading a project in a matrix organization. What is likely to be a challenge in this environment? | Unclear project objectives | Limited access to resources | Excessive project documentation | Lack of project authority | D | In a matrix organization, project managers often face challenges related to lack of direct authority over team members, as team members typically report to functional managers. This can make it difficult to manage resources and priorities effectively.
378 | Resource | What is the purpose of a RACI matrix in project management? | To define the project schedule | To identify project risks | To clarify roles and responsibilities | To allocate the project budget | C | A RACI (Responsible, Accountable, Consulted, Informed) matrix is used to clarify roles and responsibilities in a project. It helps ensure that all project activities have clear ownership and that stakeholders understand their involvement in different tasks.
379 | Resource | A project team is experiencing conflicts due to cultural differences. What should the project manager do to address this issue? | Separate team members based on their cultural backgrounds | Ignore the cultural differences and focus on the work | Implement strict rules to suppress cultural expressions | Provide cultural sensitivity training and promote open dialogue | D | To address conflicts due to cultural differences, the project manager should provide cultural sensitivity training and promote open dialogue. This approach fosters understanding, respect, and effective communication among team members from diverse backgrounds.
380 | Resource | A project manager is planning for a project team that will soon start work on a critical subsystem. Two technical alternatives are identified for the subsystem, but it is unclear if either alternative will perform satisfactorily. The project will be compromised if the performance of the critical subsystem falls short. What should the project manager do first? | Add subsystem performance to the issue log and assign an owner for that issue. | Direct the team to assess and evaluate the alternatives for the subsystem. | Schedule work for the most promising alternative and add management reserve for the other alternative. | Advise stakeholders of the major risk to the project posed by the subsystem's performance. | B | The project manager should direct the team to assess and evaluate the alternatives for the subsystem before scheduling the work. The data to support the decision of the alternative to implement must be generated and evaluated before the implementation is planned. Swarming is an appropriate way to do this.
381 | Resource | A project manager realizes that some newly hired team members have not been as productive as hoped, putting the project at risk. What should the project manager do to resolve this issue? | Provide additional training to the new team members. | Conduct job shadowing within the project team. | Tell the team that productivity must improve. | Institute project milestone completion incentives. | B | If project team members lack the necessary management or technical skills, such skills can be developed as part of the project work. Scheduled training takes place as stated in the resource management plan. Unplanned training, such as job shadowing, occurs due to observation, conversation, or project performance appraisals conducted during the management of the project team. Job shadowing can quic
382 | Resource | A project follows a strategic plan that includes key milestones that have been aligned with stakeholders. As the work is being executed, new tasks and important dependencies prevent the work from progressing as planned. The team cannot determine who should make decisions and take action on the new tasks and dependencies. What will help the project manager resolve this issue? | Use a RACI chart to facilitate team task accountability. | Use a Gantt chart to ensure milestones are accomplished. | Use a work breakdown structure (WBS) to ensure requirements are covered. | Ask the sponsors who have responsibility. | A | A RACI (responsible, accountable, consult, and inform) chart shows the project resources assigned to each work package. It illustrates the connections between work packages, activities, and project team members.
383 | Resource | An agile team replaced a key member. One of the stakeholders is concerned that the project will not be delivered on time because of the new team member. What should the project manager do to ensure successful project delivery? | Meet with their functional manager to assess the situation and obtain guidance. | Reverse the decision for replacement and bring the former key member back onto the team. | Add this concern as a risk in the risk log and escalate it to the project management office (PMO). | Assess the impact of this replacement and make further resource adjustments where necessary. | D | The project manager should assess the impact of this replacement and make further resource adjustments where necessary to ensure the project timelines are not affected by this replacement. The team should be fully independent and empowered to make their own decisions on their membership.
384 | Resource | A project manager observed that a team member was increasingly disengaged from an ongoing project. What should the project manager do to help ensure participation from this team member? | Speak to the team member, understand the problem, and ask the team member to work on corrective actions. | Ask the team member to undergo additional training to improve their communication skills. | Ask another team member to mentor the disengaged team member. | Call a team meeting to discuss team engagement expectations. | A | Understanding and empathizing with a disengaged team member is very important for a project manager. The project manager should speak to the team member, understand the problem, and ask them to work on corrective actions to ensure engagement.
385 | Business Environment | A project manager in a quickly growing hybrid organization is becoming increasingly frustrated at the rapid change in daily operations. Several newer team members have already left or been promoted to other organizational roles. What should the project manager do to ensure the project governance remains stable? | Work with senior leadership to update the organizational process assets (OPAs). | Update the project management plan regularly. | Update the team charter with new team members. | Develop a new social contract to empower the team. | D | The project manager should develop a social contract and empower the team to decide how they will work together. The key word here is to empower the team, which the project manager needs to do when "several newer team members have already left or been promoted to other organizational roles" because it is within the project manager's authority. If the team is not empowered, your project will have a
386 | Resource | The project sponsor for a major initiative recently sent a memo demanding that a milestone for a key deliverable be met much earlier than anticipated. Although this can be achieved, the original training schedule for the small project team will be dramatically impacted. The trainer will be available when needed. What should the project manager do to meet the updated timeline milestone? | Organize one-on-one workshops with the trainer and each project team member. | Organize a dedicated, longer workshop in the schedule with the trainer and project team well in advance of the new deadline. | Organize a workshop with the trainer and project team and conduct several internal team review sessions. | Organize a series of workshops with the trainer and project team over a shorter timeframe. | C | In order to meet the updated timeline milestone, the project manager should organize a workshop with the trainer and project team and then conduct several internal team review sessions. It will empower the team to problem solve together, rather than focusing on the capabilities of one individual.
387 | Resource | Close to the end of a large project, some of the technical reports related to the delivered service were not ready. The project manager asked the team members for the missing documents, but the team claimed they had already fulfilled their assigned tasks. How should the project manager address this concern? | Review the hierarchical chart to confirm positions and relationships. | Discuss the activity list and ensure the team understands the required work. | Input all assumptions and constraints into the assumption log. | Refer to the RACI chart to validate the assigned roles and responsibilities. | D | A RACI chart is a useful tool to validate assigned roles and documents and to ensure clear assignment of roles and responsibilities. The project manager should refer to the RACI chart to address the concern of the missing documents and determine who is responsible.
388 | Resource | Early in a project, the project manager realizes that one key team member is unprepared to perform the assigned task. How should the project manager address this issue? | Review each required task with the team member when it starts. | Review the training requirements with the team member. | Ensure training is built into the resource management plan. | Escalate the issue to the resource's functional manager for resolution. | B | It is essential to plan for specific tasks and ensure team members can carry them out effectively. The project manager should review the training requirements with the team member.
389 | Resource | A project is struggling to perform as expected in a company that recently adopted hybrid practices. Neither the project manager nor the team members have previous experience with this new approach to project management. What should the project manager do to ensure the transition to hybrid practices produces the desired results? | Take an active role in assigning tasks to team members and follow up with their results. | Train team members in basic hybrid practices and ensure the team performs coordination meetings. | Build a WBS and RACI chart to ensure all aspects of the project are owned, and tasks are clear. | Issue performance reports to all team members so they can review and act on them. | B | For the hybrid transition to succeed, the project manager should ensure team members receive basic training in the hybrid methods used to strengthen commitment and improve the flow of work. It leads to sound planning and execution to deliver features that add value to the customer.
390 | Resource | A Scrum team noticed a trend of work spilling over for the last several sprints. The root cause of this has been identified as the code review task. This bottleneck appears to occur because the team depends on an external expert. What should the project manager do first? | Work with the team, start reviewing the code and stop reviews from the expert to avoid spillover. | Arrange an alternative option to have a backup expert to avoid spillover. | Assess the team's capability and identify the required internal training to remove the bottlenecks. | Assess the bottleneck, highlight it, and increase the sprint length. | C | The project manager should first assess the team's capability and provide internal training to reduce the dependency on the external expert. When the team members can do the work, they will not need to wait for the expert, diminishing the bottleneck.
391 | General | A newly appointed product owner is not sure how to prioritize product specifications and mentions this challenge to the project manager. What should the project manager do to assist the product owner? | Request that the product owner becomes trained in agile methods. | Coach the product owner on how to prioritize product specifications. | Ask the project team to prioritize the product backlog. | Prioritize product backlog for the product owner. | B | The project manager should coach the product owner on prioritizing product specifications. Project managers should act as a facilitator, becoming impartial bridge-builders and coaches rather than making decisions for which others should be responsible.
392 | People | A new agile team is forming, and the project manager notices that the team is struggling in many areas. The team is experiencing both the inability to meet iteration commitments and team member conflicts. What should the project manager do next? | Involve management to help resolve the conflicts. | Inform management that commitments will not be met. | Coach the team both as a whole and individually. | Raise the issues in the retrospective and propose solutions. | C | The project manager should coach the team as a whole and individually because coaching helps the team's performance improve in a series of steps.
393 | People | A software delivery team at a large bank is frustrated by the documentation requirements put in place by the governance department in charge of their change control board (CCB). The project manager approaches the governance department and requests that they work together to reduce the paperwork required from the delivery team, explaining that it slows them down and adds overhead costs. This is an example of what kind of leadership? | Directive leadership | Servant leadership | Constructive leadership | Transactional leadership | B | It is an example of servant leadership because the project manager is offering to work with the governance board to resolve an issue for the software delivery team. The project manager has the software delivery team's interest in mind and is willing to work with the governance board to reduce the amount of paperwork.
394 | Risk | A project is in the execution phase when new team members are on board. Before onboarding the new team members, what should the project manager do to reduce the impact of this action on project performance? | Conduct a session to update the existing social agreement on how the team will work collaboratively. | Organize a meeting with all team members to communicate the current social agreement. | Plan a meeting with the new team members to explain the rules included in the social contract. | Schedule a session to let the existing team members explain to the new ones about the current social contract. | A | When new team members join an existing team, a new team is created. The project manager should conduct a session to update the existing social agreement on how the new team will work collaboratively. Setting the ground rules of the new team is a key factor, and the project manager's role is to facilitate everybody's participation to reach an agreement.
395 | Cost | A project manager is working in the fifth month of implementing a construction project. The planner reported that the current schedule performance index (SPI) and cost performance index (CPI) are 0.8 and 0.9, respectively. Which two options will help to accelerate the project? | Rearrange the schedule so that some activities on the critical path can be done concurrently to reduce the project duration. | Adjust the working procedures to streamline and improve efficiency with the current resources. | Increase the number of resources to get more people involved and get activities done faster. | Ask the resources to work overtime to accelerate the project and achieve better results. E) Change the critical path by replacing some critical path activities with activities that have float. | A | The health condition of the project is not good as per schedule and cost. Any method to be adopted in crashing the schedule must not increase the cost. The project manager should adjust the working procedures and rearrange the schedule to accelerate the project.
396 | Resource | A project manager leads a project team on a project. This project aims to enhance a product's capability in the market. What should be the top consideration when defining the team's key performance indicators (KPIs)? | Alignment with the project manager's goals | Alignment with the sponsor's business goals | Alignment with an individual's growth and development | Alignment with the customer's needs | D | To achieve project outcomes, project teams must balance work supporting individual, sponsor, team, and customer goals. Across the options, the highest goal or top consideration should be to satisfy the customer or client benefiting in its business by enhancing product range or capability. Alignment to the customer needs would be the most appropriate top consideration when developing the metrics
397 | Resource | A project manager for a new project is tasked with applying agile practices to improve team performance. Which approach should the project manager take? | Assign a budget for team activities during the project's planning phase. | Utilize active listening techniques to address the needs of the team. | Request a budget from finance for training the team members. | Ensure team retrospectives are done regularly. | D | The project manager should ensure team retrospectives are done regularly to improve team performance. Retrospectives allow the team to reflect on their processes and identify areas for improvement, which is a key practice in agile methodologies.
398 | Resource | A new project manager joins an existing team. The project manager is made aware that there are strong personalities on the team, resulting in management becoming involved in resolving team performance issues. What should the new project manager do when first joining this team? | Observe the team and determine who should be removed from the team. | Follow the advice of the most vocal team member on how to improve team dynamics. | Implement the plan that senior management has developed to resolve conflicts on the team. | Review the team velocity records and observe the team and interactions between the team members. | D | As the new project manager joins the existing team, they should observe to understand the dynamics and nature of the existing team. If there is dysfunction, all the more important to observe and then take action once there is a better understanding of the team.
399 | Cost | A project team has just reached a project milestone successfully. The project manager noticed that the team performed extremely well. Which approach should the project manager use to communicate with the team about their performance? | Disregard what was already done on the project and ask the project team to focus on what is left. | Give feedback to the project team regarding their good performance in the next meeting. | Avoid communicating about their performance, as the team is expected to deliver milestones successfully. | Wait until the end of the project and report to the team what was done well and poorly in each stage. | B | The project manager should give performance feedback to the project team as often as possible so that good work can be enhanced and unacceptable work can be corrected. By providing feedback in the next meeting, the project manager will not delay or withhold feedback like the other answer choices suggest.
400 | People | A project manager needs to survey the necessary parties to reach a consensus and build a common vision for the project. To achieve better results, who should be engaged in developing a common vision strategy? | The client and the delivery team | The project owner and the client | The delivery team and the project sponsor | The project team and the stakeholders | D | The project manager should engage the project team and the stakeholders when developing a common vision strategy because the team members must carry out the tasks that impact the stakeholders. The project manager must balance the project stakeholders' conflicting and competing goals to achieve consensus.
401 | Communications | An agile project is in its first of 12 iterations, and each iteration lasts two weeks. In the first iteration review, the stakeholders ask for a monthly report. What should the project manager do? | Educate the stakeholders according to the agile approach being followed | Ask the stakeholders to participate in an iteration review once a month | Create a monthly report and send it to the stakeholders | Ask the team members to create a monthly report | A | The project manager should educate stakeholders on the agile approach as part of servant leader responsibilities.
402 | People | A project team member continues to change a colleague's deliverable during every sprint. The colleague has asked the project manager to intervene. What action should the project manager take to address the concern? | Discuss any lack of quality in the deliverable with the colleague | Review the performance of both team members with their functional managers | Speak with the team member to determine the reason for the changes | Control the execution and delivery to ensure the deliverables are unchanged | C | Understanding the reason for constant changes is the first step the project manager should take in addressing the concerns. Then, the project manager can determine the actions necessary to resolve the conflict.
403 | Resource | A project is on schedule and three weeks away from completion. Two key team members approach the project manager because they disagree with completing the project's last task. They believe their way of addressing the task could significantly improve results. The project manager keeps the current process but considers implementing the team members' process improvement on future projects. What conflict management approach did the project manager use in this situation? | Compromise/reconcile | Smooth/accommodate | Collaborate/problem solve | Force/direct | A | The project manager wants to avoid unnecessary risks to the current project by changing the process three weeks from completion but agrees to implement the process improvement on future projects. The project manager used compromise/reconciliation to bring some degree of satisfaction to all parties and partially resolve the conflict.
404 | People | A geographically distributed project team has development issues between the co-located and virtual teams, causing productivity to decrease. What should the project manager do to address these issues? | Set up face-to-face meetings with project team members | Force the team members to work from one location | Develop protocols for resolving conflicts between team members | Obtain special expertise to advise the team members | C | When a project team is made up of colocated and virtual team members, communication management is critical. The Project manager should first understand the reasons for the issues between the teams and then set up protocols for effective team communication and conflict resolution.
405 | People | A conflict about how to proceed has developed between two team members prior to a release. The team needs to work together to complete the product release. What should the project manager do first to defuse the situation? | Observe the team members' interactions and talk with them about their complaints before applying a conflict resolution technique | Set up meetings with both team members and human resource management to remind them of the importance of the next delivery of the product | Explain to the team members that they are wasting time engaging in a conflict and not delivering the product functionality | Hire an agile coach to instruct the team members on managing their conflict without harming the project | A | The project manager must first analyze the conflict between the team member before implementing conflict resolution techniques.
406 | People | A project manager manages multidisciplinary teams. During the last project review meeting, the project manager realized there was friction between some team members. What should the project manager do next? | Consult with the sponsor to find replacements for the team members | Identify the team members and review their project performance | Evaluate the issue and apply conflict resolution techniques | Report the issue in the monthly project executive summary | C | Conflict is inevitable in projects; the success of any project manager in managing a team depends on how well he manages the conflicts. The project manager has to evaluate the situation of the given team's matrix and charter to gain insight and use conflict resolution techniques accordingly.
407 | Cost | An agile project is in its first of ten iterations. After the iteration review, the team receives stakeholder feedback not aligned with the project objectives. What should the project manager do? | Ask the sponsor to define the stakeholders' priorities | Ask the team to meet with stakeholders to understand their needs | Ask the product owner to review the product backlog and its priorities | Ask stakeholders to prioritize their needs | C | The product owner is responsible for the vision that drives the project objectives. The project manager should ask the product owner to review the stakeholder feedback and product backlog to ensure the prioritized work is aligned.
408 | Resource | In order to function optimally, a project team should have a project charter that states the vision or purpose of the project and a clear set of working agreements. To achieve this, which question should the project charter answer? | Why is this project being done? | What are the key risks and their mitigation? | Why did the organization prioritize this project? | Who will be doing the work? | A | Answering why the project is being done would explain the purpose of the project. The other options are less of a priority for addressing the project's vision and purpose.
409 | People | An organization is adopting agile approaches to execute projects for its customers. During project planning, the product owner proposed that the legal department approve any release to the customer before it is shipped. The development team is disappointed as it may delay releases and the delivery schedule. Since other departments in the organization do not use agile, what should the project manager's role be as a servant leader? | Advise senior management to introduce agile to all departments to ensure seamless customer service | Inform the customer about the organizational procedures and ask them to discuss this with the organization's leadership | Continue with organizational procedures to ensure policy compliance and avoid creating issues | Work with the legal and applicable departments to review the processes supporting the project delivery | D | The project manager should work with the legal and applicable departments to review the processes supporting the project delivery. Servant leaders facilitate and remove organizational impediments and coach teams in agile.
410 | Schedule | A team member is scheduled to visit an overseas client site next week. However, the project manager overheard the team member tell a project coordinator that their functional manager denied the team member's request for time off as compensation for the client visit. The project manager must ensure the team member will visit the client site next week. What should the project manager do? | Log the issue as a risk in the risk log and assign another team member | Confront the functional manager about the team member's time off | Meet with the team member directly to tell them what they overheard | Confirm with the team member that the client visit can take place | D | The project manager should confirm with the team member that the client visit can take place. This confirmation is important.
411 | People | During a retrospective meeting, project team members complained that open issues that were not fixed during the iteration impacted their velocity. What should the project manager do to improve productivity? | Extend the daily standup meetings to discuss the issues in more detail | Ensure team members attend daily standup meetings to discuss the impediments | Document the issues in the log and wait to solve them later | Escalate the issues to the project sponsor to get them solved immediately | B | The project manager should ensure team members attend daily standup meetings to discuss the impediments. Project managers should build their servant leadership skills of facilitation, coaching, and impediment removal.
412 | People | Client interactions with the project team have been somewhat negative and adversarial. Project team members no longer want to be part of the project. What should the project manager do? | Keep negotiating with the client and the project team to settle differences | Follow the client's expectations and feelings continuously | Schedule a meeting with the client to discuss the team's concerns | Involve all team members in stakeholder engagement | A | There is a conflict situation between the client and the project team. The favored technique for resolving conflict and setting differences is negotiation. The project manager should balance the team's concerns with the clients'.
413 | People | A project manager working with a culturally diverse team discovers major intra-team conflicts during project execution. What should the project manager do? | Engage members in team-building activities | Update the resource management plan | Advise the team members to work harmoniously | Schedule a project team meeting to understand the conflicts | D | The project manager needs to understand the conflicts and should engage the team in identifying them and developing solutions.
414 | People | As a project is nearing completion, a struggle between the product owner and the project sponsor regarding who owns the benefits derived from the deliverable becomes a matter of litigation. What should the project manager have done to prevent this conflict from happening? | Identified and captured any potential issues in the issue log | Created a detailed work breakdown structure (WBS) | Identified the project sponsor as a stakeholder at the beginning of the project | Develop and approve the project charter jointly with the product owner and the project sponsor | D | Project partnering transforms contractual relationships into a cohesive, cooperative project team with a single set of goals and established procedures for resolving disputes in a timely and effective manner. To avoid conflict, the project manager should have developed and approved the project charter jointly with the product owner and project sponsor from the beginning.
415 | People | A team has recently adopted agile and is following a scrum model. There is a conflict between a lead developer and a quality assurance team member regarding their approaches, impacting the sprint goals. What should the project manager do to resolve these conflicts? | Call separate meetings with each team member and suggest that the team members resolve it at their level | Discuss the situation in the retrospective session and create an action item | Analyze the situation and help the team members understand the impact of the conflict | Help the team members collaborate and resolve their problems together | D | The conflict between team members should be dealt with among themselves. The team members' opinions should be valued and made transparent in the process. The project manager should encourage them to collaborate to solve their issue and should intervene if the conflict cannot be resolved.
416 | Cost | A project manager is preparing the charter for a project. The project aims to automate 30 percent of the company's product testing. The project sponsor advises the project manager to assign senior test engineers to identify the tests that can be automated. The test department manager, however, is NOT cooperative because they believe that the project will lead to downsizing in their department. Which two actions are suitable in this scenario? | Present data-driven, cost-benefit evidence of test automation to the test department manager | Raise the risk that the senior testing engineers will NOT be available for the testing | Have a meeting with the test department manager to discuss mutual expectations | Request for the project sponsor to provide a rationale for test automation | A | Presenting data-driven, cost-benefit evidence of test automation to the test department manager is the most appropriate action in this scenario. It addresses the test department manager's concerns about downsizing by providing objective information about the benefits of automation. This approach can help alleviate fears and promote cooperation.
417 | Resource | A project manager receives complaints from a project sponsor because of a delay in developing a prototype. The project manager consults the resource management plan and responds that the delay was due to a lack of knowledge in a specific skill that was needed by the cross-functional project team. How can the project manager perform this task better in the future? | Create training sessions at the start of the project, so all necessary skills are learned | List required skills for the project and organize the project team based on those skills | Empower team members to problem solve where skills may be lacking, using the skills they do have | Consult with the project sponsor to add training once the lack of a specific skill becomes apparent | B | To prevent future delays due to skill gaps, the project manager should proactively identify required skills and organize the team accordingly. This approach ensures that the team has the necessary expertise from the start, reducing the likelihood of delays caused by lack of knowledge in specific areas.
418 | Resource | A customer requests a change in the technical approach for a product in development. The project manager learns about this request during a recurring project review. How should the project manager respond? | Let the team decide on the appropriate approach, giving them authority to implement and validate their decision in talks with stakeholders | In order to obtain sponsor buy-in, allow the team to benchmark the approach | Work with team members to immediately implement the new approach | Discuss the pros and cons of the proposed approach with stakeholders, then select the approach that is best for the team and notify team members | A | As this is a technical issue, the project manager should empower the team to assess and select the best options to address the customer's request. This approach leverages the team's expertise and promotes ownership of the solution while ensuring stakeholder involvement.
419 | People | A project manager notices that team member A seems unhappier after every team meeting. After looking into the situation, the project manager finds out that team member A is not making progress on a key activity. This has an impact on the critical path. Team member A also feels that they are NOT in the correct role within the project team. What should the project manager do? | Reassure team member A about their abilities by reminding them that they were chosen for a reason | Meet with team member A to discuss where they can contribute, based on their strengths | Reassign team member A to a more appropriate role in another project | Enroll team member A in targeted training to acquire the needed skills for their assigned role | B | Meeting with team member A to discuss their strengths and potential contributions is the best response. As a servant leader, the project manager should help team members find roles where they can best contribute, addressing their concerns and potentially improving their performance and satisfaction.
420 | Resource | A cross-functional team on Project B reports a delay in developing a prototype. The project manager believes that the cause is lack of knowledge in a specific, required skill on the team. In which three ways can the project manager prevent this situation on future projects? | Outsource the task to a skilled expert | Make a list of required, specific skills for the project | Identify required skills and organize the team based on the strength of those skills | Ask the team leader to recommend a solution | C | To prevent future delays due to skill gaps, the project manager should proactively identify required skills and organize the team accordingly. This approach ensures that the team has the necessary expertise from the start, reducing the likelihood of delays caused by lack of knowledge in specific areas.
421 | Scope | The IT department of a glassware manufacturer enthusiastically approved the agile team's mid-project demo of quality-checking software for assembly line workers. However, the final product was considered UNUSABLE because the workers' gloves are too thick to press the machinery's small buttons. What should the project manager do to avoid this kind of failure in the future? | Create a realistic simulation of end-user conditions for developers testing the software | Plan for end users to test prototypes and incremental releases in their production environments | Ensure that all software releases include adjustable accessibility features | Contract directly with the customer department that defines the product requirements | B | To avoid usability issues, it's crucial to involve end users in testing prototypes and incremental releases in their actual work environments. This approach ensures that the product meets real-world requirements and identifies potential issues early in the development process.
422 | Resource | Project team members are concerned that a new resource does NOT seem suitable for an assigned task. How should the project manager respond to this concern? | Schedule time to chat with the new resource to re-assess their skills and understand their strength level | Contact senior management to discuss the possibility of reassigning the new resource to a different project | Contact the project sponsor to highlight these concerns and decide on an appropriate response | Ask the team members to document task-related deficiencies displayed by the resource | A | The project manager should directly assess the new resource's skills and strengths to determine if they meet the project's needs. This approach allows for a fair evaluation and helps identify any potential areas for improvement or reassignment.
423 | Communications | The project manager receives a progress report showing that the agile project is NOT on track. Since all work was deliberately selected and sequenced to meet higher-level objectives, the project manager is surprised by the report. In the future, how can the project manager prevent this type of miscommunication? | Ensure that there is a contingency reserve to cover these issues | Provide early training and ongoing mentoring about the agile approach for the project team | Support self-organization for the project team and help them provide buy-in for the project | Ensure that the team is trained to use the agile process reporting system | C | Face-to-face communication is usually the most effective way to build trust and resolve conflicts, especially when dealing with third-party contractors. This approach allows for better understanding of concerns and facilitates more productive problem-solving.
424 | Risk | A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has NOT yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? | Schedule a meeting to discuss and brainstorm the functionality with the project team and business representative | Continue with the current sprint, recognizing that the issue will be identified during the testing phase | Ensure that the issue is addressed by escalating it to the project sponsor, who should discuss it with the representative | The functionality was formally approved, so initiate the change management process | A | As the functionality has not yet been developed, the project manager should facilitate a discussion between the team and the business representative to build common understanding and evaluate the impact of a possible change. This approach helps avoid rework and ensures alignment with business needs.
425 | Communications | During a challenging stakeholder meeting, one stakeholder indicates that they will reject an iteration's deliverable. What should the project manager do? | Send a request to the project sponsor, asking them to update the project charter then reassign the responsibilities and authorities | Meet with the project team to add new and improved features to replace the features that were rejected | Request a private meeting with the stakeholder and a member of the project team to try and defuse the situation | Work with that stakeholder to understand their concerns and address these together with the team | D | The project manager should work with the stakeholder to understand their concerns and address them collaboratively with the team. This approach promotes open communication, helps identify the root cause of the rejection, and allows for a more effective resolution.
426 | Cost | A product owner repeatedly complains, saying that a function developed by the development team does NOT seem to align with the original design. What will help to solve this issue? | Update the product owner twice per week on product development | Ask the development team to rewrite the function so that it matches with the project scope | Ask the product owner to explain his point of view clearly to the team | Ask the quality assurance team to identify any mismatches in functionality compared to the initial design | A | Keeping the product owner regularly updated on product development allows for timely feedback and alignment with expectations. This approach helps prevent misunderstandings and ensures that any deviations from the original design are identified and addressed promptly.
427 | Risk | An agile development team changes a design element in a project. Testing results improve dramatically over the next two iterations. At the third iteration retrospective, the product owner is unhappy to learn about the change to the original design and asks the team to redo the work based on the original design. How can the project manager prevent such situations? | Request additional funding from the product owner for re-work due to lack of collaboration with the team | Ensure regular engagement with the product owner and run catch-up meetings if necessary | As servant leader, help the team to focus by removing all impediments | Set out all decision path conditions in the ground rules and correct any deviations as early as possible | B | Regular engagement with the product owner is critical when considering scope changes or any changes that may impact the scope. This approach helps prevent misunderstandings and ensures that the product owner is aware of and approves any significant changes to the original design.
428 | Communications | An R&D executive, who is a project stakeholder, occasionally visits the agile team's work area to give instructions about urgent feature work. The team begins work. During sprint reviews, the product owner becomes upset that the team worked on the requested features. How should the team address the problem? | Give the executive access to add new items to the backlog | Meet with the executive and product owner to agree on a work flow | Escalate to ensure that the executive no longer interferes with the team | Require that the executive issues change requests for new items | B | To address the issue of the executive bypassing the product owner, a working agreement between the executive and the product owner is needed. This approach helps establish clear communication channels and ensures that all stakeholders follow the proper workflow for requesting changes or new features.
429 | Cost | A Scrum innovation team is funded at varying levels by six (6) market units. Four (4) niche market units complain they are neglected because the team prioritizes mainstream unit goals. The marketing director suggests devoting a constant 40% of the team effort to the four (4) niche units in a balanced way. How can the team support this request? | Group stories by unit; select 40% of niche stories to work on at each sprint | Split stories into mainstream or niche groups, plan 10% of mainstream stories at each sprint | Group stories by unit; plan 10% of story points per niche unit at each sprint | Split stories into mainstream or niche groups; plan 40% of niche story points at each sprint | C | To meet the requirement of devoting 40% of effort to the four niche units, the team should group stories by unit and plan 10% of story points for each niche unit per sprint. This approach ensures a balanced distribution of effort across all niche units while maintaining the desired 40% allocation.
430 | People | The atmosphere is tense in the sprint planning review. The agile team members are visibly unhappy—one of them kicks a chair and shouts at the product owner, "That just doesn't make sense!" Which two actions should the project manager take in this situation? | Reprimand the member who kicked the chair with a warning | Intervene, giving one uninterrupted minute to each person present to state their case | Calm all present by asking them to call on their emotional intelligence | Remind the team of the product owner's responsibilities and authority | B | In this tense situation, the project manager should intervene to ensure all viewpoints are expressed. Giving each person an uninterrupted minute to state their case allows for a fair and structured way to address the conflict, promoting open communication and understanding among team members.
431 | Resource | A project manager observes that team members are in a low mood after demos. Feedback from stakeholders is constantly causing concern for the team. As a result, the team rushes through product demos, and the interaction between the team and stakeholders is minimal. Which action should the project manager take? | Verify that the project requirements are suitable and that the team members can do the work | Meet with the stakeholders and find out the root cause of their feedback. Work with the stakeholders to rectify the problems | Consult the stakeholder matrix and identify whether any of these people are known to be difficult | Coach the team to be more confident in their work and communicate properly with the stakeholders | D | The project manager should coach the team to be more confident in their work and improve their communication with stakeholders. This approach addresses the root cause of the team's low moods and helps them better handle feedback and interactions with stakeholders.
432 | Cost | A project manager has assembled a project team. During initial meetings, the project manager observes that team members are getting to know each other, feeling excited and positive about the project, and have NOT been told the specific details of the project. In what phase of development is the team? | Storming | Norming | Performing | Forming | D | The team is in the Forming stage of development. During this phase, team members are getting to know each other, feeling excited about the project, and have not yet been given specific details. This is typical of the initial stage of team formation.
433 | Resource | Three project teams are working on parts of a single project. The parts are highly dependent on each other. The leader of the team indicates that this might create conflicts when the outputs from the three teams are combined. What guidance should the project manager offer to the team lead? | Document conflicts as they occur and take action to remedy any problems that arise | Tell all three teams to continue to work simultaneously, recognizing that conflicts can be addressed at the testing phase | Identify potential conflicts and arrange for a weekly joint meeting with the members of the three teams to monitor each other's work | Decide which team's work should be prioritized, then delay the work from the other two teams to ensure there are NO conflicts | C | To address potential conflicts between the three interdependent teams, the project manager should proactively identify potential issues and arrange regular joint meetings. This approach promotes communication, collaboration, and early detection of potential problems.
434 | Procurement | A project is utilizing a third-party contractor. A member of the contractor's team raises an issue with a member of the project team. The two individuals are NOT able to work out a solution. The project manager is aware of the disagreement. Which type of communication should the project manager use first when contacting the vendor about this issue? | Phone | Face-to-face | Contractual letter | Email | B | Face-to-face communication is usually the most effective way to address conflicts and build trust, especially when dealing with third-party contractors. This approach allows for better understanding of concerns and facilitates more productive problem-solving.
435 | Schedule | During the execution of a project, a key team member is concerned with the overall approach documented in the project management plan. The member surprises the project manager with negative comments about the approach during a weekly status meeting. How should the project manager address the team member's concerns? | Remember that a project should NOT go forward when key team members are in disagreement. Use the meeting to discuss the members' concerns | Make a short comment to acknowledge the team member's concerns, continue with the meeting, and meet with the member in private to discuss their concerns | Continue with the meeting and ensure that the concerns are added to the risk register after the meeting is finished | Continue with the scheduled agenda items after reminding the team member of expected meeting etiquette. Then, solicit feedback about the etiquette expectations | B | The project manager should acknowledge the team member's concerns briefly, continue with the scheduled meeting, and then address the concerns privately. This approach maintains the meeting's focus while ensuring that the team member's concerns are addressed appropriately.
436 | People | An efficient, empowered agile innovation team does NOT understand why required approvals from the legal department are allowed to delay their progress. Eventually, the team confronts the product owner in a heated exchange. The product owner replies that the approvals are needed to check for existing patents, which would block the product from going to market. How should a project manager prevent such conflicts? | Require the team to move a story to the Kanban blocked column if they have concerns about progress | Require that supporting department stakeholders attend the daily meetings to report progress | Ensure that the product owner can be easily approached to respond to team questions and concerns | Ensure that the product owner presents the team the rationale behind the refinement work flow | D | To prevent conflicts and misunderstandings, the product owner should explain the rationale behind the refinement workflow to the team. This approach helps the team understand the importance of certain processes, such as legal approvals, and their impact on the project's success.
437 | Resource | A project manager wants to know whether an agile team possesses a good combination of T-shaped skills. What can the project manager measure to determine this? | Reduction in reassigned tasks | Less internal knowledge sharing | More collaboration with SMEs | Decrease in detected defects | A | A reduction in reassigned tasks indicates that the team possesses a good combination of T-shaped skills. T-shaped team members have both depth in their primary skill area and breadth across other areas, allowing them to collaborate more effectively and complete work without frequent task reassignments.
438 | Cost | An agile team member solved a problem that had blocked work for several weeks. After release of the software, it appears that the solution caused a function to fail. The quality director demands an explanation. In which two ways should the project manager react? | Issue a warning to the team member about NOT taking risky initiatives | Work with the team to identify gaps in the Definition of Done | Work with the team to identify gaps in the Definition of Ready | Ask the team member to present his rationale and lessons learned | D | To address the issue and learn from it, the project manager should ask the team member to present their rationale and lessons learned. This approach promotes accountability and helps the team understand the context of the error, potentially preventing similar issues in the future.
439 | Resource | A recently formed agile team is exhausted after working 12-hour days to fulfill sprint commitments. Who has NOT properly performed their duties in this situation? | Scrum master | Product owner | Project manager | Team members | A | The Scrum master is responsible for ensuring that the team's working conditions, including workload, are appropriate and sustainable. In this situation, the Scrum master has not properly performed their duties by allowing the team to become exhausted from working excessive hours.
440 | Cost | The product owner's schedule is very busy, and he wishes to delegate some of his tasks to the experienced agile team. Which task is suitable to delegate to the agile team? | Select prioritized items for the sprint backlog | Prioritize items to the backlog according to size | Add items to the backlog before prioritization | Initiate and run backlog refinement sessions | C | Adding items to the backlog before prioritization is a suitable task to delegate to the agile team. The product owner typically has sole authority to prioritize and plan the backlog according to business needs, but adding items can be delegated, with the product owner prioritizing at a later time.
441 | Risk | Project manager A identifies three critical risks with probability of a high impact on the schedule and budget of project A—this project is producing critical deliverables for the company. The team meets to devise a solution for the risks and decides that three specific resources will be required to address the risks. However, these resources are already committed to a separate project, which is managed by project manager B. Which party should the project manager work with first to find a solution? | The three resources – to convince them to join the team or, at least, agree to coach the existing team | The project team members – to assist in training the new team members quickly so they can complete work on time | The project sponsor – to request more funding for the budget in order to hire contractors | Project manager B – to negotiate reallocation or sharing of the three required resources | D | The project manager should first work with Project manager B to negotiate the reallocation or sharing of the required resources. This approach respects the authority of Project manager B and allows for a professional discussion about resource allocation, considering the needs of both projects.
442 | Resource | A customer is NOT satisfied with the delivered product, saying that it was NOT what they expected. The project manager is surprised, because the agile development team delivered the product several iterations early. What is one way that the project manager could have avoided this result? | Set aside more resources for product testing after making changes | Required team sign off for each of the changes to the requirements | Ensured that the development team fully participated in the iteration review, by explaining and answering questions | Ensured that the customer was aware of the value of demos and the approval process for the deliverable | D | To avoid customer dissatisfaction, the project manager should have ensured that the customer was aware of the value of demos and the approval process for deliverables. This approach promotes customer engagement throughout the development process and helps align expectations.
443 | Scope | A key stakeholder voices a concern during the planning stage about whether the available resources are adequate to meet the objectives of the project. After further discussion about the requirements and the number of resources identified, the project manager is hesitant about the original plan. Which two steps should the project manager take next? | Engage in negotiations for more resources | Ensure that the impact of the shortage of required resources is fully documented | Determine the project's ultimate objectives after carefully evaluating project priorities | Review the bounds of the negotiations for stakeholder agreement | A | Given the stakeholder's concern and the project manager's hesitation about the original plan, engaging in negotiations for more resources is an appropriate next step. This approach addresses the potential resource shortage and helps ensure that the project has adequate resources to meet its objectives.
444 | Procurement | A contractor has sent an email request for urgent payment of their last invoice on a project that is going through a long execution stage with multiple contractors. How should the project manager respond to this contractor's request? | Authorize the payment by notifying accounts payable and follow up to ensure it was made | Authorize payment only after reviewing forecast spend versus actual spend to see if the actual status allows it | Negotiate payment terms through a meeting with procurement and the contractor | Act according to the agreed-upon commitments in the procurement management plan and the signed agreement/contract | D | The project manager should respond to the contractor's request by following the agreed-upon commitments in the procurement management plan and the signed contract. This approach ensures consistency and adherence to established terms and conditions for payments.
445 | Resource | A project manager is working on a small project that is critical for a larger program milestone. A new resource has been assigned to replace a key resource who had to leave the project. Unfortunately, an outside stakeholder claims that the person who assigned the new resource sent their weakest team member. How should the project manager approach this rumor? | File a request with the project management office (PMO) manager in order to obtain a better resource | Address the rumor with the new resource's functional manager to mitigate any conflict within the project team | Assess the new resource's ability to perform the necessary work by testing their communication skills with the current project team | Evaluate the skills of the new resource to see how the resource can provide value to the project | D | The project manager should focus on assessing the new resource's skills objectively rather than relying on rumors or hearsay. This approach allows for a fair evaluation of the resource's potential contributions to the project.
446 | People | A project manager joins a project team, replacing a manager who left. During initial meetings, the project manager realized that the team members have differing opinions about how to address technical decisions. Team members did NOT respect each other's ideas, and the environment was becoming counterproductive. However, now with the new manager's leadership, the team has begun to communicate more effectively and develop some processes and procedures for working together. In what phase of development is the team now? | Storming | Performing | Forming | Norming | D | The team has moved past the initial conflict stage (storming) and is now developing processes and procedures for working together effectively, which is characteristic of the norming phase of team development.
447 | Resource | A project has the following characteristics: Schedule performance issues occur due to low expertise levels of project resources. Junior-level resources are NOT completing tasks in a timely manner. Highly-experienced resources report that their junior colleagues are performing unnecessary tasks. In what two ways can the project manager enhance the performance of this team? | Design a checklist for all team members E) Set up mentoring sessions within the team so that the experienced resources can coach the junior resources and work collaboratively | Meet with the team leader to discuss the situation and decide if escalation to the project sponsor is necessary | Implement a whole-team training program to address efficient working and task completion | Work collaboratively with the team to design training and a checklist for task completion aligned with project goals | D | These approaches address the skill gap by involving the entire team in creating solutions and leveraging the expertise of experienced team members to improve overall performance.
448 | Communications | A project manager went on a vacation and returned to discord. According to two stakeholders, stakeholder C is causing problems. Every day for the last two (2) weeks, stakeholder C sent an email to the team, checking progress and giving new instructions. The team ignored the emails and continued working, but the other stakeholders are concerned about stakeholder C's behavior. What should the project manager do? | Initiate a private conversation with stakeholder C and resolve this problem | Invite everyone to a meeting and work through the communication issue | Instruct the two stakeholders to ignore stakeholder C, just as the team did | Investigate the problem to find the root cause | D | Before taking any action, it's crucial to understand the underlying reasons for the communication issues and stakeholder behavior. This approach allows for a more informed and effective resolution.
449 | People | A project team is comprised of local and virtual team members. To manage scheduling priority conflicts among team members, the project manager schedules a video conference call. Which conflict resolution technique does this statement demonstrate? | Force/Direct | Smooth/Accommodate | Collaborate/Problem Solve | Compromise/Reconcile | C | Scheduling a video conference call to address scheduling conflicts demonstrates a collaborative approach to problem-solving, involving all team members in finding a solution.
450 | People | An unresolved conflict between a member of a third-party vendor's team and a member of a project team is causing disruption. The issue is escalated to the project manager. What should the project manager do first? | Draft and send a contractual letter to the vendor | Send an email to the vendor to discuss the issue | Place this item on the backlog | Meet with the vendor to discuss the issue | D | A face-to-face meeting is the most direct and effective way to address the conflict, allowing for immediate communication and resolution of the issue.
451 | Resource | A project is comprised of three highly dependent parts; each being completed by its own project team. The team leader, worried that conflicts might arise when the outputs from the three teams are combined, asks for advice. What advice should the project manager provide? | Document conflicts as they occur and take action to remedy any problems that arise | Decide which team's work should be prioritized, then delay the work from the other two teams to ensure there are NO conflicts | Identify potential conflicts and then arrange for a weekly joint meeting with the members of the three teams to review each other's work | Continue to let all three teams work simultaneously, recognizing that conflicts can be addressed at the testing phase | C | This proactive approach helps prevent conflicts by ensuring regular communication and alignment between the interdependent teams.
452 | Cost | A frustrated agile team member approaches the project manager to complain that a senior team member is claiming all the "interesting" backlog items and leaving the tedious activities for everyone else. How should the project manager address the complaint? | Encourage the complaining member to take assertiveness training | Define a new rule so members can select an item on a rotating basis | Discuss the importance of fairness with the senior team member | Ask the team to define new ground rules for work distribution | D | Involving the team in creating solutions promotes self- organization and collaboration, addressing the issue while empowering the team to establish their own working norms.
453 | Resource | On an agile team, staff members from various organizational departments rotate in and out, to augment the team. How can the project manager help shield the permanent team members from disruption? | Give them higher priority to choose which tasks they work on | Require staff leaving the project to run a knowledge-sharing workshop | Ask staff leaving the project to pick members who deserve recognition | Give them authority to assign tasks to the rotating members | B | This approach helps mitigate the loss of skills and knowledge when team members rotate out, while also developing the permanent team members' cross-functional capabilities.
454 | Resource | A new resource joins a working project team and is assigned to a small project that is critical to a larger program milestone. Unfortunately, the new resource is under-skilled and very nervous. The team dynamic has become awkward, and work has slowed on the small project. Which are two possible ways for the project manager to handle this situation? | Assess the new resource's communication skills to evaluate their ability to perform acceptably as part of the project team | Talk with the new resource about their skills and then determine how they can contribute to the project | Privately ask the project management office (PMO) to assign a different resource with better skills | Meet with the functional manager of the new resource to understand their background better E) Solicit the team about integrating and coaching the new team member | B | These actions focus on understanding the new resource's capabilities and involving the team in supporting their integration, promoting a collaborative and supportive team environment.
455 | Resource | During a technical project, a well-liked project member is reassigned to a different project. The team has expressed disapproval regarding the reassignment. What action can help mitigate the team's disapproval? | Schedule a team-building day to keep the team happy | Notify the project sponsor regarding the team's disapproval and brainstorm a response | Add a resource with the same skills to replace the key team member | Employ leadership and emotional intelligence tools and techniques to inspire the team to continue working | D | This approach addresses the team's emotional response to the reassignment while maintaining focus on the project objectives. It demonstrates the project manager's ability to lead through challenging situations.
456 | Resource | A project manager in an organization that uses traditional project management is assigned to an ongoing project. Recently, the organization has started to use agile methodologies for projects. The project manager hears that some team members think key subject matter expertise is missing and that the team does NOT collaborate enough. How should the project manager respond to these team members' concerns? | Add cross-functional internal resources and explain their value to the team | At the next standup meeting, emphasize the importance of collaboration to the entire team | Start using Kanban boards instead of Gantt charts so that work co- dependencies become obvious to everyone | Employ third-party specialists to fill the knowledge gap | A | This solution addresses both the lack of subject matter expertise and the need for increased collaboration by introducing team members with diverse skills who can work across different areas of the project.
457 | Risk | A key team member is asked to move to another project during the middle of a technical project. The team believes this is an unwise move and expresses concern. Which action will help to resolve the issue? | Replace the key team member with a new resource who has the same skills | Acknowledge the team's concern and analyze the impact to the project | Discuss the conflict with the project sponsor and formulate a response | Use coaching tools and techniques to motivate the project team | B | This response shows respect for the team's concerns while taking a pragmatic approach to assess the situation's impact on the project, allowing for informed decision-making.
458 | Resource | A technology development project has the following characteristics: It requires a highly skilled resource that is unavailable locally. The project manager has identified a resource who can do the work, but the resource lives in a different country and requires a work visa. The work visa process is taking more time than anticipated. What should the project manager do? | Request that the resource work remotely | Reduce the project scope | Delay the project by an equivalent duration | Assign the existing team overtime work | A | This solution leverages technology to overcome geographical barriers and visa delays, allowing the project to proceed with the required expertise without further delays.
459 | Resource | During Project A's kickoff phase, the project manager provided training for the entire team regarding the specifics of the company operations that the project supports. A year later, project productivity is suffering because members who were added later in the project do NOT have the same level of understanding. How should the project manager respond to this challenge? | Add new members who have the relevant experience, reassign the newer team members, and log turnover issues in the lessons learned register | Recognize that this is a natural project progression and revise the schedule to allow for the slight decrease in productivity | Tell the newer team members to ask for help from the long-term members when they run into things they do not understand | Ask current team members to provide training and support and hold a second kick-off meeting for new team members | D | This approach addresses the knowledge gap by utilizing existing team members' expertise and ensures that new members receive the necessary information to contribute effectively to the project.
460 | Scope | A project has the following characteristics: A quality management plan is in place. The quality management plan states that project deliverables must be reviewed, at a minimum, 1.5 weeks before the deadline. Four (4) deliverables have missed this quality requirement. Which step should the project manager take? | Reach out to the project sponsor for their input | Request that the project undergo an internal audit | Modify the quality management plan to conform to project practices | Use a cause-and-effect diagram for root cause analysis | D | This tool helps identify the underlying reasons for the quality requirement failures, allowing the project manager to address the root causes and prevent future occurrences.
461 | Quality | A project is in the execution stage. Based on the originally approved blueprint, 1,000 products were developed. The project team randomly chooses 100 products to evaluate against the quality plan. What is the project team undertaking? | Quality assurance | Process audit | Control procurement | Statistical sampling | D | The team is using a random selection of products to evaluate against the quality plan, which is a form of statistical sampling used to assess overall quality without inspecting every item.
462 | Quality | The project is overseen by a senior project manager. A new project manager joins the project, and the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | Meet with the senior project manager to identify established plans and processes. Then, ask for assistance in selecting the appropriate standards | Obtain the necessary benchmarking samples and cost-benefit analyses from the sponsor | Postpone the development of the quality management plan until quality metrics and quality checklists are created | Schedule a meeting with the customer to collect requirements and obtain benchmarking samples | A | This approach ensures continuity with existing project practices and leverages the senior project manager's experience in developing an effective quality management plan.
463 | Quality | The project is overseen by a senior project manager. When a new project manager is added to the project, the sponsor asks the new project manager to develop the quality management plan. How should the new project manager proceed? | Schedule a meeting with the sponsor to obtain benchmarking samples and cost-benefit analyses | Schedule a meeting with the customer to collect requirements and obtain benchmarking samples | Obtain established quality processes and plans from the senior project manager. Then, ask them for guidance in selecting the appropriate standards | Postpone the development of the quality management plan by submitting a change request. Only proceed when quality metrics and quality checklists have been created | C | This approach ensures alignment with existing project practices and leverages the senior project manager's expertise to develop an effective quality management plan.
464 | Cost | Company B is setting up a new agile innovation team with a mission of placing product quality above all other considerations. The initiative comes after a number of high-profile complaints on social media networks about the brand's diminished quality. Which option would be most effective to achieve the team's goals? | Use Test-Driven Development based on continuous user focus group input | Raise the product price to fund use of better-quality materials | Create an automated testing bench to eliminate human error | Benchmark features against competitor products and track defects | A | This method combines a quality-focused development approach with ongoing user feedback, directly addressing the company's goal of improving product quality and responding to customer concerns.
465 | Resource | Some agile approaches have recently been added to an infrastructure company's predictive processes. The team is NOT completing the planned story points, and they are becoming passive. The project manager is concerned and wants to improve productivity. Which two actions should the project manager take? | Gain the needed time for story point completion by adding more iterations to the project | Use burndown and burnup charts to evaluate team performance and show story points completion | Provide team training, so the team can do a better job of estimating story points | Speed up the project by reducing the backlog | C | Training helps improve estimation skills, while burndown and burnup charts provide visual feedback on team performance, both of which can help address productivity issues in an agile environment.
466 | Cost | During sprint planning, some new backlog items are prioritized but NOT estimated. The product owner requires a new set of tests to verify the unique properties of the items. What should happen before adding it to the sprint backlog? | The product owner defines a new epic to allow testing in the next sprint | Add the relevant acceptance criteria in the Definition of Ready before estimating | Use analogous estimating based on similar tests on similar stories | The product owner should provide the initial estimate to be refined by the team | B | Adding acceptance criteria to the Definition of Ready ensures that all aspects of the work are considered before estimation, leading to more accurate planning and execution.
467 | Resource | An agile approach is required during the final phase in a team's project. As the team discusses the phase, some team members disclose that they have NOT worked with agile before. The deadline is approaching soon. How should the project manager respond? | Escalate this as an issue to the project sponsor, as it is a company-wide issue and a blocker for this project | File a change request that addresses the agile training that members lack | Identify and provide the most cost-effective agile training for team members | Ask the team members who have worked with agile to mentor the others | C | This approach addresses the immediate need for agile skills while being mindful of project constraints, allowing the team to adapt quickly to the new methodology.
468 | Resource | At a weekly project status meeting, a key team member expresses concerns about the overall approach documented within the project management plan. The project manager is surprised because the team is in the process of executing an important component of the project and the concern has NOT been raised before. What steps should the project manager take? | Address the team with a generic reminder about meeting etiquette, then ask if the team wants to use the time to discuss the concerns raised during the meeting | Recognize that the concern must be discussed and resolved prior to continuing with the meeting's agenda items | Update the risk register to document the concerns, then continue with the meeting's scheduled agenda items | Acknowledge the team member's concern immediately, continue with the scheduled agenda, then privately meet with the team member to understand the concerns expressed | D | This response balances the need to address the concern while maintaining meeting efficiency, and allows for a more in-depth discussion in a private setting.
469 | Communications | Certain key stakeholders are dissatisfied with the development of a key feature of a project. They express their dissatisfaction during an iteration review meeting. What should the project manager do first to resolve this issue? | Identify the reasons why there are issues with the feature, then address the issue | Add a neutral party, such as the project sponsor, to function as a negotiator with stakeholders | Gather the project team for a brainstorming session and identify a solution | Create a list of the pros and cons of the situation to define the impact of the conflict | A | Understanding the root cause of stakeholder dissatisfaction is crucial before attempting to resolve the issue, ensuring that the solution addresses the actual problem.
470 | Schedule | The project manager schedules an iteration review and learns that a few key stakeholders do NOT approve of the development of a feature. What should the project manager do first to address this issue? | Address the issue only after evaluating why these stakeholders are concerned | Ask the project sponsor to act as a neutral party in negotiation with those stakeholders who are dissatisfied | Determine the impact of the conflict by listing the pros and cons of the situation | Invite project team members to a brainstorming session to identify an appropriate response | A | This approach prioritizes understanding stakeholder concerns before taking action, allowing for a more informed and effective resolution strategy.
471 | Communications | A skincare company reports growing customer complaints about an underweight product. A project manager needs to determine if something needs to be changed in the production line. Which tool or technique can the project manager use for this task? | Affinity diagram | Scatter diagram | Histogram | Control chart | D | Control charts are ideal for monitoring process performance over time and identifying whether a process is in control or if there are unusual variations that need to be addressed.
472 | Cost | The IT integration team has a major setback in a hybrid project. Testing has confirmed that the hardware does NOT support the target operating system. The agile team's software releases must now run on a later operating system version. What should the project manager do next? | Meet with the product owner and team to update the product backlog during the sprint | Inform the team at the daily meeting and update the Definition of Done and Definition of Ready | Meet with the scrum master to determine if the product vision is still valid | Work with the agile team to run root cause analysis on why the problem did not surface earlier | A | This approach allows for quick adaptation to the new requirements by involving key stakeholders and updating the product backlog to reflect the necessary changes.
473 | Scope | A hybrid virtual reality project is running an agile software track and a predictive electronics track. Halfway into the project, delays are accumulating due to misaligned deliverable releases between the two tracks. Which two elements should the project manager combine to produce a common network diagram? | Epic breakdown with work breakdown structure | Product backlog with critical path task sequence | Definition of Done with exit criteria E) Definition of Ready with work breakdown structure | Definition of Ready with dependency milestones | D | Combining these elements helps create a comprehensive network diagram that accounts for both the start and end conditions of tasks across both agile and predictive tracks.
474 | Cost | A project manager is managing a project to develop a new software application. The project is using an agile approach. During a sprint review, a stakeholder suggests a major change to the product backlog. How should the project manager handle this situation? | Implement the change immediately to satisfy the stakeholder | Reject the change as it was not part of the original sprint plan | Escalate the issue to senior management for a decision | Add the change to the product backlog for prioritization | D | In agile projects, changes are welcome but should be properly managed. Adding the suggested change to the product backlog allows it to be prioritized alongside other items, ensuring that the most valuable work is done first.
475 | Cost | In a Scrum project, who is responsible for prioritizing the product backlog? | Development Team | Scrum Master | Product Owner | Project Manager | C | In Scrum, the Product Owner is responsible for managing and prioritizing the product backlog to maximize value.
476 | Resource | What is the primary purpose of a sprint retrospective in Scrum? | To plan the next sprint's work | To improve the team's processes and practices | To update the product backlog | To demonstrate the completed work to stakeholders | B | The primary purpose of a sprint retrospective is for the team to reflect on their processes and identify ways to improve their effectiveness and efficiency.
477 | Process | Which of the following is NOT a characteristic of an agile project? | Detailed upfront planning | Iterative development | Adaptive planning | Continuous feedback | A | Agile projects typically use adaptive planning rather than detailed upfront planning, which is more characteristic of traditional project management approaches.
478 | General | What is the recommended duration for a sprint in Scrum? | 6-8 weeks | 2-4 weeks | 4-6 weeks | 1-2 weeks | B | While sprint length can vary, the Scrum Guide recommends a sprint duration of one month or less, with 2-4 weeks being a common practice.
479 | General | Which of the following is a key principle of the Agile Manifesto? | Responding to change | Following a plan | Comprehensive documentation | Contract negotiation | A | One of the key principles of the Agile Manifesto is "Responding to change over following a plan."
480 | General | What is the purpose of a burndown chart in agile project management? | To visualize remaining work | To track team velocity | To prioritize the product backlog | To estimate story points | A | A burndown chart is used to visualize the amount of work remaining in a sprint or project over time.
481 | General | In Kanban, what does the term "WIP limit" refer to? | The maximum number of completed items | The maximum number of items in the backlog | The maximum number of team members | The maximum number of items in progress at any given time | D | In Kanban, WIP (Work In Progress) limits refer to the maximum number of items that can be in progress in any given stage of the workflow.
482 | Cost | Which of the following is NOT a typical Scrum artifact? | Burndown Chart | Gantt Chart | Sprint Backlog | Product Backlog | B | Gantt Charts are typically associated with traditional project management approaches, not Scrum. The typical Scrum artifacts are the Product Backlog, Sprint Backlog, and Increment.
483 | Resource | What is the primary role of a Scrum Master? | To manage the project timeline | To prioritize the product backlog | To facilitate the Scrum process | To assign tasks to team members | C | The primary role of a Scrum Master is to facilitate the Scrum process and help the team and organization understand and implement Scrum theory, practices, and rules.
484 | Resource | What is the purpose of a daily stand-up meeting in Scrum? | To plan the day's work in detail | To review and update the product backlog | To synchronize the team and identify impediments | To provide a detailed status report to management | C | The daily stand-up (or Daily Scrum) is a brief meeting where team members synchronize their work and identify any impediments to progress.
485 | Process | Which of the following is NOT a typical ceremony in Scrum? | Quarterly Business Review | Sprint Planning | Daily Scrum | Sprint Review | A | The typical Scrum ceremonies are Sprint Planning, Daily Scrum, Sprint Review, and Sprint Retrospective. A Quarterly Business Review is not a standard Scrum event.
486 | Scope | What is the primary purpose of user stories in agile project management? | To assign tasks to team members | To provide detailed technical specifications | To estimate project costs | To capture requirements from a user's perspective | D | User stories are used to capture product requirements from the perspective of an end user, focusing on the value delivered to the user.
487 | Resource | In agile project management, what does the term "velocity" refer to? | The amount of work completed in a sprint | The speed at which the team completes tasks | The number of story points assigned to a user story | The frequency of team meetings | A | In agile project management, velocity refers to the amount of work a team can complete in a single sprint, typically measured in story points.
488 | General | Which of the following is a key principle of Lean software development? | Maximize batch size | Eliminate waste | Increase work in progress | Optimize for resource utilization | B | Eliminating waste is one of the key principles of Lean software development, focusing on removing anything that doesn't add value to the customer.
489 | Resource | What is the purpose of a product vision in agile project management? | To provide a detailed project plan | To define the high-level goals and direction of the product | To assign roles and responsibilities to team members | To estimate the project budget | B | A product vision provides a high-level view of the product's goals and direction, guiding decision-making throughout the project.
490 | Resource | In Scrum, who is responsible for ensuring that the Development Team adheres to Scrum theory and practices? | Scrum Master | Development Team Lead | Product Owner | Project Manager | A | The Scrum Master is responsible for promoting and supporting Scrum by helping everyone understand Scrum theory, practices, rules, and values.
491 | Cost | What is the primary purpose of a sprint review in Scrum? | To update the product backlog | To plan the next sprint | To demonstrate completed work and gather feedback | To improve team processes | C | The primary purpose of a sprint review is to demonstrate the work completed during the sprint and gather feedback from stakeholders.
492 | Resource | Which of the following is NOT a typical role in a Scrum team? | Development Team Member | Project Manager | Product Owner | Scrum Master | B | In Scrum, there is no role of Project Manager. The typical roles are Product Owner, Scrum Master, and Development Team members.
493 | General | What is the purpose of story points in agile estimation? | To measure relative effort or complexity | To assign monetary value to user stories | To provide an exact time estimate for each task | To determine team velocity | A | Story points are used to estimate the relative effort or complexity of user stories, rather than providing exact time estimates.
494 | Cost | What is the primary purpose of a product backlog in Scrum? | To assign tasks to team members | To prioritize and store all desired work for the product | To list all completed work | To track team velocity | B | The product backlog is an ordered list of everything that might be needed in the product, serving as the single source of requirements for any changes to be made.
495 | Resource | In agile project management, what is the purpose of a retrospective? | To demonstrate completed work to stakeholders | To update the product backlog | To plan the next iteration's work | To reflect on and improve team processes | D | The primary purpose of a retrospective is for the team to reflect on their processes and identify ways to improve their effectiveness and efficiency.
496 | Schedule | Which of the following is NOT a typical agile estimation technique? | T-Shirt Sizing | Planning Poker | Critical Path Method | Dot Voting | C | The Critical Path Method is typically associated with traditional project management, not agile. Planning Poker, T-Shirt Sizing, and Dot Voting are common agile estimation techniques.
497 | Resource | What is the primary purpose of a sprint goal in Scrum? | To set a specific objective for the sprint | To provide a detailed list of tasks for the sprint | To prioritize the product backlog | To estimate the team's velocity | A | The sprint goal provides a specific objective that the team aims to achieve during the sprint, giving coherence and focus to the work.
498 | General | In Kanban, what does the term "pull system" refer to? | A system where team members choose their own tasks | A system where work is assigned by managers | A system where work is pulled into the next stage when capacity allows | A system where all work is done simultaneously | C | In Kanban, a pull system means that work is pulled into the next stage of the process when there is capacity, rather than being pushed regardless of capacity.
499 | Quality | What is the purpose of a definition of "Done" in Scrum? | To assign tasks to team members | To estimate the project budget | To provide a detailed project plan | To establish a shared understanding of when work is complete | D | The definition of "Done" creates a shared understanding of what it means for work to be complete, ensuring quality and consistency.
500 | General | Which of the following is NOT a principle of the Agile Manifesto? | Individuals and interactions over processes and tools | Comprehensive documentation over working software | Responding to change over following a plan | Customer collaboration over contract negotiation | B | This is the opposite of one of the Agile Manifesto values, which states "Working software over comprehensive documentation."
501 | Cost | What is the primary purpose of a sprint backlog in Scrum? | To plan and visualize work for the current sprint | To track completed work | To estimate team velocity | To list all desired features for the product | A | The sprint backlog is a plan for delivering the sprint goal and realizing the sprint forecast. It makes visible all of the work that the Development Team identifies as necessary to meet the sprint goal.
502 | Resource | In agile project management, what is the purpose of a user persona? | To represent a typical user of the product | To estimate project costs | To provide technical specifications | To assign tasks to team members | A | A user persona is a fictional representation of a typical user of the product, helping the team to understand and focus on user needs and preferences.
503 | Scope | A project manager is working on a project to modernize a bank's information technology (IT) infrastructure. The project manager recently received approval of the project's change management plan from the project sponsor. The project sponsor now requests that the project manager implement a new technology in the solution. What should the project manager do next? | Submit a change request to the change control board (CCB) | Add the new technology as a risk in the risk register | Update the schedule and cost baselines to document the new technology | Request the project sponsor to procure the new technology | A | The project manager should complete and submit a change request to the CCB. This is the correct process to follow when implementing new technology that wasn't originally planned, especially after the change management plan has been approved.
504 | Cost | A project manager is delivering a complex project for a client who has their own project manager. The client's project manager is the sole decision maker for the project but is not the delegated financial authority. For every financial decision, the client's project manager must seek approval from a higher authority. This additional step has caused significant impacts on the resource management, cost, and time of project delivery. How can the project manager resolve this problem? | Escalate the problem to the project steering committee | Raise this problem in the quarterly project status report | Discuss the problem with the client's project manager | Add the problem to the lessons learned report | A | The steering committee is an advisory body comprised of senior stakeholders and experts that provide guidance on many issues that could face companies and projects, such as budgets, new endeavors, company policy, marketing strategies, and project management concerns. The steering committee should resolve an authority issue.
505 | Scope | A project manager is working with a cross-functional team. From lessons learned, the project manager knows that this team typically raises additional requirements not in the approved scope. What should the project manager do to handle this expected behavior? | Attend daily standup meetings with the cross-functional team and key stakeholders | Guide the team to manage scope using standard agile methodology | Explain to the team that requirements cannot be changed unless the budget is unaffected | Escalate to senior management and request replacement team members | B | The best option is to guide the team to manage the scope using the standard agile methodology. This approach allows for flexibility in handling changing requirements while maintaining project control.
506 | Procurement | A project manager has requested to purchase the same parts from two vendors. Vendor A informs the project manager that they fulfilled a similar order two months ago, 2% under the original planned cost. Vendor B has delivered consistently on the orders but has announced a pricing increase. How should the project manager evaluate this situation? | Use the metrics from vendor A to request better pricing from vendor B, keeping both providers as a risk mitigation strategy | Review the work performance information of both vendors against their contracts to find the preferred supplier | Review vendor B's agreements and procurement documentation to force them to keep the original pricing | Evaluate the contract clauses to reduce the orders from vendor B and buy them from vendor A to improve project indicators | B | To evaluate the situation, the project manager should review the work performance information of both vendors against their contracts to find the preferred supplier. This allows for a comprehensive comparison of vendor performance and pricing.
507 | Resource | A project manager is working on a project charter and discovers that some of the key stakeholders in this project are moving to other departments, and their replacements have not been identified yet. What should the project manager do next? | Obtain support from the project sponsor to continue the project | Perform an impact analysis of the possible delays | Involve senior management to resolve the challenge | Put the project on hold until the replacements are identified | C | The project manager should involve senior management because they have the power to resolve staffing-related challenges, especially when it comes to key stakeholders moving departments.
508 | General | A project manager recently took over a project from a project manager who left the company. The new project manager is aware that the previous project manager had a very authoritarian management style and made all the decisions regarding the project. The new project manager notices that a senior supervisor's morale is low. What should the new project manager do? | Identify the cause of the morale issue | Speak with the supervisor and update the project issue log | Increase the supervisor's level of authority | Modify the role of the supervisor in the project | A | The new project manager should first gather additional information to identify the root cause of the low morale issue before taking any action to address it.
509 | Risk | A project manager has been informed that the first of several major deliveries from another country will be delayed. These deliveries are on the critical path, and the delay will result in a missed milestone. What should the project manager do first? | Revise the project schedule and notify the stakeholders of the delay | Register the delay in the issue log and develop an immediate action plan | Identify the parties responsible for the delay in issuing back charges for their portion | Update the project's lessons learned register and project management plan | B | When faced with a delay that will impact a critical path and milestone, the project manager should first document the issue in the issue log and create an immediate action plan to address it.
510 | Resource | An agile project team member is working on a user story that is overdue. Not having a completed user story is causing a significant delay to specific functionality and will cause the team to miss the sprint goals. The reasons for this delay are unknown to the project manager. What should be the first action for the project manager to do? | Discuss this delay at the next team standup meeting | Replace the project team member with a new developer | Request additional resources from the sponsor | Exclude this functionality in the final product | A | In an agile project, the team is empowered to discuss and agree on actions to address delays. The best first action is to discuss the delay at the next team standup meeting.
511 | Integration | A project manager who was just assigned to an information technology project found a compatibility issue with the technical infrastructure. Which step should the project manager take first to solve the problem? | Consult the project sponsor about the issue | Escalate the issue to the technical infrastructure team | Examine if there is an alternate solution | Check the lessons learned database | D | When facing a technical issue, the project manager should first check the lessons learned database to see if similar issues have been encountered and resolved in past projects.
512 | Schedule | A collocated project team faces communication issues because team members arrive and leave at different hours of the day. At a recent weekly meeting, several members were absent. What is the best way for the project manager to ensure the team is on the same level of communication? | Encourage team members to work the same hours | Discuss with the team members the importance of team meetings | Create an information radiator for public display | Schedule team meetings during core hours | D | To ensure all team members can attend meetings and receive the same information, the project manager should schedule team meetings during core hours when most team members are likely to be present.
513 | Resource | A company is expanding, and the project manager is contemplating whether to hire new resources or outsource resources from an approved vendor team. What should the project manager focus on regarding this decision? | The procurement strategy of the company and procurement standards | The cost of internal resources versus vendor resources | The cost of outsourcing to a local vendor versus a global vendor | The organization's resource strengths and skills versus the vendor's | D | When deciding between hiring new resources or outsourcing, the project manager should focus on comparing the organization's current resource strengths and skills to those of the potential vendor.
514 | Scope | An agile project to implement a new automation process in a factory is underway. The project manager needs a vendor to help with the installation. What should the project manager do before the vendor comes to work with the team? | Remind the team that the vendor works for them and that the team can make final decisions | Submit the communication matrix so that all team members and vendors are known | Hold orientation to ensure both parties share the same understanding of project goals and requirements | Delegate all key decisions to the vendor's team so the project manager does not take risks | C | Before the vendor begins work with the team, the project manager should hold an orientation to ensure all parties have the same understanding of project goals, requirements, and expectations.
515 | Cost | A project manager is helping an organization transition from traditional methods to agile. The infrastructure, data warehousing, and enterprise architecture teams operate differently than the application development teams. How should the project manager implement agile in this organization? | Ask each team to decide which agile methodology fits best for them and let them implement different methodologies based on their needs | Ask one team to implement scrum as a pilot so that all other teams in the organization can also implement scrum by learning from this team | Ask every team in the organization to implement the same agile methodology so that a one-size-fits-all solution can provide similarity across all teams | Force the top-down transition approach by asking the CEO to provide support for implementing agile in every team in the organization | A | When transitioning to agile, it's best to allow each team to choose the agile methodology that best fits their specific needs and work processes.
516 | Resource | An agile coach is counseling a large software organization using a waterfall and plans to jump into the agile or hybrid method. What would be a project manager's suggestion? | Team members succeed using hybrid methodologies, for they are already familiar with waterfall | Agile takes time to implement, but it is more suitable to implement agile and then move to hybrid | Continue using waterfall since hybrid does not fit with the organizational structure | Hybrid is the more appropriate methodology for software organizations | B | For a large organization transitioning from waterfall, it's generally better to implement agile first and then consider moving to a hybrid approach once teams are comfortable with agile principles.
517 | Resource | A company's leadership team asked a project manager about the status update of the latest iteration of a project. The project manager directed the leadership team to the project folder. The leadership team informed the project manager that a piece of specific information was not found. What should the project manager have done to avoid this situation? | Ask team members to update the project folder before sharing the link with the leadership team | Check the project folder to ensure everything is updated before sharing the folder with the leadership team | Ask the leadership team about the needed information and provide the same | Regularly update the project folder to ensure project artifacts are current | D | To avoid situations where information is missing or outdated, the project manager should regularly update the project folder to ensure all project artifacts are current and easily accessible.
518 | Cost | A company in a heavily regulated industry is planning to release a new product not previously available in the market. The CEO has asked the project manager to propose a way to ensure that competitors in the industry do not enter the market of this product before this company. Which project delivery approach should the project manager use? | Use a predictive approach as the company has previous experience with it | Include adequate resources in the budget to fast-track the project | Request an agile coach be included on the agile team to increase the speed of the releases | Implement iterations early in the product development processes, and schedule predictive tasks to be performed just before the rollout phase | D | To ensure a competitive advantage, the project manager should implement iterations early in the product development process to allow for customer feedback and adjustments, while scheduling predictive tasks for the rollout phase.
519 | Cost | In an innovative project, the customer wants a creative, large data processing platform to be delivered. However, the project's requirements cannot clearly describe the platform's function. In order to obtain continuous investment, every output that shows progress will be demonstrated to management. What kind of project approach should the project manager recommend? | Hybrid | Predictive | Agile | Iterative | C | For an innovative project with unclear requirements and a need for continuous demonstration of progress, an agile approach is most suitable as it allows for frequent deliveries and regular feedback.
520 | Risk | The government of a country intends to construct a multibillion-dollar railway across three major cities. The designs for the project will be completed within a few months after signing the contract. However, the government urgently needs and expects the project deliverables to be achieved within 24 months. When developing the project management plan, which two techniques should the project manager consider to share the risk with both parties evenly? Choose two: | Not-to-exceed time E) Early cancellation option | Graduated time and materials | Dynamic scope option | Fixed-price increments | B | To share risk evenly between parties in a large, complex project, the project manager should consider using graduated time and materials and fixed-price increments. These techniques allow for flexibility while maintaining some cost control.
521 | General | A project manager was assigned to deliver new software for university students. In this project, the software is being delivered to a specific niche of people. The project manager must develop an archetype user to understand this niche better. How should the project manager do that? | Publish a marketing plan | Create a persona character | Contract with an architecture firm | Submit a public questionnaire | B | To develop an archetype user representing the specific niche of university students, the project manager should create a persona character. This helps in understanding the target user's goals, behaviors, and needs.
522 | Schedule | A new program manager checks the status of a project. The forecast shows that the project is slightly behind schedule. However, in reporting, the project manager stated that the project was on track. The program manager asks the project manager to explain the discrepancy. The project manager explains that this is because a different estimation technique was used for the forecast. What should the project manager have done to avoid this discrepancy? | Educated the program manager in different forecasting techniques | Ensured that the program manager has the necessary knowledge to understand estimation techniques | Asked the program manager to use the same forecasting technique | Aligned the project artifacts with the new estimation technique and provided them to the program manager | D | To avoid discrepancies in reporting, the project manager should have aligned all project artifacts with the new estimation technique and provided updated information to the program manager.
523 | Scope | A company is switching from a predictive to an agile project management approach. The team is challenged with changing customer requirements. What is the best corrective action for this issue? | Develop guidelines for training and mentoring | Provide the product owner with training and acceptance training | Break down complex story points | Use the project retrospectives | C | When transitioning to agile and facing challenges with changing customer requirements, breaking down complex story points into smaller, more manageable units is the best corrective action.
524 | Scope | A project manager has been asked to manage an existing complex project. The previous project manager has already delivered some goals. While reviewing the project management plan, the project manager realizes that one of the key deliverables is missing from the project goal. What should the project manager do next to ensure the expected project value is delivered? | Confirm the expected deliverables and rebaseline the project | Use the contingency fund for more resources to complete the missing deliverable | Escalate the issue about the deliverable to the project sponsor | Track through the Requirements Traceability Matrix | A | When discovering a missing key deliverable in an existing project, the project manager should first confirm the expected deliverables with stakeholders and then rebaseline the project to include the missing deliverable.
525 | Risk | A project is delayed by one month, and a change order needs to be approved. The next change control board (CCB) meeting is two weeks away. Because of supply chain disruptions, delaying the implementation of the change for two weeks will have a two-month impact on the schedule. What should the project manager do? | Implement the change to keep the project under budget | Ask the CEO to approve and implement the change | Review the change management plan and request the change | Ask the sponsor to contact the CCB and request their approval | C | In this situation, the project manager should review the change management plan, which may include provisions for emergency CCB meetings, and request the change according to the established procedures.
526 | Scope | Halfway through implementation, the project cosponsor, who is contributing significant capital, informs the project team of an additional feature to the project deliverable. What should the project manager do? | Assess the impact of the new requirement and update the risk register | Complete the current project as planned and update it with the new requirements later | Collect the cosponsor's requirements and perform the integrated change control process | Convince the cosponsor to maintain the current scope and complete the project as planned | C | When a cosponsor requests an additional feature, the project manager should collect the requirements and follow the integrated change control process to properly evaluate and implement the change.
527 | Risk | Project team members inform their project manager of a challenge they are facing. This challenge will likely impact project timelines. What should the project manager do next? | Escalate to the project sponsor for proper resolution | Determine if the challenges the project team brings impact the critical path | Initiate a change request to extend the project timeline | Work with the team members to understand and evaluate the challenge's impact on the overall project | D | When team members report a challenge, the project manager should first work with them to understand and evaluate the impact on the overall project before taking any further action.
528 | Scope | A customer reviewed a product and requested additional features not in the requirements documentation. The work-in-progress (WIP) limits have already been optimized for the teams working on different work components. How should the project manager begin to resolve the customer requirements? | Release increments of the new items for customer validation | Obtain details for the new items and submit them to the Change Control Board Correct Answers & Explanations | Build the product according to the previously agreed customer requirements | Breakdown work on additional features with existing component teams | B | When a customer requests additional features not in the original requirements, the project manager should obtain details for the new items and submit them to the Change Control Board for proper evaluation and approval. PMP PRACTICE TEST 3
529 | Risk | A project manager has just received news that a new regulation has been adopted, and the expectation is that the project will be delivered compliant with this new regulation. It was previously documented as a low probability and moderate impact risk item. What should the project manager do to address the issue? | Update the issue log and apply corrective action. | Revise the project management plan. | Initiate a change request for the updated regulation. | Revisit the risk register and update the rating and response. | D | As the risk impact changes, it must be updated in the risk register. Revisiting the risk register and updating the rating and response is the correct action to take in this situation.
530 | Communications | A project manager has been hired to lead a multinational enterprise program with a geographically distributed team. There is a difference of opinion among team members about status reporting. How should the project manager resolve the issue? | Create a new template for status reporting. | Ask the team members to resolve the issue internally. | Adhere to the communications management plan. | Escalate the issue to the project sponsor. | C | The project manager must emphasize to the team that the reporting should be done per the communication management plan. This ensures consistency and clarity in communication across the multinational enterprise program.
531 | Cost | An agile team has members in several countries. Daily meetings are conducted in a common language over a conference call, and the project manager takes notes to track work progress. Differences in pronunciation and vocabulary make it extremely difficult for members to understand each other. What should the project manager do to improve project efficiency? | Ask team members to report daily on the work completed, work to do, and blockers, which will be sent to the team's email distribution list. | Use an electronic Kanban board to give a visual summary of the work progress for each member. | Use the call to summarize the work status as reported by members verbally. | Ask for a change in the project's budget to provide access to a real-time translation service so members can listen to the meeting in their language. | B | Using an electronic Kanban board provides a visual summary of work progress, overcoming language barriers and pronunciation differences. This solution improves project efficiency while maintaining the benefits of daily meetings.
532 | Communications | During a project, the team has had to address unexpected issues that may impact the schedule and budget, many of which require resolution before others can be addressed. The communications plan requires only weekly written reports to the client and stakeholders. How should the project manager communicate the impact of these issues? | Update the project issue log to ensure the communication issues are captured. | Revise the communications management plan for approval prior to performing any work. | Increase client and stakeholder communications as necessary. | Maintain weekly client reports as per the communications management plan. | C | Issues impacting cost and schedule should be communicated as soon as these issues are identified, regardless of the stipulations of the communications plan. Increasing communication as necessary ensures stakeholders are informed promptly about potential impacts.
533 | Communications | A project manager asks one of their team members to prepare a monthly report in a format supplied by the CEO. The day before the meeting, the project manager reviews the report, which is not formatted as requested. What should the project manager have done to avoid this situation? | Modified the communications management plan to include the new report. | Employed the interactive communications model to ensure the team member understood requirements. | Asked for the report from the team member earlier to ensure it was in the requested format. | Requested more detailed requirements about the format from the CEO. | B | As part of the communication process, the sender is responsible for transmitting the message, ensuring the communicated information is clear and complete, and confirming that the message is correctly interpreted. Using an interactive communications model would have ensured the team member understood the requirements.
534 | Communications | A 5-year highway construction project is in its third year of execution. The project manager received a complaint from an activist group in the neighborhood. What should the project manager have done to avoid this issue? | Request the formal notification complaint from the activist group | Identify the neighborhood representatives in the communications management plan. | Ask the project communications team to address the complaint. | Identify the risks associated with the highway construction project. | B | Project stakeholder identification and analyses are part of the project communication management process. Identifying neighborhood representatives in the communications management plan would have helped prevent this issue by ensuring proper engagement with local stakeholders.
535 | Scope | A project manager is beginning a new financial software project. The regulations for compliance are clear, but the requirements are not. The company is very competitive, so the customer needs results as soon as possible. Which project life cycle should the project manager choose for this project? | Incremental | Predictive | Dynamic | Iterative | A | When the requirements are unclear, and the customer needs results as soon as possible, the most suitable method is to use an incremental life cycle. This allows for delivering functionality in stages, meeting the need for quick results while accommodating evolving requirements.
536 | Communications | A project manager needs to complete reporting for sprint four. The product owner is worried about the minimum viable product (MVP) delivery. What calculation should the project manager include in the report to satisfy the product owner's concern? | Scheduled Performance Index (SPI) | Burndown Rate | Qualitative Risk Analysis | Schedule Cost Index (SCI) | B | The project manager must include the burndown rate in the report to satisfy the product owner's concern about the minimum viable product (MVP) delivery. The burndown rate measures the progress towards completing the MVP.
537 | Cost | A project manager is assigned to a new project. The requirements are still evolving, but there is a need to deliver business value quickly. What approach should the project manager take in this situation? | Develop a feature burndown chart and show progress on requirements. | Ensure scope changes are documented in the requirements traceability matrix. | Use a product backlog and complete the highest priority requirements first. | Develop mitigation strategies to address the risks of evolving requirements. | C | In a situation with evolving requirements and a need to deliver business value quickly, using a product backlog and completing the highest priority requirements first is the best approach. This aligns with Agile methodologies and allows for quick delivery of value.
538 | Scope | A project manager must obtain approval for requirements before proceeding to the delivery stage. The project manager realizes that the initial estimates were unrealistic and that the project will take much longer to complete. What should the project manager do to mitigate the problem? | Divide the project team into separate units, each member working on a different component. | Update the schedule baseline so that it is based on realistic estimates. | Break down and re-prioritize the project deliverables to allow delivery in incremental releases. | Survey the project team to determine which members can work overtime to meet the deadline. | C | To mitigate the problem of unrealistic initial estimates, the project manager should break down and re-prioritize the project deliverables to allow delivery in incremental releases. This approach allows for meeting timelines with an MVP release, which can be further enhanced over future releases.
539 | Risk | The tables show the requirements for an agile project with the anticipated return on investment (ROI), identified project risks, and the analysis details. What should be the priority order in the product backlog? | Requirement 3, Requirement 1, Risk 3, Requirement 2, Risk 1, Risk 2 | Requirement 3, Requirement 1, Requirement 2 | Requirement 3, Risk 3, Requirement 1, Requirement 2, Risk 2 | Risk 3, Risk 1, Risk 2, Requirement 3, Requirement 1, Requirement 2 | A | The priority order in the product backlog should be based on the monetary value of requirements and risks. After calculating the Expected Monetary Value for risks and considering the ROI of requirements, this order represents the correct prioritization.
540 | Communications | As part of the project sprint review, stakeholders appear uninformed and are unable to provide their agreement to move the project forward. What should the project manager do first to ensure stakeholders can approve the project deliverables? | Perform a stakeholder analysis. | Colocate the team. | Review the communications management plan. | Include the stakeholders in daily standup meetings. | C | To ensure stakeholders can approve project deliverables, the project manager should first review the communications management plan. This will help identify any gaps in stakeholder communication and allow for necessary adjustments to keep stakeholders informed and engaged.
541 | Schedule | A project manager is leading a complex software development project. The project team cannot agree on the process to use when solving a problem. What approach should the project manager take to help bring the team to a consensus? | Assign a new team leader with experience in solving similar software development problems | Exert expert authority and define the path forward for the team | Facilitate a meeting and encourage team members to develop potential solutions | Update the responsible, accountable, consult, and inform (RACI) matrix and assign the work to a different team | C | The best option is to facilitate a meeting with the team to work out the solution. A collaborative approach inspires creative problem-solving and fosters team member engagement and participation.
542 | People | A project manager is beginning a new project and forming the project team. The project manager has not previously worked with anyone from this team, and most of the team members do not know each other. Some of the team members are located in different countries. Which two actions should the project manager take to help the team work more closely together? | Allocate a budget for the team members to colocate for the project's duration temporarily E) Arrange virtual team-building sessions that allow team members to get to know each other | Select team members who have previously worked together to be allocated to the project | Identify experienced team members to mentor the less experienced team members | Identify the cultural differences and potential conflict areas to mitigate these going forward | D | The project manager should identify cultural differences and potential conflict areas to ensure that issues do not arise. They should also organize virtual team-building activities to encourage team rapport.
543 | Resource | A project manager is working on a global project with team members from several countries. The project manager plans to hold virtual meetings and on-site visits monthly to manage communications. What should the project manager do next while working with this team? | Request the team members' résumés and become familiar with the teams' experiences | Propose and establish a team charter with the rules and principles to be followed | Request the budget for weekly in-person meetings with the entire team to allow for direct contact among team members | Ask each site's IT manager to manage the virtual meeting's technical components | B | The next thing the project manager should do is establish a team charter. The team charter is a document that establishes the team values, agreements, and operating guidelines. The project manager can use this document to solve or avoid problems in the team.
544 | Cost | A project manager works in a matrix organization. Following a reorganization, project resources are reassigned to another project. What should the project manager do? | Review the communications management plan | Review the resource management plan | Refuse to release team members | Review resource needs with the functional manager | D | The project manager should review resource needs with the functional manager, as the resources must report to their functional managers. Then the project manager can develop a path to meet the project schedule and budget objectives.
545 | Resource | The project manager does not have a 100% dedicated team for an agile project. How should the project manager ensure good velocity, cycle duration, and on-time iteration completion? Choose two: | Revisit the resource log to ensure the most skilled resources are on the project | Request the product owner and stakeholders to provide cross-functional team members | Get buy-in from the product owner and stakeholders for obtaining full- time team members | Deploy additional team members, irrespective of the story points or iterations E) Use multitasking so team members can splice their time | B
546 | Risk | During a daily standup meeting, a team member raises a critical issue that could potentially lead to the project being canceled. The team started discussing how to address the issue. How should the project manager handle this situation? | Add the issue to the parking lot and schedule another meeting to address the issue | Recommend extending the next daily standup to resolve this issue | Immediately address the issue with the team during the meeting | Ask the product owner to create a new user story | A | The daily standup is no longer than 15 minutes when everyone answers questions about completing work since the last standup, plan work to complete for the next standup, identify impediments and risks or problems related to work in a round-robin fashion. Standups are for realizing there are problems - not for solving them. The project manager should add the issues to a parking lot and schedule anot
547 | Risk | During the execution of repair work, the root cause of the damage was discovered to be failures that occurred during the construction phase. The same contractor who performed the construction work is performing the repairs. Because of this, the CEO wants to negotiate with the contractor for a reduced price. What should the project manager do? | Proceed with the contractor and subtract the amount paid for supervising the previous work | Negotiate the repair work with the contractor based on a shared-risk- reward relationship | Proceed with the contractor without mentioning the issue since the previous work is closed | Negotiate with the contractor to cancel the repair work and pay compensation for the previous work | B | Since the current project does not fall into the same contract as the previous one, a collaborative approach is required. The project manager should negotiate the repair work with the contractor based on a shared-risk- reward relationship.
548 | Communications | During a product demonstration, a stakeholder suggests the product does not meet expectations. What artifact should the project manager use to assess the stakeholder's suggestion? | Minimum viable product (MVP) description | Definition of ready (DoR) | Acceptance criteria on the user story | Definition of done (DoD) | C | The acceptance criteria on the user story define the conditions that must be met for the product to be accepted by the stakeholder. This is the most appropriate artifact to assess whether the product meets expectations.
549 | Schedule | An organizational transformation project has two workstreams running in parallel between corporate headquarters and an overseas office. Before kick-off, the project manager is scheduled to meet the overseas office leader. What should be the focus of the meeting? | Help the overseas office leader communicate with corporate staff about the project | Agree on the choice of procurement strategies to be used by the overseas office | Inform the overseas office leader of the business' strategic value, the key deliverables, and their expected involvement | Define and assign a subject matter expert (SME) for the project to represent the overseas office | C | Since the meeting is scheduled before the project kick-off, it is important to set expectations with all parties involved by informing the overseas office leader about the project business' strategic value, key deliverables, and expected involvement.
550 | Stakeholder | A project is in execution. The project manager was just reassigned to another strategic project, and the project was handed off to a new project manager. The project is currently facing issues with the quality and scheduling of some deliverables. What should the new project manager review first? | Work breakdown structure (WBS) | Stakeholder register | Risk register | Quality metrics | B | As this project will touch many departments and vendors, there will be "different internal and external stakeholders." The best thing for the project manager to do is check the stakeholder register to find major requirements, expectations, the potential for stakeholders to influence project outcomes, and the project life cycle phase where the stakeholder has the most influence or impact.
551 | Cost | Although a project performs within its time, scope, and budget constraints, the project manager learns that the project sponsor is unhappy with its progress. What should the project manager have done to avoid this situation? | Developed a communications management plan | Written a project charter | Reviewed and confirmed the stakeholder analysis | Obtained approval on project requirements | C | At the beginning of the project, the project manager needs to understand the expectations and goals of each project stakeholder. These people will send messages to the project sponsor, resulting in possibly incorrect perceptions about how the project is going.
552 | Cost | While working on a long project with many changes, a team member informs a project manager that some users are uncomfortable with certain product functionalities released in the previous iteration. Which action should the project manager take? | Obtain stakeholder feedback and team insights | Update the change log and issue log | Communicate the changes to the team and external stakeholders | Ensure that the team assignments are clear | A | Obtaining stakeholder feedback and team insights on each release is part of an iterative approach to development; thus, the project manager should do so. It enables alignment among stakeholder needs, expectations, and project objectives.
553 | Resource | As agreed at the start of a predictive project, all outgoing information should be shared beforehand with the project manager. During the project, one of the team leaders communicated directly with the sponsor, bypassing the project manager. As a result, unfiltered information was conveyed to the sponsor, and important information from the team was not shared with the project manager. What should the project manager do next? | Modify the team's agreements to obtain project manager approval prior to sending out any communication | Talk to the sponsor to find out what the team leader has shared with the sponsor | Remind the team leader to always inform the project manager of any issues | Talk to the team leader to find out if they have any personal issues with the project manager | A | The project team's ground rules, which state that the project manager should receive all communication, had been agreed upon beforehand. The project manager should modify the team's agreements to ensure all communication goes through them for approval before being sent out.
554 | Resource | During the execution of a project in a remote area, team members complain about the way one team member behaves after work. What should the project manager do to solve this problem? | Review the stakeholder's expectations and discuss this with the team | Review the team norms and discuss this with the team | Call a meeting with the team to discuss the problem | Plan a team-building session to discuss the problem | B | Since the behavior of the specific team member is after work hours, but it can affect the project if other team members see it as a problem, the team norms and ground rules must be discussed with the entire team. If the ground rules are unclear, team members might have different expectations.
555 | Resource | A company has been using predictive methods for a long time and is trying to implement a few iterative initiatives within its project framework. A project manager has been appointed to lead the first project in this hybrid environment. How should the project manager build awareness of the hybrid approach within the organization? | Build the project schedule with iterative sessions and communicate this to stakeholders | Meet with the project team in order to define roles and responsibilities | Recommend iterative methodology training for senior managers | Invite key stakeholders to the daily stand-ups and project review meetings | D | Hybrid is a combination of predictive and adaptive project lifecycles; thus, a team transitioning to the agile approach from predictive needs regular daily stand-ups, retrospectives, and short iterations. By inviting key stakeholders, the project manager can build awareness of the hybrid approach within the organization.
556 | Communications | The project manager of an agile project noticed that many stakeholders are not familiar with the iterative approach and are either tentatively attending reviews or skipping them altogether. Which action should the project manager take? | Review and update the communications management plan | Record the iteration review and share it with stakeholders | Build a RACI matrix and develop a training plan for stakeholders | Identify gaps and mentor stakeholders on the iterative approach | D | Stakeholders should be aware of what the iterative approach means to attend iteration reviews and should be mentored if they do not understand what it means. Thus, the project manager should identify gaps and mentor stakeholders on the iterative approach.
557 | Resource | During a standup meeting, some team members strongly disagreed about distributing tasks. They feel tired and frustrated because task distribution has been a frequent complaint throughout the project. What should the project manager do? | Review the project management plan to determine how to manage this situation | Negotiate with the team to find a new way to distribute the work of each iteration scope | Interview these members to identify, assess, and manage their feelings about the situation | Discuss with other project managers if they had to address similar complaints in their projects | C | Every project manager needs to be able to identify, assess, and manage the personal emotions of oneself and other people and the collective emotions of groups of people.
558 | People | A senior team member was very influential and crucial to past projects. In this new project, the senior member no longer plays a crucial role and is demotivated. What should the project manager do to address this situation? | Provide incentives to increase motivation | Arrange a team meeting to discuss ways of increasing motivation | Arrange a one-on-one meeting with the team member | Ask the functional manager to speak with the team member | C | Feedback sessions are usually the best option to assess team members' concerns and build a relationship to increase motivation.
559 | People | A project manager does not attend the daily stand-up meetings frequently. After attending one particular meeting, the project manager noticed that the meeting was not productive. What should the project manager do to improve the situation? | Analyze the dynamics of these meetings, remove impediments, and provide feedback | Delegate the responsibility to the product owner to facilitate future daily review meetings | Ask the team to send meeting minutes to the project manager after each daily meeting | Start attending daily meetings to promote a better collaboration effort with the team | A | Teams run their stand-ups. The project manager should act as a servant leader, remove impediments, and coach the team as needed. It can be achieved after analyzing the dynamics of the team.
560 | Resource | A project manager is addressing an impediment to a lengthy organizational process. The project is planned for six weeks but can be finalized within three weeks. What should the project manager do? | Consider making work visible using Kanban | Meet with the project sponsor to remove the setback | Encourage the team to analyze the effect of the barrier | Assign a team member to solve the problem | A | The project manager should consider using a Kanban board to display work and assist in taking action to remove impediments.
561 | Cost | During the testing phase of a technical project, the project manager discovers some issues with the final product and subsequently learns that during the sales process, the marketing team did not include important product features in the contract's scope to minimize costs for the client. What should the project manager do to resolve the issue? | Continue with the project and register the issue in the issue log | Define a negotiation strategy for the client to deliver the product with the important features | Review the lessons learned to find a solution for this issue | Escalate the issue to the sponsor to decide to solve the problem | B | The scoping process group includes eliciting the client's true needs, documenting the client's needs, and negotiating with the client how those needs will be met. In this case, the project manager has discovered a deficiency in the scope and needs to remedy it, including informing the client and negotiating a strategy to deliver the product with the important features.
562 | Risk | A project manager is working on a deployment project to replace some equipment that will soon become obsolete. A review of the schedule and cost has revealed that a 5-month delay is likely. How should the project manager address risks from the delay? | Request to negotiate with the vendors for a longer support period | Analyze the business impact in order to reprioritize the deliverables | Ask to order new equipment immediately so there will be no support issue | Acknowledge these constraints and take them into account when planning | B | The project manager should be able to consider all constraints and provide outputs that are the best for a given context. In this case, the business impact is important.
563 | Cost | An email from a project manager to a team member is accidentally distributed to the entire global project team. It contains harsh feedback on a recent quality incident, which could have been avoided by closer attention to detail. What should the project manager do next? | Ask the team to attend a virtual meeting and discuss the email as a group | Await responses and feedback from the team about the email before responding | Send a special follow-up apology email to the intended recipient | Create a special follow-up apology email and send it to the entire team | A | Transparency is important in a team. Now that the team is aware of the situation, it can be used to discuss lessons learned; hence, the project manager should ask the team to attend a virtual meeting and discuss the email as a group.
564 | Resource | An agile project is in the first of six iterations. The team is located globally, so the meetings are in a virtual environment. After the fifth daily meeting, the project manager realizes that not all members actively participate. What should the project manager do? | Allow the team to find their way to participate fully | Ask the team members why participation is lacking | Ask each team member individually to participate in future meetings | Engage and guide the team to encourage all members to participate | D | The project manager should engage and guide the team to encourage all members to participate. The project manager must ensure that the environment can accommodate member participation.
565 | Resource | During the weekly team meeting, the project manager reviewed task progress and found that a senior team member did not follow the plan. They performed tasks by personal preference without communicating with the project manager. The senior team member is an expert and a critical resource for the project. How should the project manager address this? | Discuss this with the functional manager, then update the team charter if necessary | Discuss this with the functional manager, then update the resource management plan if necessary | Discuss this with the resource personally, then update the resource management plan if necessary | Discuss this with the resource personally, then update the team charter if necessary | D | To solve this issue, the project manager should first talk to the resource instead of the functional manager to understand the reason and try to solve the problem before escalating. If the senior team member suggests a better option for the project, then update the team charter if required. A team charter is a document that establishes team values, agreements, and operating guidelines.
566 | Resource | Which one of the following is a best practice to ensure that virtual team meetings are effective? | Prioritizing the agenda with items that require more discussion | Having the meetings recorded for participants who could not attend | Work with the virtual team members to determine communications most appropriate for them, given their location and participation in the project | Assigning a timekeeper and a note taker alternating for each meeting | C | As a best practice, you will work with the virtual team members to determine the most appropriate communications for them, given their location and participation in the project.
567 | Resource | A virtual team is midway through a sprint of a complex task and is ahead of schedule. During the daily standup, which often ends early, a new team member interrupts and asks everyone to define their role and what they worked on before this sprint. How should the project manager handle this situation? | Allow the new team member to ask the team whatever questions are needed for clarification | Respectfully inform the team member that this would be best handled in another meeting | Team members are not supposed to interrupt meetings; the project manager can ask them to keep quiet | Address the situation immediately and ensure the new team member has all the information they need to succeed | B | A standup is not the place or time to have a status meeting. The project manager should respectfully inform the team member that this would be best handled in another meeting.
568 | Cost | For a new sales report integration project, the lead sales manager and the team cannot submit a project status report on time. In addition, the report does not meet the expectations highlighted in the group review meetings. What should the project manager consider doing? | Confirm that the plan is documented and shared among the team and stakeholders | Evaluate the team's understanding of the action plan by requesting feedback | Ensure that team members have more time to deliberate and plan | Increase the frequency of the team meetings for the status report submission | B | The project manager should consider evaluating the team's understanding of the action plan by requesting feedback. It will help them understand what is meant to be delivered in the report.
569 | Resource | During the standup, a team member reported the completion of a story dependent on other stories. When the team starts working on the related stories, they cannot continue developing because the initial story is unfinished. What should the project manager do to correct the situation? | Ask the team to explain their interpretation of the definition of done (DoD) at the end of the sprint | Review the acceptance criteria with the team every time a story is pulled into the sprint | Review the sprint planning with the whole team to understand story interdependencies | Ask the product owner to review the acceptance criteria before pushing it into the sprint backlog | B | Identify the root cause analysis as a Scrum master to avoid misunderstanding within the team moving forward, not tactic. Acceptance criteria are the root of the problem; it was unclear but not discussed.
570 | Scope | A project manager is working on an internal project and notes that the visions/goals of other department leaders are not clear. It creates confusion and ambiguity within the project team, making distinguishing between the wish list and scope items difficult. Which document should the project manager review to clarify this situation? | Risk Register | Project Charter | Communications Management Plan | Stakeholder Engagement Plan | B | The project manager should review the project charter. The project is likely to fail if the documented vision and goal are unclear by team members or stakeholders. The project exists because the sponsor signed it off, and it has been in line with business strategies.
571 | Business Environment | A project manager is developing the project management plan. The project duration is set for three months due to regulatory compliance and dependency on senior staff. Which two project objectives are defined well enough to be included in the project management plan? | Reduce the company's environmental footprint by using detailed employee recycling guidelines | Improve the development process by redesigning new templates for the design documentation | Identify training needs and create a development plan to compete the delivery in three months | Develop detailed process maps to align operational activities with the new software system | C | These options are correct because the project manager has control over the project plans. The other choices are not under the project manager's authority but at an organizational level.
572 | Resource | A project manager is assigned to a mobile application development project. The project manager realizes that an agile approach is better suited for the project, but the team is not skilled in agile approaches. What should the project manager do next if the organization is open to using any project management approach? | Arrange training on agile principles and mindset for the existing project team | Request that the project be assigned to an agile project team | Ask to replace the team with members who have used agile approaches | Use a predictive approach since the project team is already familiar with that approach | A | As the project manager, you are expected to build your team by continuously enhancing their skills to meet project needs.
573 | Scope | The project sponsor approves the project scope statement. The team members would like to modify the work breakdown structure (WBS) without changing the scope and send a request to the project manager. What should the project manager do with this request? | Empower the team to make the decisions, then inform the sponsor | Determine which changes to implement and inform the team | Discuss it with the team members and decide by consensus | Decline the request and escalate it to the project sponsor | A | The project manager should empower the team to make the decisions so that the team is accountable for their accomplishments and understands their level of authority.
574 | Cost | A newly launched product prototype is receiving some customer complaints. To reduce negative feedback, the team comes up with an action plan. At the end of the quarter, however, the project manager finds no significant reduction in complaints. What should the project manager do next? | Report the status to the executive management team and seek help | Identify the key performers on the team and recognize them appropriately | Identify the team members who lack the required skills and train them | Revisit and reevaluate the project's key performance indicators (KPIs) | D | In an agile project, the project manager should revisit and reevaluate KPIs frequently to check the effectiveness of the action plan.
575 | Cost | A project manager has a new project. The work breakdown structure (WBS) and sequence of activities have been defined, but the team has difficulty estimating the duration of each activity. Which approach should the project manager take to ensure the estimates are reliable? | Ask each team member to estimate the duration of each activity | Consult other project managers for the duration estimate of each activity | Access performance records of similar past projects and use them as a reference | Consider the project schedule constraints and estimate the activities accordingly | C | The best approach is to check the PMO records of past similar projects and use them as references for estimating activity durations.
576 | Resource | A dedicated team member is disappointed in the performance increment within the team and raises this concern with the project manager. How should the project manager handle this situation? | Escalate the issue to the human resources (HR) manager | Update the resource management plan | Verify the key performance indicators (KPIs) | Meet with the team member to resolve this issue | C | The project manager should verify the KPIs to gauge the performance increment within the team and address the team member's concerns.
577 | Resource | A functional manager involved in a project complains about the latest quality metrics reports associated with all previous iterations. The team does not think this is a valid complaint. What should the project manager do first? | Perform a quality audit to validate the applied quality metrics | Review the RACI matrix to identify who is responsible for quality metrics | Fix the reports to accommodate the functional manager's complaints | Speak to the functional manager's superior to check if this is a common complaint | B | The project manager should first consult the RACI matrix to identify who is responsible for quality metrics. Responsibilities, including quality management activities, are identified within the RACI matrix.
578 | Resource | In a multidisciplinary project, a project manager delegates some project management activities to several team members. What should the project manager do? | Develop a project communications management plan and distribute it to the stakeholders | Develop a mentoring plan and include it in the project status report | Develop an organizational breakdown structure (OBS) and a work breakdown structure (WBS) | Develop a responsible, accountable, consult, and inform (RACI) chart | D | The project manager should develop and share a RACI chart with project team members and concerned stakeholders to empower project team members and delegate some project management responsibilities to them to ensure engagement.
579 | Cost | A non-colocated project team just finished a sprint with complex tasks ahead of schedule. During the retrospective, which often ends early for this team, a new team member interrupts and asks everyone to explain their roles and what they plan on working on for the next sprint. What should the project manager do? | Set up one-on-one meetings with each new team member | Address the situation immediately and answer the new team member directly | Inform the team member that this would be best handled in another meeting | Ask each team member to explain their role and what they will work on for the next sprint | C | The best way for the project manager to handle the interruption is to inform the team member that this would be best handled in another meeting, like a backlog refinement for sprint planning, not the retrospective.
580 | Resource | Due to economic implications, a company announces imminent layoffs. A project is nearing delivery, and the team worries they might lose their jobs. The team's morale is very low, and the project manager is experiencing delivery delays from the team. What should the project manager do to address team morale? | Schedule one-on-one sessions with each team member to reassure them of their value to the company | Hold a meeting with the team members who are not delivering optimally and proactively discuss their concerns | Meet with the project management office (PMO) to discuss delivery concerns | Set up a team meeting to address the upcoming changes and potential impact on the project | A | Scheduling one-on-one meetings with team members will boost their confidence and enhance their morale during periods of uncertainty.
581 | Resource | A managing director has engaged a project manager to transform the project management office (PMO) from a waterfall structure focused on software development to an agile PMO. The manager of the PMO has been particularly resistant to the change. Upon investigation, the project manager realizes that the manager's lack of agile knowledge may make them seem incompetent in front of their team of project managers and thus will not support the transformation. How should the project manager proceed? | Ask the managing director to intervene with the PMO manager to explain why this is necessary | Implement a change management strategy for all staff to ensure a process that can meet governance requirements | Ask the project team to support the transformation despite the PMO manager's negativity | Implement a training program on agile for all staff to ensure congruency of learning for everyone | D | The project manager should proceed by implementing a training program on agile for all staff, including the manager of the PMO, to ensure there is congruency of learning for everyone. Developing the manager's skills will help reduce resistance to the transition and build consensus.
582 | Risk | During a standup meeting, team members of a software development team discovered that one of the developers was struggling to complete work due to a lack of experience with test automation. The team member is worried that this might impact achieving the sprint goal. A quality assurance engineer on the team has automation testing experience and becomes aware of the problem but is busy preparing a presentation to new employees. What action would increase the chances of achieving the sprint goal? | Give the automation work to the engineer after the presentation is finished | Train the developers on quality assurance and automation work | Remove the current activity from the sprint, and reprioritize when the quality assurance engineer is available | Ask the engineer to shift their work to support the developer as soon as possible | D | Asking the engineer to shift their work to support the developer as soon as possible can increase the chances of achieving the sprint goal.
583 | Schedule | A project manager is working on a nationwide systems project that will affect business operations. Training is required to ensure everybody can use the new system. What should the project manager do first to address this concern? | Plan a training schedule to manage limited resources | Recruit additional trainers to ensure training for all users | Develop and schedule an online training program | Determine the requirements for each user function and organization | D | The project manager first needs to identify the training requirements of every user and organization before planning the training schedule or developing the training program.
584 | Resource | The imminent retirement of a key resource may impact a multiyear project. The project manager is concerned about the impact on the project. What should the project manager do? | Work with the resource manager to identify and train a replacement | Encourage the team members to volunteer for the key resource's position | Require the team members to work additional hours to make up for unassigned tasks | Advise the stakeholders that the key resource's tasks will not be completed after their departure | A | For all project teams, training requirements should be identified. Back up competencies should be required for the team.
585 | Resource | A project is currently behind schedule when a new team member, known for their high performance, is assigned to the team. While assessing the new team member, the project manager realizes that the individual lacks training for the specific project but has the skills and relevant experience to join the team. What should the project manager do? | Ensure that the team member receives training before joining the team | Decline the addition of the new team member to the team | Assign the new team member to critical activities under close monitoring while they receive training | Assign the new team member to noncritical activities without close monitoring while training is provided | D | This approach allows the new team member to contribute to the project while receiving necessary training, without exposing critical activities to potential risks.
586 | Resource | A hybrid project delivery strategy that involves an iterative design process is being used in product development, whereby the design and execution teams are not the same. As this hybrid approach is new to the company, some key stakeholders are concerned about project success. What should the project manager do? | Escalate the issue to the steering committee, requesting the design team be responsible for the execution phase | Communicate to the project management office (PMO) that a hybrid approach is too risky and recommend returning to a predictive framework | Enhance project team skills on iterative tools by providing training on an adaptive project management framework | Invite the execution team to the design reviews to build design awareness and facilitate knowledge sharing | D | Collaboration between the design and execution teams during project delivery is required to ensure success in a hybrid project delivery strategy.
587 | Scope | In an ongoing project, performance is continuously evaluated to determine benefits. Which two actions should the project manager do at the beginning of the project? | Hold regular meetings with all of the stakeholders | Review the project administration regularly E) Agree on the requirements for measurement tracking | Ensure approval of the performance parameters with the stakeholders | Simulate and predict the performance parameters for key stakeholders | C | All parties having a stake in the project must agree and sign off on the metrics to measure the project's performance. These answers reinforce this by ensuring approval of the performance parameters with the stakeholders and agreeing on the requirements for measurement tracking.
588 | Resource | During a project review meeting, an end user reports that the personal computers supplied for testing are experiencing performance degradation. Which three actions should the project manager take? | Assign ownership for the issue | Log the issue reported E) Implement a resolution of the issue | Monitor the issue continually until closure | Purchase new personal computers | A | These are the appropriate steps a project manager should take when an issue is reported: log the issue, assign ownership, and monitor it until closure.
589 | Communications | A stakeholder complains that one of the product's components is not easy to use. What should be the immediate next step for the project manager? | Clarify product acceptance criteria with the stakeholder | Raise a change request according to the stakeholder's requirement | Ask a user experience expert to explain why the component was designed that way to the stakeholder | Check if the component meets the design and performance specifications as per the acceptance criteria | D | The requirement and acceptance criteria should be agreed upon before the development work starts. Any complaints about the requirement should be checked against the acceptance criteria first.
590 | Resource | A new project manager joins an organization without formal project management processes. Some team members refuse to participate in basic tasks, such as taking ownership of action items at meetings. What should the project manager do? | Explore the benefits of project management with executives of the organization | Create an internal document outlining the benefits of project management for all team members | Set up a private meeting with the specific team members to discuss the benefits of project management | Host a meeting with the team focused on collaborative problem-solving to develop an approach to accomplishing project tasks | D | The project manager should use collaborative problem-solving to allow input from all team members without involving executive mandates, allowing for more team buy-in to accomplish the tasks.
591 | Stakeholder | During a project closing review meeting, the Project Manager notes that a software development task took longer than planned. Which action should the Project Manager take for continuous project improvement? | Update the communications management plan with reviewed details of the problem | Update the performance data in the lessons learned register | Update the risk register so the problem will not happen | Update the problem in the issue log and distribute it to the project team | B | The project is at the project closing phase, so the issue is documented in the Lesson Learned Register for continuous project improvement. The other options are only employed in execution, not during closing.
592 | Communications | A project manager manages a project with 34 team members from six countries. The project's scope is to modernize a process used for almost 40 years in the organization. What criteria should the project manager consider while developing the communication plan? | Skills diversity | Age diversity | Cultural diversity | Personal diversity | D | The project scope implies stakeholders with personal, age, and cultural diversities. The project manager must create a plan to communicate with them effectively. Technical skills are not a factor in developing the communication plan.
593 | People | A project team member suddenly approaches the project manager and asks to resign. The team member is upset because of poor treatment and consistent complaints from the technical leader. The team member explained that they were no longer willing to tolerate this treatment from the technical leader. The project manager has never had quality issues with the team member. How should the project manager handle this situation? | Speak with the team member and technical leader to analyze the conflict and resolve it through mediation | Talk to the technical leader to determine how the team member performs poorly | Allow the team member to resign and replace them since additional resources are available within the company | Discuss the situation with the team member to determine why the technical leader treats them poorly | A | The project manager should mediate between the technical leader and the team member to ensure conflict resolution and collaboration. It is important to discuss with both parties to analyze and truly understand the issues they are facing.
594 | People | A project manager used to work on predictive projects and now has started working on a project using a hybrid approach. What should the project manager do to enable the teams to focus on their mission? | Adopt servant leadership | Innovate with new processes | Apply lean methods | Implement a Scrum method | A | Servant leaders are committed to serving and prioritizing team tasks, growth, learning, development, autonomy, and well-being. The project manager moving to a different project should adopt and exhibit Servant Leadership skills before directing the team.
595 | People | A new project manager is assigned to an ongoing agile project. The project is now starting its second 4-week iteration cycle. The project manager finds significant differences of opinion within the project team, leading to major setbacks for the project. What should the project manager do to help overcome differences and bring the project back on track? | Wait for the next iteration review to let the team members discuss things and solve the problem | Allow the team to self-organize before the next iteration to solve the problem | Promote conversation among team members in upcoming review meetings to help solve the problem | Reach out to their functional managers so they can talk to the team members and solve the problem | C | Conflict is an inevitable consequence of team interaction. The project manager should take a proactive approach to resolve this conflict. Servant leaders promote collaboration and conversation within the team and between teams.
596 | People | A client has contracted a company to manage a large project in an agile environment with many subcontractors. The client gives direct orders to the subcontractors rather than the contractor's project manager. It has created conflict within the team. What should the project manager do to prevent this situation from occurring again? | Ask the client not to give direct orders to the subcontractors | Tell the team to avoid conflicts with the client | Invite the client to the team planning meeting | Keep the team informed about client expectations | C | The client's actions can be prevented by ensuring that the client understands the team's agreed approach to allocating work within the team. This understanding can be achieved when the client attends a team meeting to see how work is allocated and reviewed.
597 | Stakeholder | A project manager analyzes with relevant stakeholders to validate project alignment with organizational strategy and expected business value. Some key stakeholders missed the analysis session, so their input was not factored in. What is the main impact of these absences on the project? | There is inconsistent input on benefits from various key stakeholders | There is inconsistent input on risks from various key stakeholders | Conflict in subsequent phases of the project may result | Important project approval was not received | C | Conflicts can be generated because the stakeholders have different expectations and sometimes conflicting interests. It could lead to a dispute in the project.
598 | People | During a software development project, the team realizes that several features failed to comply with quality requirements. After receiving instructions to fix the issues, one team member becomes frustrated, claiming that unclear requirements are causing the issues. Other team members argue that negligent testing is the real cause of these issues. The testers blame poor coding quality. What should the project manager do? | Support the project team in a retrospective to identify the root cause of the quality issues | Remove the most frustrated resource from the team, as the confusion impacts team motivation | Discuss the issue with the management team to identify possible solutions to improve quality | Perform a quality review in each stage of the development life cycle to identify the reason for quality issues | A | The project team is initially responsible for conflict resolution, but the project manager can facilitate it when required. Retrospectives can address the issue; thus, the project manager should support the project team in a retrospective to identify the root cause of the quality issues.
599 | Resource | A key project team member publicly asserts that another team member has been speaking negatively about them. The team member threatens to quit their job if the project manager does not take immediate action to address the conflict. What should the project manager do first? | Call a team meeting because the project is in jeopardy without the key team member | Meet with the accused team member to understand their point of view | Decide to remove one of the two members of the team to address the conflict | Schedule a meeting in the future to allow the issue to diffuse over time | B | The project manager should meet with the accused team member to understand the situation before attempting to resolve this conflict.
600 | Risk | A Chief Technology Officer (CTO) is excited that the company uses servant leadership practices on a current project. The CTO requests that all future projects be completed using servant leadership practices. Which statement below best represents how the project manager should respond to the CTO's request? | Servant leadership can be applied to any project situation | Servant leadership is only effective in specific situations | Servant leadership only works for projects with substantial financial impact | Servant leadership practices focus on the client | A | Servant leadership can be applied to any project situation. Stating that servant leadership is only effective in specific situations, only focuses on the client, or should be applied only to projects with substantial financial impact are incorrect.
601 | People | During a multidisciplinary project, a project manager learns that there are many conflicts about design among team members from different disciplines. What should the project manager do to ensure the smooth delivery of the project? | Ensure that the project sponsor is aware of the current situation | Identify the matter as a risk and check available budget reserves | Escalate to functional managers and seek resolution | Facilitate team discussions to achieve the desired results | D | The project manager must be proactive and facilitate the resolution of any conflict within the multi-disciplinary project team.
602 | People | A team member with sufficient experience and knowledge informs the project manager about a conflict with another team member and asks for advice and help. What should the project manager do? | The project manager discusses the issue with the team members, and they decide on the solution together | The project manager and team members discuss the challenge, and the project manager chooses the solution | The project manager and team members discuss the situation, and the project manager directs the steps | The project manager and the team members discuss the situation, and the project manager leaves the decision to the team members | A | Collaborative planning and decision-making lead to team member ownership and buy-in, which results in higher motivation, which will compensate for the time and effort required to agree.
603 | People | During a retrospective meeting, some team members strongly disagreed with how the product owner and scrum master handled some issues related to the scope of the last cycle. What should the project manager do first? | Review the backlog with the product owner to ensure appropriate scope | Schedule a meeting with only these team members to discuss the scope | Collect all available information from the team and address the problem | Address the differences between the product owner and scrum master | C | Project managers realize that conflicts are inevitable but that good procedures or techniques can help resolve them. Once a conflict occurs, the project manager must collect all available information from the team, study and address the problem, develop a situational approach or methodology, and set the appropriate atmosphere or climate.
604 | People | A developer is complaining about the time spent on daily standups, updating stories, creating tasks, and reviewing dependencies between stories instead of developing code. Other team members support the comment. What should a servant leader do next? | Acknowledge the frustration and emphasize the benefit of each activity | Ask for suggestions on how to manage their time more effectively | Explain the definition of an information radiator to the project team | Reduce the interactions among team members to increase development time | A | A key role of a servant leader is to coach the team in agile practices and highlight the benefits of each activity and agile ceremonies and how they can help the team complete their tasks faster.
605 | People | A company is implementing Agile. Which action should the project manager take to ensure they act as a servant leader? | Ensure the team follows all processes as defined without questioning them | Keep strict control of the team and their activities | Serve as a backup in case a team member becomes ill | Understand the bottlenecks and support the team in removing them | D | A servant leader should be a coach and help the team change a process if the team finds a better way to do it. They should understand bottlenecks and support the team to remove them.
606 | Cost | A project manager has been assigned to a late and over-budget project. The project uses a predictive approach integrated with agile iterations for the most critical part of the scope. During the project assessment, the project manager notices that the team is afraid of making mistakes and is seeking individual recognition while lacking accountability. How should the project manager improve productivity? | Request approval to replace a few team members so the project team can understand the importance of meeting goals | Reinforce and communicate the next milestone, following individual performance and execution on a detailed level | Develop a performance management plan for each project team member and share the performance results with the team | Enable collaboration, create common goals, and celebrate group achievements while providing group rewards | D | The project manager must create a collaborative environment that focuses on common goals and group rewards and moves away from working in silos.
607 | Business Environment | During a project meeting, an important stakeholder questioned how the project aligned with the company's new mission. What should the project manager do? | Let the sponsor answer the question in the meeting | Register this query as a new risk in the risk management plan | Explain the alignment between the company's mission with the project | Amend the communications management plan to answer this question | C | The project manager should articulate the alignment between the project's objectives and the company's mission. The project manager should apply the following knowledge and information about the organization to the project to ensure alignment with the organization's strategy and mission.
608 | Cost | In the middle of a release, the project manager is replaced. Feedback provided by the team to the new project manager hinted at team friction caused by the previous project manager's constant demands for rapid delivery. What approach should the new project manager adopt to establish credibility with the team quickly? | Help the team succeed with excellent service, on-time commitments, and adequate budget | Have the team explain what is needed, create tasks, and report progress on those tasks | Do what the team needs, maintain the action log, and provide feedback | Assess the team's culture and observe and interact with them | D | To quickly establish credibility, it is important that the new project manager first observe and understand how the team works and how to serve them best.
609 | Resource | Regular check-ins with the delivery team reveal low morale and a lack of efficiency. What should the project manager do to address these concerns? | Perform a skill assessment | Conduct a satisfaction evaluation | Conduct team-building exercises | Perform roadblock-removing techniques | B | Before employing any solution, it is important that the project manager further assess the problem (survey) and then clear any remediation activities with the client. It could include team-building exercises or skill evaluations.
610 | Scope | A project manager is assigned to a new project and needs to determine the project's objectives and requirements. What should the project manager review first? | Work breakdown structure | Project charter | Scope statement | Project management plan | B | The project charter is the document that formally authorizes the project and provides the project manager with the authority to apply organizational resources to project activities. It contains high-level information about the project's objectives and requirements, making it the first document a project manager should review when assigned to a new project.
611 | Resource | During project execution, a team member informs the project manager that a critical activity cannot be completed as planned due to a technical issue. What should the project manager do next? | Inform the project sponsor | Update the risk register | Review the issue log | Implement a workaround | C | When a team member reports a critical issue, the project manager should first review the issue log to see if this or similar issues have been reported before and what actions were taken. This helps in understanding the context and potential solutions before taking further action.
612 | Schedule | A project manager is developing the project schedule and needs to determine the sequence of activities. Which tool or technique should be used? | Critical path method | Resource leveling | Precedence diagramming method | Fast tracking | C | The Precedence Diagramming Method (PDM) is a technique used in project scheduling to determine the sequence of activities. It uses boxes or rectangles, referred to as nodes, to represent activities, and connects them with arrows to show dependencies.
613 | Stakeholder | A project manager is working on a complex project with multiple stakeholders and conflicting requirements. What should the project manager do to ensure all stakeholders' needs are addressed? | Prioritize requirements based on stakeholder influence | Develop a communication management plan | Conduct a stakeholder analysis | Create a stakeholder engagement plan | C | Conducting a stakeholder analysis is the first step in addressing conflicting requirements from multiple stakeholders. This process helps identify and prioritize stakeholders based on their influence and interest in the project, which can then inform the development of engagement and communication strategies.
614 | Resource | During project execution, a team member suggests a change that could improve project efficiency. What should the project manager do first? | Update the project management plan | Consult with the project sponsor | Implement the change immediately | Submit a change request | D | When a team member suggests a change that could improve project efficiency, the first step is to submit a formal change request. This ensures that the proposed change is properly documented and goes through the established change control process for evaluation and approval.
615 | Cost | A project manager is developing the project budget and needs to estimate the cost of resources. Which technique should be used? | Three-point estimating | Analogous estimating | Parametric estimating | Bottom-up estimating | D | Bottom-up estimating is a method of estimating project costs by estimating individual work packages or activities and then aggregating these estimates to get a total project cost. This method is often more accurate than other estimating techniques, especially when estimating the cost of resources.
616 | Risk | A project is experiencing frequent scope creep, leading to delays and cost overruns. What should the project manager do to address this issue? | Increase the project budget | Implement a change control process | Fast track the project schedule | Add more resources to the project team | B | To address frequent scope creep, the project manager should implement a change control process. This process ensures that all changes to the project scope are properly evaluated, approved, and documented, helping to prevent unauthorized changes and manage their impact on the project.
617 | Risk | A project manager is developing the risk management plan and needs to identify potential risks. Which tool or technique should be used? | Ishikawa diagram | SWOT analysis | Monte Carlo simulation | Delphi technique | B | SWOT (Strengths, Weaknesses, Opportunities, Threats) analysis is a useful tool for identifying potential risks in a project. It helps in assessing both internal and external factors that could affect the project, making it a comprehensive approach to risk identification.
618 | Communications | During project execution, a stakeholder expresses dissatisfaction with the project's progress. What should the project manager do first? | Update the project status report | Review the stakeholder engagement plan | Escalate the issue to senior management | Schedule a meeting with the stakeholder | D | When a stakeholder expresses dissatisfaction with the project's progress, the project manager should first schedule a meeting with the stakeholder. This allows for direct communication to understand the stakeholder's concerns, provide updates, and discuss potential solutions.
619 | Integration | A project manager is closing out a project and needs to document lessons learned. What is the primary purpose of this activity? | To improve future project performance | To justify project expenses | To evaluate team member performance | To assign blame for project failures | A | The primary purpose of documenting lessons learned is to improve future project performance. By capturing experiences, successes, and failures from the current project, organizations can apply these insights to enhance the planning and execution of future projects.
620 | Scope | A project manager is developing the quality management plan and needs to define quality metrics. What should be the primary focus of these metrics? | Product performance | Project budget adherence | Stakeholder satisfaction | Project team productivity | A | When defining quality metrics in the quality management plan, the primary focus should be on product performance. These metrics should measure how well the project's deliverables meet the specified requirements and stakeholder expectations.
621 | Resource | During project execution, a team member reports a potential ethical violation by a vendor. What should the project manager do first? | Report the issue to senior management | Update the risk register | Terminate the vendor's contract | Investigate the allegation | D | When a potential ethical violation is reported, the project manager's first action should be to investigate the allegation. This ensures that the issue is properly understood and verified before any further actions are taken.
622 | Procurement | A project manager is developing the procurement management plan and needs to determine the appropriate contract type. What factor should be given the most consideration? | Risk allocation | Project duration | Project budget | Vendor experience | A | When determining the appropriate contract type in the procurement management plan, risk allocation should be given the most consideration. Different contract types allocate risk differently between the buyer and seller, and this allocation should align with the project's risk profile and objectives.
623 | Resource | During project execution, a team member consistently underperforms and misses deadlines. What should the project manager do first? | Reassign the team member's tasks | Escalate the issue to HR | Meet with the team member to discuss performance | Provide additional training | C | When a team member consistently underperforms, the project manager should first meet with the team member to discuss their performance. This allows for understanding the root causes of the underperformance and collaboratively developing a plan for improvement.
624 | Communications | A project manager is developing the communications management plan and needs to determine the appropriate communication channels. What factor should be given the most consideration? | Stakeholder preferences | Project budget | Team size | Project complexity | A | When determining appropriate communication channels in the communications management plan, stakeholder preferences should be given the most consideration. This ensures that information is delivered in a way that is most effective and comfortable for each stakeholder.
625 | Schedule | During project execution, a critical path activity is delayed, impacting the project schedule. What should the project manager do first? | Analyze the impact on the project timeline | Request additional resources | Fast track the project | Crash the schedule | A | When a critical path activity is delayed, the project manager should first analyze the impact on the project timeline. This analysis helps in understanding the extent of the delay and informs decisions about potential corrective actions.
626 | Resource | A project manager is developing the human resource management plan and needs to define team roles and responsibilities. Which tool or technique should be used? | Organizational chart | Resource histogram | RACI matrix | Skills matrix | C | A RACI (Responsible, Accountable, Consulted, Informed) matrix is an effective tool for defining team roles and responsibilities in the human resource management plan. It clearly outlines who is responsible for each task and how other team members are involved.
627 | Risk | During project execution, a team member identifies a potential opportunity that could significantly benefit the project. What should the project manager do first? | Analyze the potential impact and risks | Inform the project sponsor | Implement the opportunity immediately | Update the project management plan | A | When a potential opportunity is identified, the project manager should first analyze its potential impact and risks. This analysis helps in determining whether pursuing the opportunity is beneficial for the project and aligns with its objectives.
628 | Scope | A project manager is developing the scope management plan and needs to define how changes to the project scope will be managed. What should be included in this plan? | Change control process | Requirements traceability matrix | Scope baseline | Work breakdown structure | A | The scope management plan should include a change control process that defines how changes to the project scope will be managed. This process outlines the steps for submitting, evaluating, approving, and implementing scope changes.
629 | Risk | During project execution, a stakeholder requests a significant change to the project scope. What should the project manager do first? | Reject the change request | Update the project management plan | Implement the change immediately | Analyze the impact on project constraints | D | When a stakeholder requests a significant change to the project scope, the project manager should first analyze the impact on project constraints (time, cost, quality, etc.). This analysis informs the decision-making process and helps in determining whether the change can be accommodated.
630 | Risk | A project manager is developing the risk response plan and needs to determine the appropriate strategy for a high-impact, low-probability risk. Which strategy should be considered first? | Accept | Mitigate | Avoid | Transfer | D | For a high-impact, low-probability risk, transfer is often the most appropriate strategy to consider first. This involves shifting the impact of the risk to a third party, such as through insurance or contractual agreements, which can be cost-effective for risks that are unlikely to occur but would have severe consequences if they did.
631 | People | During project execution, a team member reports a conflict with another team member that is affecting their work. What should the project manager do first? | Meet with both team members to discuss the conflict | Reassign one of the team members | Ignore the conflict and focus on project deliverables | Escalate the issue to HR | A | When a conflict between team members is reported, the project manager should first meet with both team members to discuss the conflict. This allows for understanding both perspectives and facilitating a resolution that maintains team cohesion and productivity.
632 | Quality | A project manager is developing the quality control plan and needs to determine the appropriate sampling method. Which factor should be given the most consideration? | Product characteristics | Stakeholder requirements | Project budget | Team expertise | A | When determining the appropriate sampling method in the quality control plan, product characteristics should be given the most consideration. The nature of the product being produced or the service being delivered will largely dictate the most effective sampling approach.
633 | Risk | During project execution, a vendor fails to meet a critical milestone, jeopardizing the project timeline. What should the project manager do first? | Meet with the vendor to discuss the delay | Escalate the issue to senior management | Terminate the vendor's contract | Update the risk register | A | When a vendor fails to meet a critical milestone, the project manager should first meet with the vendor to discuss the delay. This allows for understanding the reasons behind the delay and collaboratively developing a plan to address the issue and mitigate its impact on the project timeline.
634 | Stakeholder | A project manager is developing the stakeholder engagement plan and needs to determine the appropriate engagement strategy for each stakeholder. Which tool or technique should be used? | Power/Interest grid | RACI matrix | Stakeholder cube | Salience model | A | The Power/Interest grid is an effective tool for determining the appropriate engagement strategy for each stakeholder. It helps in categorizing stakeholders based on their level of power (influence) and interest in the project, which informs how to manage relationships with different stakeholder groups.
635 | Risk | During project execution, a team member suggests using a new technology that could improve project efficiency. What should the project manager do first? | Analyze the potential benefits and risks | Implement the new technology immediately | Consult with the project sponsor | Reject the suggestion to avoid scope creep | A | When a team member suggests using a new technology, the project manager should first analyze the potential benefits and risks. This analysis helps in determining whether implementing the new technology would be beneficial for the project and aligns with its objectives and constraints.
636 | Cost | A project manager is developing the cost management plan and needs to determine the appropriate method for tracking project costs. Which technique should be considered first? | Net Present Value analysis | Earned Value Management | Cost-benefit analysis | Return on Investment calculation | B | Earned Value Management (EVM) is a widely used and effective technique for tracking project costs. It integrates scope, schedule, and cost data, providing a comprehensive view of project performance and allowing for early detection of potential issues.
637 | Stakeholder | During project closure, a stakeholder expresses dissatisfaction with the project outcomes. What should the project manager do first? | Reopen the project to address the concerns | Ignore the feedback and focus on project closure | Document the feedback in the lessons learned register | Escalate the issue to senior management | C | When a stakeholder expresses dissatisfaction during project closure, the project manager should document this feedback in the lessons learned register. This ensures that the information is captured for future reference and can be used to improve processes in subsequent projects. It's an important part of the project closure process and contributes to organizational knowledge.
638 | Risk | A project manager is developing the schedule management plan and needs to determine the appropriate method for estimating activity durations. Which technique should be considered first? | Analogous estimating | Three-point estimating | Parametric estimating | Expert judgment | B | Three-point estimating is often considered the best initial approach for estimating activity durations. This technique uses optimistic, most likely, and pessimistic estimates to determine a range of activity durations. It provides a more accurate estimate than single-point estimates and accounts for uncertainty and risk in the estimation process.
639 | Risk | During project execution, a team member identifies a potential risk that was not included in the initial risk register. What should the project manager do first? | Update the project management plan | Ignore the risk as it was not part of the initial assessment | Implement a risk response immediately | Analyze the potential impact and probability of the risk | D | When a new potential risk is identified during project execution, the first step should be to analyze its potential impact and probability. This analysis helps determine the severity of the risk and informs decisions about how to respond to it. It's a crucial step in the ongoing risk management process throughout the project lifecycle.
640 | Risk | A project manager is conducting a project benefits analysis with key stakeholders of an IT project. An engineer from another department informs the project manager that there are systems impacted by the solution that have not yet been identified. What should the project manager do? | Note the engineer's issue in the issue log | Review the project benefits analysis to consider the additional impact | Document this information in the risk register | Work with the team to identify all stakeholders | C | Because the issue hasn't happened yet, you must document this information in the risk register.
641 | Risk | A project manager realizes that an issue that occurred several weeks ago has negatively impacted the schedule. When the mitigation plan is initiated, it fails because the required resources are unavailable. What should the project manager have done to avoid this? | Updated the resource management plan | Reviewed and updated the risk mitigation plan | Conducted stand-up meetings to communicate project status | Sent out status reports to stakeholders | B | To ensure that the project team and key stakeholders are aware of the current level of risk exposure, project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process.
642 | Communications | A project manager invites stakeholders to a gate review meeting. What should be done at this meeting? | Ensure that all late changes to the project have been added | Evaluate if the project has met its objectives and agree on phase closure | Evaluate project risks and move on to the next project phase | Ensure that the change control board (CCB) has approved the latest project changes | B | A phase gate is held at the end of a phase. The project's performance and progress are compared to project and business documents. A decision (e.g., go/no-go decision) is made as a result of this comparison.
643 | Quality | A design project is ready to be transferred to production. What activity is required for phase closure? | Record impacts of tailoring to any process | Determine a summary budget | Ensure preventive actions are completed | Manage quality | A | Activities in Close project or phase needed to Collect project or phase records, Audit project success or failure, Manage knowledge sharing and transfer, Identify lessons learned, and Archive project information for future use by the organization.
644 | Stakeholder | When procuring, what process should the project manager implement to obtain stakeholder agreement? | Monitor and Control Project Work | Manage Stakeholder Engagement | Update Stakeholder Engagement Plan | Plan Procurement Management | B | Obtaining stakeholder agreement is performed in the Executing process group, which is carried out when project managers manage stakeholder engagement.
645 | Communications | Due to a recent incident, a dissatisfied stakeholder filed a complaint about a project that has been closed. What can the project manager do to help resolve this? | Update the risk register | Execute the relationship management plan | Review the project management information system (PMIS) archives | Consult with the project sponsor to manage the dissatisfied stakeholder | C | Because the project was closed, we must look for historical information in the PMIS archives to resolve this situation.
646 | Scope | All quality controls have passed, and a project deliverable is ready to be released to the customer. However, a change request to add new quality criteria has been approved. What should the project manager do first? | Update the risk register | Stop the release of the deliverable to the customer | Use the new quality criteria for future deliverables | Update the project management plan | D | Update the project management plan with the approved change request and then implement the approved change request in the process Direct and manage project work.
647 | Scope | After the presentation of the final product, the client expressed satisfaction that the requirements for the firm fixed price (FFP) contract were met. What should the project manager do next? | Advise the procurement team to initiate payment processing | Inform the project sponsor that the customer has accepted the deliverable | Update the lessons learned to record success factors | Obtain formal customer acceptance of the deliverable | D | Validate Scope is the process of formally accepting the completed project deliverables by the authorized stakeholder. The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of the final product, service, or result acceptance by validating each deliverable.
648 | Risk | A project's deliverables due date is approaching, but one team member's performance negatively impacts the schedule. What should the project manager do? | Acquire a more skilled resource | Remove the team member from the project | Mentor the team member | Ask the team member's line manager to provide training | C | The project manager should be proactive in helping team members to work fine on their tasks.
649 | Cost | During project implementation, the project manager reviews identified key performance indicators (KPIs) and determines that the project is within budget and on schedule. To what process does this activity belong? | Monitor and Control Project Work | Review Project Performance | Perform Integrated Change Control | Review Scope Baseline | A | Monitor and Control Project Work is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan.
650 | Process | A key stakeholder misses a project kick-off meeting. The project manager arranges a separate meeting to ensure the stakeholder understands that the project's expected business value aligns with the organization's strategy. What are the key areas that should be reviewed? | Schedule, benefits, and WBS | Cost, schedule, risks, and work breakdown structure (WBS) | Benefits, effort, and resources | Goals, objectives, benefits, and risks | D | The project kick-off meeting is usually associated with the end of planning and the start of executing. Its purpose is to communicate the project's objectives, gain the team's commitment to the project, and explain the roles and responsibilities of each stakeholder.
651 | Stakeholder | A project manager invites the new CIO to a meeting to review a project's key deliverables, milestones, roles, and responsibilities. What is the project manager's purpose for this? | Planning communications management | Identifying stakeholders | Developing the project charter | Minimizing stakeholder resistance | D | Managing Stakeholder Engagement is communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder involvement. The key benefit of this process is that it allows the project manager to increase support and minimize stakeholder resistance.
652 | Resource | During a project review, the construction manager reports that the concrete production rate has changed over the last three months. What analysis should be conducted? | Cost | Critical path | Trend | Earned value (EV) | C | Trend report examines project results over time to see if performance is improving or deteriorating.
653 | Communications | A project manager must obtain approval for a network cabling project. After preparing detailed information, some team members remain dissatisfied, as the selected equipment is new and insufficiently tested. The project manager determines that the equipment meets technology needs. What skills should the project manager use to obtain team consensus and sponsor approval? | Interpersonal | Leadership | Stakeholder engagement | Team-building | A | The project manager also performs communication roles between the project sponsor, team members, and other stakeholders. This includes providing direction and presenting the vision of success for the project. The project manager uses soft skills (e.g., interpersonal skills and the ability to manage people) to balance the project stakeholders' conflicting and competing goals to achieve consensus.
654 | Scope | A project team member identifies a quality issue that may cause the product to be rejected by the customer. However, the project sponsor wants to deliver the product. What should the project manager do? | Deliver the product | Review the quality checklist | Ensure that the product meets customer requirements | Update the issue log | C | Failure to meet the quality requirements can have serious negative consequences for any or all of the project's stakeholders. The project manager must ensure that the product meets customer requirements.
655 | Risk | Upon approval, a new project manager immediately begins a project. Three months into the project, the project manager identified numerous obstacles. What should the project manager have done? | Identified risks | Performed a qualitative risk analysis | Planned risk responses | Performed a quantitative risk analysis | A | Identifying risks is the process of identifying individual project risks and sources of overall project risk and documenting their characteristics. The key benefit of this process is the documentation of existing individual project risks and the sources of overall project risk.
656 | Procurement | Due to increased price volatility, a vendor asks the project manager to make a price change that will affect the project contract. What should the project manager do next? | Execute the approved change | Evaluate the impact, then update the risk register, project management plan, and budget | Ask the change control board (CCB) for approval | Submit a change request and analyze the impact | D | Any change needs to be analyzed and submitted to CCB for approval. Follow the steps to make changes in Perform Integrated Change Control.
657 | Cost | A project's most recent status report indicates a schedule performance index (SPI) of 1.1 and a cost performance index (CPI) of 1.2. A key stakeholder then suggests a change to include a value-added feature that would not impact the project schedule and cost. What should the project manager do next? | Advise the stakeholder that the feature will be added since the project is under budget | Advise stakeholders that changes should not be implemented when a project is behind schedule | Evaluate the change's impact with the team | Update the project management plan to include the new feature | C | Because this is a project change, the project manager needs to follow the steps to make a change, which means the project manager needs to evaluate the change's impact with the team.
658 | Resource | An ongoing cross-functional project has team members in several countries and stakeholders who provide insufficient support. How can the project manager improve this situation? | Review the stakeholder register and update the stakeholder engagement assessment matrix | Prepare a change request to collaborate and more closely manage the team | Conduct cross-cultural team-building activities and assess the results | Consult the communications management plan and update the responsibility assignment matrix (RAM) | C | The question asks about how to improve the insufficient support. Conduct cross-cultural team-building activities that enhance the team's social relations and build a collaborative and cooperative working environment.
659 | Scope | Some company board of director members feel that the organization does not possess the capabilities to handle the scope and complexity of its projects. As a result, they request an external audit of past project performances. The project management office (PMO) asks previous project managers about their availability to answer questions for the audit. What else does the PMO need? | Performance reports | Project documents | Organizational strategy plan | Enterprise environmental factors | B | The documents from previous projects containing historical information would help the PMO provide the external audit with helpful information.
660 | Scope | A project manager develops the project closure documentation to transition the final deliverables to the client. What should be used to develop the project closure documentation? | Organizational process assets and project management plan | Accepted deliverables and preliminary releases | Project management plan and preliminary releases | Accepted deliverables and project charter | A | The question asks about developing the project closure documentation, so we need OPA and PM plan to develop the project closure documentation. All components of the project management plan are an input to this process. The organizational process assets can influence the Close Project or Phase process.
661 | Resource | An issue arises on a project. A team member recalls that this issue has occurred before but cannot remember the solution. Where is the first place the project manager should look to find the solution? | Organizational process assets | Organizational policies | Escalation procedures | Checklists | A | Organizational process assets contain information on financial performance, lessons learned, performance metrics, issues, and defects that are continually updated throughout the project.
662 | Quality | During a product's testing phase, the customer discovers that a previously identified defect remains unfixed. What should the project manager do? | Assign a team member to fix the issue | Identify and discuss corrective actions with the team | Review and update the issue log | Update the risk register | C | The issue log is a project document that records and tracks all issues. It helps the project manager track and manage issues, investigating and resolving them.
663 | Communications | A project management team is developing a project management information system (PMIS) as a collaboration tool for internal and external stakeholders. A dashboard is updated monthly with information on the project's performance. What type of communication method does this describe? | Corporate intranet | Pull | Project progress reporting | Interactive | B | Pull communication is used for large complex information sets or large audiences, where recipients must access the content at their discretion. This includes web portals, intranet sites, dashboards, etc.
664 | Communications | A project manager reviews lessons learned from previous projects while preparing a project charter for a new project. The lessons learned documents show frequent issues with low engagement levels and stakeholder misalignment on project objectives. What should the project manager do to avoid repetition of this issue in the new project? | Build a common understanding among stakeholders about key deliverables described in the approved project charter | Include all stakeholders in the responsibility assignment matrix (RAM) for acceptance of the deliverables | Allow any stakeholder to join the change control board (CCB) at any time in the project | Gather every stakeholder's requirements and include them in the work breakdown structure (WBS) | A | Stakeholder satisfaction should be identified and managed as a project objective. The key to effective stakeholder engagement is continuous communication with all stakeholders to understand their needs and expectations.
665 | Scope | After stakeholders in a company's sales department examined all the deliverables, they stated that there had been a change in the company strategy. Therefore, important changes must be made to the requirements. The project manager believes that these changes make the deliverables unusable. What should the project manager do? | Evaluate and incorporate the changes to the project management plan to start executing them | Request that stakeholders specify and present the new requirements to the change control board (CCB) | Evaluate the impact on the project, coordinate with the sponsor, and close the project | Request the details about the new requirements, evaluate them with the project team, and recommend whether to continue or close the project | D | Follow the steps to make the change. The project manager should gather information, evaluate the impact with the team, and make a recommendation.
666 | Risk | An external provider is late with the delivery of a finished item. To maintain the project's schedule, the provider offers to bear the cost of renting a temporary system as a measure of goodwill. Since no schedule slippage will occur, what should the project manager do next? | Conduct the Perform Integrated Change Control process | Update the project documents | Take no further action because there is no schedule slippage | Account for this additional resource in the work breakdown structure (WBS) | A | Follow the steps to make the change. Need to assess the impact with all knowledge areas.
667 | Resource | A project manager notices that work started by the project team is misaligned with an industry regulation. The project manager recalls that this topic was previously discussed during a stakeholder meeting. What should the project manager review? | Organizational process assets | Work performance data | Issue log | Project management plan | A | To review historical information, we can find it in the organizational process assets.
668 | Risk | A project manager notices an unusually high rate of risks but has limited resources to address them. To what should the project manager refer to determine risk priorities? | Risk probability and impact matrix | Risk mitigation strategy | Risk breakdown structure (RBS) | Risk management plan | A | The probability and impact matrix helps prioritize risks by using descriptive terms or numeric values for probability and impact. This allows the relative priority of individual risks to be evaluated within each priority level.
669 | Risk | Although previously identified project risks have not yet materialized, a project appears to be in trouble. The project manager implements the appropriate risk responses but fails to keep the project on track. What should the project manager do next? | Update the risk register | Transfer the risks | Analyze the risks | Request a risk audit | A | The risk register should be updated to reflect any changes to previously agreed-upon risk responses for individual project risks that are subsequently made as a result of the Implement Risk Responses process.
670 | Risk | A project manager realizes that a new government regulation affects the current project, and to comply with the new law, the project scope should be changed. The team is now analyzing the impact on the schedule and budget. Which tool or technique should the project manager have considered before this issue occurred? | Stakeholder analysis | Stakeholder register | Risk register | Risk management plan | A | "Stakeholder register", "Risk management plan", and "Risk register" are project documents or project management plan subsidiaries. Only Stakeholder analysis is a tool and technique that could have helped identify potential regulatory impacts before they occurred.
671 | Scope | A major project deliverable is completed. What should the project manager and team do to confirm that specifications have been met? | Check the organizational process assets | Validate the quality audit reports | Verify the scope | Perform quality control Correct Answers & Explanations | D | Control Quality is the process of monitoring and recording results of quality management activities to assess performance and ensure the project outputs are complete, correct, and meet customer expectations. The key benefit of this process is verifying that project deliverables and work meet the requirements specified by key stakeholders for final acceptance. The Control Quality process determines
672 | Resource | A project manager leading the implementation of a company's new financial system needs to evaluate the system's quality. What can the project manager use to understand the project's quality metrics and policies? | Quality audits | Process analysis | Quality control measurements | Quality management plan | D | The quality management plan is a component of the project management plan that describes how applicable policies, procedures, and guidelines will be implemented to achieve the quality objectives. It describes the activities and resources necessary for the project management team to achieve the quality objectives set for the project.
673 | Cost | A project sponsor decides to add a feature to the project that affects the project's cost, schedule, and scope. The change control board approves the change. Which process governs the project manager's implementation of the approved change? | Control Cost and Schedule | Monitor Risks | Direct and Manage Project Work | Perform Integrated Change Control | C | Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project's objectives.
674 | Cost | While reviewing a status report, a project manager notices that, for six months, the coding quality for one developer is statistically lower than another developer assigned the same task. Which tool should the project manager use to trace the problem's source back to its actionable root cause? | Ishikawa diagram | Scatter diagram | Histogram | Control chart | A | Cause-and-effect diagrams, also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams, break down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem.
675 | Resource | A project execution phase overlaps with a holiday in the country where most team members are based. This phase is critical; all team members must work through the holiday. This negatively impacts team morale. What should the project manager have done to avoid this? | Better developed the resource management plan | Prepared the stakeholder engagement plan | Postponed project activities | Requested help from other teams based in other countries | A | The resource management plan is the component of the project management plan that guides how project resources should be categorized, allocated, managed, and released. It may be divided between the team management plan and the physical resource management plan according to the project's specifics.
676 | Scope | An experienced project manager is preparing a kick-off meeting for a new service assessment. A high-level description of the service has been provided. What should the project manager do next? | Develop the project charter | Develop the responsible accountable, consult, and inform (RACI) matrix | Define the project scope statement | Create the work breakdown structure (WBS) | A | With just a high-level description, there isn't enough information to define the project scope statement, but it's helpful information to develop the project charter.
677 | Cost | An unforeseen issue requires procuring a new piece of machinery critical for meeting quality specifications. From where may the necessary funds be obtained? | Contingency reserve | Key stakeholders | Project sponsor | Management reserve | D | Management Reserve is an amount of the project budget or project schedule held outside of the performance measurement baseline (PMB) for management control purposes and is reserved for unforeseen work within the project's scope.
678 | Risk | At the first team meeting, the project manager uses the risks noted in the project charter as a starting point for developing the risk register. After identifying the risks, what should the project team do next? | Calculate the management reserve | Populate a probability and impact matrix | Perform quantitative risk analysis | Develop contingent response strategies | B | After identifying risks, Perform qualitative risk analysis is carried out. This process populates a probability and impact matrix of project risks.
679 | Resource | A company has a history of implementing system integration projects using their in-house software with a vendor hardware infrastructure. A project manager, new to the company, has no prior experience with vendor integration projects. What should the project manager do? | Review the project charter | Seek expert judgment | Meet with the sponsor | Refer to the project statement of work (SOW) | B | Expert judgment is defined as judgment based on expertise in an application area, knowledge Area, discipline, industry, etc., as appropriate for the activity being performed. Any group or person may provide such expertise with specialized education, knowledge, skill, experience, or training.
680 | Cost | A project's cost performance index (CPI) is 1.05, and the schedule performance index (SPI) is 0.95. Based on this information, what is the result of the project? | On schedule and over budget | Behind schedule and over budget | Behind schedule and within budget | Ahead of schedule and within budget | C | CPI > 1.0 indicates the project is under planned cost (within budget), while SPI < 1.0 indicates the project is behind schedule.
681 | Scope | While working on a project, the project team realized that recent data center upgrades could impact the project's outcome. Certain modules of the project deliverable are incompatible with the new environment. The team identifies the appropriate steps to address the issue. What is the next step for the project manager? | Change the project schedule | Submit a change request | Request a budget increase | Update the requirements document | B | Following the steps to make changes, a formal change request needs to be issued.
682 | Quality | During an IT hardware manufacturing project, the project manager discovers that certain batches of components are failing quality inspections. What should the project manager use to lower the failure rate? | Fishbone diagram | Tornado diagram | Control chart | Probability and impact matrix | A | The Fishbone diagram, also known as the Ishikawa diagram, is used to figure out the root causes of problems.
683 | Risk | A project team member encounters an issue and identifies a workaround but fails to inform the project manager. Two weeks later, a similar issue occurred that impacted the project. What could have prevented this issue's reoccurrence? | Documenting the organizational process assets | Revising the responsibility assignment matrix (RAM) | Updating the risk register | Performing a root cause analysis | D | Root cause analysis (RCA) is an analytical technique used to determine the basic underlying reason that causes a variance, defect, or risk. When all root causes for a problem are removed, the problem does not recur.
684 | Scope | Before implementing a system upgrade, a team member discovers a critical defect in the current system that must be fixed. What should the project manager do? | Notify the project sponsor and execute the Perform Integrated Change Control process | Implement the fix and install it with the upgrade | Notify the operational manager, as this is not a project issue | Take no further action since the project scope has been finalized | A | This is an addition to the project scope, so the project manager needs to execute the Perform Integrated Change Control process.
685 | Integration | A project manager is assigned to start the charter of an IT project and review the process inputs. However, the project manager realizes that the business case does not have adequate support. What should the project manager do to resolve this situation? | Notify the project sponsor | Request that the business analysis team perform an evaluation | Propose a review of the lessons learned in similar projects | Hire an external subject matter expert (SME) | A | The project manager works closely with the project sponsor, especially when there are issues with project initiation documents like the business case.
686 | Risk | During project execution, a project team develops a new response for an existing risk that will reduce the schedule by 30 days. What document should the project manager update? | Risk register | Work breakdown structure (WBS) | Risk breakdown structure (RBS) | Mitigation plan | A | The Risk Register includes a list of potential risk responses. When a new response for an existing risk is developed, it should be recorded in the risk register.
687 | Risk | A strike at a contracted production plant affects the delivery of a project's major deliverable and impacts project objectives. To what should the project manager refer to address this issue? | Procurement statement of work (SOW) | Risk response plan | Standardized bid documents | Managing multiple suppliers' documents | B | Proper attention to the Implement Risk Responses process will ensure that agreed-upon risk response plans are executed.
688 | Cost | According to the information below, what is this project's estimate at completion (EAC), and what does it represent? BAC: US$9,000 EV: US$1,000 AC: US$1,500 PV: US$1,200 | US$9,000 - the original project budget | US$9,000 - the revised estimate for total project cost (based on performance to date) | US$13,500 - the original project budget | US$13,500 - the revised estimate for total project cost (based on performance to date) | D | First, calculate the Cost Performance Index (CPI) = EV / AC = 1,000/1500 = 0.666667. Then, calculate EAC = BAC / CPI = 9,000/0.666667 = $13,500.
689 | Risk | A supplier reports that they are over capacity, which may delay their delivery. What should the project manager update? | Stakeholder register | Project schedule | Risk register | Issue log | C | The risk register is updated with information on individual project risks. This may include adding new risks, updating outdated risks or risks realized, updating risk responses, and so forth.
690 | Procurement | Company A hires a project manager for Company B's new project. What document does the project manager need from company B to develop the project charter? | Project management plan | Scope statement | Statement of work (SOW) | Work breakdown structure (WBS) | C | The procurement statement of work (SOW) becomes a key input to many of the seller's management processes. It may contain inputs such as major deliverables, key milestones, and cost objectives.
691 | Business Environment | A project manager develops a business case during project initiation. What areas should the project manager consider when developing the business case? | Business benefits provided by project deliverables and portfolio analysis | Business benefits provided by project deliverables and the organizational strategy | Expected resource performance and the project's contribution to the strategic portfolio objectives | Expected resource performance and cost-benefit analysis | B | When developing a business case, the project manager should consider the business benefits provided by project deliverables and how they align with the organizational strategy.
692 | Cost | A client adds a new feature and requests a budget update. The development of this feature cannot extend the project schedule for more than one month. The client has already agreed to a cost per hour. What should the project manager do next? | Review the responsibility assignment matrix (RAM) | Calculate project performance using the earned value management (EVM) method | Update the resource management plan | Estimate the required number of additional project resources | D | The project manager needs to know how many additional resources are required to develop the new feature to complete it within no more than 1 month to extend the project schedule.
693 | Scope | A set of high-impact, repetitive tasks must be executed during a project. What can the project manager use to ensure that all team members consistently perform these tasks similarly? | Quality audits | Quality checklists | Quality metrics | Quality controls | B | A checklist is a structured tool used to verify that a set of required steps has been performed or a list of requirements has been satisfied. Quality checklists help ensure consistency in frequently performed tasks and incorporate acceptance criteria from the scope baseline.
694 | Scope | After identifying the root cause of defective deliverables, the project director closely examines the team performance assessment. What will the results of this method contribute to during project execution? | Project team management and the improvement of team interactions | Project team development and the improvement of the team's skill level | Project team acquisition and the analysis of combined project experience | Resource management planning and the definition of role descriptions | B | Team performance assessments contribute to project team development by identifying improvements in skills and competencies that allow team members to perform assignments more effectively and function better as a team.
695 | Cost | A project manager for a US$15 million construction project must meet a specific project milestone earlier than planned because a season-long pattern of extreme weather is expected soon. The project is already over budget, and the sponsor is unprepared to provide additional funding. Which tool or technique should the project manager use to achieve the milestone before the extreme weather begins? | Crashing | Resource smoothing | Simulation | Fast-tracking | D | Fast-tracking is a schedule compression technique where activities normally done in sequence are performed in parallel. This can shorten the project duration without additional costs, making it suitable for a project that's already over budget.
696 | Communications | A project is ready to complete the planning process, and stakeholders have reviewed and approved all planning documents. What should the project manager do next? | Create the schedule baseline | Acquire the resources | Determine the budget | Conduct a kick-off meeting | D | After completing the planning process and getting stakeholder approval, the next step is to conduct a kick-off meeting to communicate the start of the project, key milestones, and other relevant information to stakeholders.
697 | People | Two team members have continuing conflicts that affect team morale. What should the project manager do to resolve the conflicts? | Remove both team members from the team | Remove one of the team members from the team | Work with each team member using a direct and collaborative approach | Discuss a resolution with all team members | C | Conflict should be addressed early and usually in private, using a direct, collaborative approach. This method is most effective for resolving conflicts between team members and improving team morale.
698 | Resource | Which of the following is NOT a characteristic of a high-performing team? | Shared leadership | Common approach | Specialized skills | Mutual accountability | C | While specialized skills are important for team members, a high-performing team is characterized by shared leadership, mutual accountability, and a common approach. Specialization alone does not define a high-performing team.
699 | Resource | What is the primary purpose of a project charter? | To identify stakeholders | To define project scope | To estimate project costs | To authorize the project | D | The primary purpose of a project charter is to formally authorize the existence of the project and provide the project manager with the authority to apply organizational resources to project activities.
700 | Scope | Which of the following is a tool used in the Collect Requirements process? | Stakeholder register | Focus groups | Work breakdown structure | Project scope statement | B | Focus groups are a tool used in the Collect Requirements process to gather information from a group of stakeholders about their expectations and attitudes about a proposed product, service, or result.
701 | Scope | What is the main purpose of the Perform Integrated Change Control process? | To update the project management plan | To implement approved changes | To create change requests | To review all change requests | D | The main purpose of the Perform Integrated Change Control process is to review all change requests, approve changes, and manage changes to deliverables, organizational process assets, project documents, and the project management plan.
702 | Resource | What is the purpose of a project kickoff meeting? | To align stakeholders on project objectives | To develop the project schedule | To close out the project | To create the project charter | A | The primary purpose of a project kickoff meeting is to align stakeholders on project objectives, introduce team members, and set expectations for the project.
703 | People | Which of the following is NOT a type of conflict resolution technique? | Delegating | Smoothing | Forcing | Compromising | A | Delegating is not a conflict resolution technique. The main conflict resolution techniques are forcing, smoothing, compromising, confronting, and withdrawing.
704 | Risk | What is the primary purpose of a risk register? | To respond to project risks | To document project risks | To analyze project risks | To identify project risks | B | The primary purpose of a risk register is to document identified risks, their characteristics, and planned responses.
705 | Communications | What is the main purpose of a project communication plan? | To create project reports | To define communication channels | To identify stakeholders | To manage stakeholder expectations | B | The main purpose of a project communication plan is to define how project communications will be planned, structured, monitored, and controlled, including communication channels.
706 | General | Which of the following is NOT a type of project lifecycle? | Predictive | Incremental | Iterative | Linear | D | Linear is not a specific type of project lifecycle. The main types are predictive, iterative, incremental, and adaptive (agile).
707 | Stakeholder | What is the purpose of a lessons learned register? | To document project successes and failures | To manage stakeholder expectations | To identify project risks | To create project reports | A | The primary purpose of a lessons learned register is to document knowledge gained during a project, including successes, failures, and recommendations for future projects.
708 | Scope | What is the primary purpose of a work breakdown structure (WBS)? | To identify project risks | To define project deliverables | To manage project resources | To estimate project costs | B | The primary purpose of a work breakdown structure (WBS) is to decompose the project scope into smaller, more manageable components, defining the project deliverables.
709 | Procurement | Which of the following is NOT a type of project procurement contract? | Performance-based | Time and materials | Cost-reimbursable | Fixed-price | A | Performance-based is not a specific type of project procurement contract. The main types are fixed-price, cost-reimbursable, and time and materials.
710 | Communications | What is the main purpose of a project management information system (PMIS)? | All of the above | To track project progress | To facilitate communication | To store project documents | A | A project management information system (PMIS) serves multiple purposes, including storing project documents, facilitating communication, and tracking project progress.
711 | Resource | What is the primary purpose of a project management office (PMO)? | To manage individual projects | To provide project management support | To approve project charters | To allocate project resources | B | The primary purpose of a project management office (PMO) is to provide project management support, standardize processes, and facilitate sharing of resources and methodologies between projects.
712 | Stakeholder | What is the main purpose of a project stakeholder register? | All of the above | To manage stakeholder expectations | To analyze stakeholder influence | To identify project stakeholders | A | A project stakeholder register serves multiple purposes, including identifying stakeholders, analyzing their influence, and helping to manage their expectations.
713 | Risk | What is the primary purpose of a project risk management plan? | To identify project risks | To respond to project risks | To define how risks will be managed | To analyze project risks | C | The primary purpose of a project risk management plan is to define how risk management activities will be structured and performed on the project.
714 | Scope | What is the main purpose of a project scope baseline? | To identify project risks | To define project deliverables | To manage project changes | To estimate project costs | B | The primary purpose of a project scope baseline is to define the approved version of the project scope statement, work breakdown structure (WBS), and its associated WBS dictionary.
715 | General | What is the primary purpose of a project management plan? | To authorize the project | To close out the project | To guide project execution | To define project scope | C | The primary purpose of a project management plan is to define how the project is executed, monitored and controlled, and closed.
716 | Schedule | Which of the following is NOT a type of project schedule compression technique? | Resource leveling | Lead and lag | Fast tracking | Crashing | A | Resource leveling is not a schedule compression technique, but rather a resource optimization technique. The main schedule compression techniques are fast tracking and crashing.
717 | Scope | What is the main purpose of a project requirements traceability matrix? | To estimate project costs | To link requirements to their origin | To manage project changes | To identify project risks | B | The primary purpose of a requirements traceability matrix is to link product requirements from their origin to the deliverables that satisfy them.
718 | Integration | Which of the following is NOT a type of project organizational process asset? | Lessons learned documentation | Project management plan | Policies and procedures | Corporate knowledge base | B | The project management plan is not an organizational process asset, but rather a project-specific document. Organizational process assets include policies, procedures, corporate knowledge bases, and lessons learned documentation.
719 | Integration | What is the primary purpose of a project change control board (CCB)? | To review all change requests | To create change requests | To implement approved changes | To update the project management plan | A | The primary purpose of a change control board (CCB) is to review, evaluate, approve, delay, or reject changes to the project, and to record and communicate such decisions.
720 | Communications | A project manager is working on a complex project with multiple stakeholders. Which of the following is the most effective way to ensure clear communication and alignment among all parties? | Send weekly status reports via email | Use a project management software to track progress | Hold daily stand-up meetings with the core team | Conduct monthly face-to-face meetings with all stakeholders | D | Face-to-face meetings with all stakeholders are the most effective way to ensure clear communication and alignment in complex projects with multiple stakeholders. This allows for direct interaction, immediate clarification of issues, and fosters better relationships among stakeholders.
721 | Scope | What is the main benefit of using a Work Breakdown Structure (WBS) in project management? | It identifies project stakeholders | It breaks down the project into manageable components | It defines the project schedule | It helps in resource allocation | B | The main benefit of a Work Breakdown Structure (WBS) is that it breaks down the project scope into smaller, more manageable components. This helps in better planning, estimating, and controlling of the project work.
722 | Scope | Which project management process group is responsible for formally accepting the completed project deliverables? | Executing | Closing | Initiating | Planning | B | The Closing process group is responsible for formally accepting the completed project deliverables. This includes verifying that all work is completed and obtaining formal acceptance from the customer or sponsor.
723 | Cost | What is the purpose of a project kick-off meeting? | To finalize the project budget | To conduct a detailed risk analysis | To introduce team members and align on project goals | To celebrate the completion of the project | C | The primary purpose of a project kick-off meeting is to introduce team members to each other and align everyone on the project goals, objectives, and expectations. It sets the tone for the project and ensures everyone is on the same page from the start.
724 | Risk | What is the primary purpose of a risk register in project management? | To document project requirements | To track project expenses | To list all potential project risks and their mitigation strategies | To assign tasks to team members | C | The primary purpose of a risk register is to document identified risks, their potential impacts, and the planned responses or mitigation strategies. It serves as a central repository for all risk-related information in the project.
725 | Communications | What is the main purpose of a project status report? | To assign tasks to team members | To communicate project progress to stakeholders | To define project scope | To identify project risks | B | The main purpose of a project status report is to communicate the current state of the project, including progress, issues, and upcoming activities, to stakeholders. It keeps everyone informed about the project's health and performance.
726 | Communications | Which of the following is NOT typically considered a project stakeholder? | Project sponsor | Competitors | Project team members | End users | B | Competitors are not typically considered project stakeholders. Stakeholders are individuals, groups, or organizations that may affect, be affected by, or perceive themselves to be affected by a decision, activity, or outcome of the project.
727 | Scope | What is the primary purpose of a project scope statement? | To identify project stakeholders | To allocate project resources | To define project deliverables and boundaries | To establish project timelines | C | The primary purpose of a project scope statement is to clearly define what is included in the project (deliverables) and what is not (boundaries). It provides a common understanding of the project scope among stakeholders.
728 | Resource | Which of the following is NOT a typical project management software feature? | Gantt chart creation | Automatic code generation | Resource allocation | Task dependency mapping | B | Automatic code generation is not a typical feature of project management software. Project management software typically includes features like Gantt charts, resource allocation, and task dependency mapping, but not software development functions like code generation.
729 | Scope | What is the main purpose of a project milestone? | To define project scope | To assign tasks to team members | To mark the completion of a major deliverable or phase | To identify project risks | C | The main purpose of a project milestone is to mark significant points or events in a project, typically the completion of a major deliverable or phase. Milestones help in tracking progress and often trigger transitions between project phases.
730 | Risk | Which of the following is an example of a project risk? | Project budget | Project timeline | Potential loss of key team member | Project deliverables | C | The potential loss of a key team member is an example of a project risk. It's an uncertain event that, if it occurs, could have a positive or negative effect on one or more project objectives.
731 | Cost | What is the primary purpose of a project change control process? | To extend project timelines | To prevent any changes to the project | To increase project costs | To manage and document project modifications | D | The primary purpose of a project change control process is to manage and document modifications to the project scope, schedule, or budget. It ensures that changes are evaluated, approved, and integrated into the project in a controlled manner.
732 | Business Environment | Which of the following is NOT a typical project management role? | Team Member | Project Sponsor | Project Manager | Chief Financial Officer | D | Chief Financial Officer is not a typical project management role. While they may be involved in some aspects of project governance, particularly in large organizations, they are not typically part of the core project team like Project Managers, Sponsors, or Team Members.
733 | Resource | What is the main purpose of a project charter? | To identify project risks | To define project scope | To authorize the project and assign the project manager | To allocate project resources | C | The main purpose of a project charter is to formally authorize the project and assign the project manager. It provides a high-level description of the project and gives the project manager the authority to use organizational resources for project activities.
734 | Cost | What is the primary purpose of a project kickoff meeting? | To finalize the project budget | To celebrate project completion | To conduct a detailed risk analysis | To introduce team members and align on project goals | D | The primary purpose of a project kickoff meeting is to introduce team members to each other and align everyone on the project goals, objectives, and expectations. It sets the tone for the project and ensures everyone is on the same page from the start.
735 | Scope | A project manager is working on a software development project. Two customers are repeatedly submitting new feature requests. The completed scope definition for the product's next version release has already been provided to stakeholders. What should the project manager do next? | Ask to meet with the product manager to discuss reducing new requests | Meet face-to-face with stakeholders to set expectations | Assess the scope management plan to see how changes in scope are managed | Meet with the sponsor immediately to discuss project boundaries | C | The scope management plan provides details on how project and product scope will be defined, validated, and controlled. It is needed to help control the scope of the project.
736 | People | A Project Manager joins a project as a replacement on a project team. During initial meetings, the Project Manager realizes many differing opinions about addressing technical decisions. Team members do not respect each other's ideas, and the environment is becoming counterproductive. However, the team developed processes and procedures and worked smoothly and productively on the project without conflict or interruption. In what phase of development is the team? | Forming | Performing | Norming | Storming | C | Storming often starts when there is a conflict between team members' natural working styles. People may work differently for various reasons, but if differing working styles cause unforeseen problems, they may become frustrated and counterproductive. Once the team members start working together and adjusting their work habits and behaviors to be more supportive, the team has transitioned into Norm
737 | Schedule | A project manager receives the following for a new project: Assumptions Restrictions Preliminary scope. After receiving this information, what should the project manager do first? | Ensure project charter approval is obtained from the sponsor | Put together the project team and assign project tasks | Review and understand the business case and project goals | Build the project schedule and determine the critical path | C | The business case and project goals must be understood before a charter can be written. Building a team and a schedule come later in the process.
738 | Scope | A key project resource is discussing the complexity of project deliverables with the project manager two (2) weeks before the kick-off call. The resource expresses nervousness and concern regarding the deliverables. The project manager wants to ensure that the deliverables are realistic. What is the appropriate action to take? | Hold a meeting with the project sponsor to discuss the resource's concerns and revise the project charter | Implement a feasibility study and then assess and review the results | Start to identify threats and preventive actions by performing a risk assessment | Ensure the concerns are documented in the issue log for later review | B | The feasibility study will support the business case to begin a new project.
739 | General | During user testing, a client agrees to the final product. One day later, the client indicated that the final product MAY NOT be acceptable. What should be the project manager's first step in resolving this issue? | Refer to the project charter and lessons learned register | Review the project's quality management plan | Review the project's requirements documentation | Discuss concerns with the client and consult the project's acceptance criteria | D | The client says the final product MAY NOT be acceptable, so the project manager should review the acceptance criteria to see if anything was missed and understand why the client thinks the product MAY NOT be acceptable. Satisfying all acceptance criteria
740 | Schedule | The success of an ongoing agile project is measured as follows: What two (2) conclusions can be drawn from these figures? | The Team kept a steady rate of efficiency | The backlog was NOT prioritized for time to value | The Team worked less efficiently over time | The backlog was prioritized for time to value E) The Team worked more efficiently over time | B | The table shows that value increases over time (meaning late time to value) when dividing planned value/storied planned. The SPI above 1 (stories completed/stories planned) shows that the team completed more stories faster.
741 | Cost | A new product development project will be initiated in a difficult business context. Competition is driving prices down, and supply costs are rising. Why would an agile incremental project approach be the safest choice in this context? | It reduces the team size and eliminates communication bottlenecks | It provides stringent methods to reduce the cost of quality and conformity | It accelerates the delivery of business value and minimizes the risk of irrelevancy | It ensures that the project can be canceled at any time without loss | C | Accelerated business value and better-targeting result from incremental deliveries because smaller releases can go to market faster and benefit from earlier user input.
742 | Cost | The marketing director is displeased that the agile innovation team produces too many novelty products with too little business value. Which two approaches should the project manager take to correct the team's approach? | Work with the product owners to tighten value criteria in the Definition of Ready | Survey end users and integrate resulting value rank into the product backlog E) Add a process so the marketing director can approve each story | Ask the team to take a training course on direct response marketing | Increase the story sizes to integrate more valuable features | A | The Definition of Ready and user value ranking in the backlog addresses the root problem: the team is NOT focusing on value.
743 | Resource | An agile innovation team is highly productive. However, the Head of Operations informs the product owner that the company is NOT getting a sustainable return on investment from the team's work. How should the product owner address the problem? | Reduce the number of team members as necessary to guarantee a positive return on investment | Define a minimum viable product (MVP) with the team and prioritize relevant backlog items | Work with the project manager to run a retrospective and perform project cancellation | Identify minimum marketable features (MMF) and prioritize relevant backlog items | D | Frequent release of smaller incremental products is the fastest way to get the return on investment. MMFs are ready for public launch, whereas MVPs are releases that are just able to function. Reducing the team would NOT enable value acceleration, as is required in this case.
744 | Resource | A company is losing market share to disruptive competitors with new business models. A cross-functional agile team has been formed to recommend ways to recover market share. How can the team increase their chance of producing successful recommendations? | Gain a deep understanding of why customers are disappointed by the company's products | Understand how the competitors' business models can reach more consumers at a lower cost | Focus on understanding the value consumers seek and the value competitors offer | Focus on enabling profitable delivery of unique, high-quality, and innovative products | C | The first principle of the Agile Manifesto focuses on value: "Our highest priority is to satisfy the customer through early and continuous delivery of valuable software." Markets are driven by the value consumers attribute to the offerings. The team needs to focus on understanding the value consumers seek and the value competitors offer to product successful recommendations.
745 | Cost | Over the past six months, the development cost per story has risen by more than 250% due to a faulty platform that is NO longer supported. The product vision highlights the platform's unique features as a pre-requisite for the product. What should the project manager do to determine next steps? | Cancel the project as the product vision CANNOT be fulfilled | Ask the product owner to select an alternative platform | Cancel the project due to exceeding the budget constraint | Run what-if cost impact scenarios with the product owner | D | Foundational assumptions for the product can no longer be fulfilled in an economically sustainable way. The product owner will need an analysis of the possible scenarios to determine if the project can be continued.
746 | Risk | The agile team will take over from another supplier to maintain a client's website. The team notices that recent browser changes imply that most of the website's existing content would now require users to install a plug-in. How should the agile team move forward? | Inform the client about the previous supplier's negligence | Inform the client and propose an impact analysis | Deliver the code updates as defined in the contract | Update all pre-existing code to remove plug-in dependencies | B | In this case, the client needs to be aware of the impact of the recent plug-in issue on business and costs.
747 | Cost | The quarterly results show that competitors are driving prices down. The company is losing market share, and midway into a product development project, it appears the sponsoring unit is not likely to get a return on their investment. Which two actions should the project manager take to adapt the project to these new conditions? | Incrementally replace local staff with outside expert staff who can work at half the hourly rate or less | Make a cost/benefit analysis of deliverables to optimize delivery cost and speed | Fast-track the remainder of the project to deliver the intended scope with lower overhead costs E) Create an agile track to incrementally maximize value within a fixed budget | Re-scope the project to deliver the same features as the competitors to match their pricing | B | Cost/benefit analysis and fixed-budget incremental development are correct because they address the loss of profitability without disruption to business.
748 | Resource | A pharmaceutical project includes an agile team of doctors who analyze human tissue scans from drug trial patients. The CEO wants to leverage Machine Learning (ML) technology because it is proven faster and more accurate than doctors in scan analysis. How should the product owner proceed in response to the CEO's wish? | Anticipate a negative response from the team and be ready to persuade them that their time and skill will be better spent elsewhere | Record the risk in the register and plan for discussing a response in the retrospective | Work with the team to plan how to use the ML resources and produce a business case | Ask the Team to produce a SWOT analysis supporting human-based validation | C | The project owner works for the business and supports the CEO's decision. ML is an accelerative tool, NOT a replacement for experts. Working with the team to plan their new ways of working and using a business case to support the decision is in the company's and team's best interests.
749 | Business Environment | As part of an organizational change program, a company with a strong predictive culture hires an experienced project manager with agile experience and certification. Which two actions can the project manager take to start helping the company adopt agile methodologies? | Analyze all planned projects to pick the appropriate agile model | Ensure that the MoSCoW method is used to write all project requirements | Train project teams to be more self-reliant and cross-functional E) Identify opportunities for incremental business value delivery | Show stakeholders how agile can increase quality and decrease risk | D | Agile adoption is enabled through communicating and demonstrating its benefits.
750 | Resource | An agile team must decide who should represent them in the Scrum of Scrums. Which option should be used to select the best-suited team member? | Scrum | DevOps | CI/CD | Extreme Programming | B | DevOps is designed to eliminate the potential impediments and gaps that cause incidents in the development cycle, deployment, and use of software and IT resources. CI/CD is included within DevOps, and therefore, CI/CD alone would NOT address as many problems. XP and Scrum would NOT address coordination with operations.
751 | Resource | A Project Manager must successfully lead a project with diverse, globally- dispersed team members. What should the Project Manager do to develop cultural sensitivity? | Seek help from the human resource department to obtain formal training in this area | Explore each team member's culture in-depth for several weeks to be sensitive to their needs | Travel to each team member's geographic location to gain awareness of their culture and meet face-to-face | Be aware of local customs, remain flexible when working with team members, and recognize that culture is learned | D | The Project Manager must be proactive and learn what he can while maintaining flexibility.
752 | Resource | As part of effective leadership, Project Managers help team members grow and keep them motivated throughout each project. What is one trait that supports this effective leadership? | Provide a team reward for each completed task | Use daily discussion sessions to solicit and respond to the team's concerns | Stand up for the team's beliefs and be assertive | Challenge the Team by delegating project tasks | C | The Team Charter is a rare but key agile document. Created by the entire team and updated when there are new joiners. Servant Leaders must defend the Team Charter and assert its principles if challenged.
753 | Resource | A new Project Manager joins the project's daily stand-ups, only to find that the project team spends too much time discussing ways to deal with obstructions in the project. Because of these discussions, stand-ups often last well over two hours. What process should be used to deal with this issue? | Explain to team members that long discussions take time away from actual work on the project | Ask team members to invite their managers to stand-up sessions to find solutions more quickly | Tell the team members that they are required to shorten the stand-up meetings and improve on finding solutions | Insert a new team member who will manage obstacles and schedule additional meetings to discuss possible solutions | C | The project manager should explain to the team that stand-up meetings are designed to be short and to the point, 10-15 minutes. Each team member answers three questions: 1) What have you done since the last stand-up? 2) What will you do today? 3) What are your impediments or roadblocks? Problem-solving discussions are held outside the daily stand- up and only with those who need to attend. Team me
754 | Resource | A project needs a specialized resource. A resource that fits the project's needs is identified and can work on-site but lives in another country. The visa process was expected to take weeks but is now taking months. What should the project manager do? | Request that the resource work virtually | Put the project on hold for an equivalent duration | Place a limit on the project's scope | Ask the existing team to work overtime | A | The globalization of projects has promoted the need for virtual teams that work on the same project but are not collocated.
755 | Scope | A Project Manager joins a project that has the following features: -Globally distributed team -Budget that is fixed -Very tight deadlines. What should the Project Manager do during planning to avoid scope creep and keep the team focused on delivering a product that meets requirements? | Disallow stakeholders from directly interacting with the development team lead | Ask that all development team leads prepare detailed requirements | Hold daily stand-ups with all development teams | Put any changes to scope through the formal approval process | D | Scope creep can be avoided by adherence to the agreed-upon change management process.
756 | Resource | Necessary changes are being requested to a project; however, team members do not agree regarding how to implement the changes. The Project Manager needs to address this issue. Which action should the Project Manager take? | Schedule an in-person meeting with the project sponsor and the board to address the issue | Use the change management plan and ensure all team members and stakeholders understand and follow it | Ensure all requested changes are applied to the project and communicate face-to-face with all team members | Hold a meeting with team members to assess the issues and request changes where needed | B | The change management plan describes how the change requests throughout the project will be formally authorized and incorporated.
757 | Resource | There are concerns about the cost risk of adding an external supplier at the mid-point of a project. Still, several team members have been transferred to another project, and the Project Manager requires resource support from an external supplier. The Project Manager needs to work with the procurement team to establish specifications and the type of contract to be used. What should be done? | Suggest a cost-plus incentive fee (CPIF) contract | Suggest a fixed price incentive fee (FPIF) contract | Recommend a firm fixed price (FFP) contract | Recommend a time and material (TM) contract | B | A Fixed Price Incentive Fee Contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as defined by the contract), and the seller can earn an additional amount if the seller meets defined performance criteria. FPIF contracts are the most risk-averse.
758 | Cost | An empowered agile team showed impressive progress in the first four iterations, but the product owner has noticed low output in the last five iterations without any apparent reason. What could be the cause of this situation? | The Team was in the storming stage of the development and now has moved to norming | A specific underperforming team member is most likely slowing the team down | The Team worked on low-complexity stories from the backlog in the first four iterations | Technical debt has set in, and the team's output will keep dropping until the cause is eliminated | C | Some agile teams want to favor faster progress by completing less complex stories before more complex ones. Prioritization of backlog should be value-based, not speed-based.
759 | Scope | A project that is nearing completion has the following characteristics: It is very large. It contains functional groups in five different countries. Closeout documents are being prepared. The Project Manager needs to gain acceptance of the project deliverables. What should the project manager do? | Contact managers from the five countries involved in the project for sign-off | Seek the project sponsor's sign-off | Contact the steering committee for sign-off | Seek sign-off from the director of the Project Manager's business unit | B | The project charter determines who will sign off on the project, but of the given options, the sponsor is the best answer due to their role.
760 | Communications | A project has the following characteristics: -Is in the process of completing the planning stage. -A key stakeholder will be unavailable for 2.5 weeks during the project. After learning about the key stakeholder's unavailability, the Project Manager must decide what to do first. What is the correct step to take? | Request that the finance department provide a replacement during the stakeholder's absence | Continue planning and acknowledge the change's impact on the project schedule | Organize a meeting with the sponsor to evaluate the situation and identify alternatives | Ensure that the issue log is updated and inform the other stakeholders | D | The FIRST thing the project manager needs to do is to capture this as an issue and communicate this to the other stakeholders. Until then, no action can or should be taken.
761 | Resource | The Project Manager reviews the issue log and sees three tasks assigned to three team members are significantly behind schedule. How should the Project Manager handle this issue? | Contact the project sponsor and escalate the issue to reduce delays | Meet with the relevant team members to review the tasks and determine a strategy for resolving the issue | Ask those who are responsible for the reason for the delays and their plans for the next steps | Instruct the Team to quickly update the tasks so the project is not at risk | B | Since the three tasks are behind schedule, there is a possible risk to the project. The Project Manager needs to be proactive and review the activities with the team to identify resolution strategies.
762 | Stakeholder | Although a previously-identified technical issue has been resolved, the Project Manager is warned that the same issue will likely occur on similar projects. Which document should be part of the first step in responding to the warning? | The issue log | The lessons learned register | A risk report | A communication for the project sponsor | B | The lessons learned register can be used for future projects to help avoid past project issues.
763 | Scope | A week before the project kick-off call, a project manager meets with a key project resource to gain a deeper understanding of the complexity of the project deliverables. The resource expresses concern and worry regarding the deliverables. How can the project manager ensure that the deliverables are realistic? | Perform a feasibility study and then assess the results | Note the concerns in the issue log to review at a later date | Identify threats and preventive actions by conducting a risk assessment | Discuss the resource's concerns with the sponsor and modify the project charter | A | To ensure the deliverables are realistic, the project manager must conduct a feasibility study and evaluate the results. None of the other choices will ensure realistic deliverables.
764 | Cost | A project manager needs to ensure that all data security requirements are covered during a data warehouse development project's execution phase. Each database created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? | Plan a database development specification, then regularly check to ensure the work aligns with the specification. | Add a quality assurance specialist resource to the project team, who will be responsible for monitoring the data security quality of the project. | Tell the database developer to submit documentation of data security items and the steps they need to take to correct items that do NOT meet specifications. | Arrange for a quarterly review of the data security status and recommend remedial steps if noncompliance is found. | D | This is the official answer provided by PMI. The emphasis here is on quality management, particularly the Control Quality process, as the question addresses data security compliance during the execution phase. This option's emphasis on "meetings" and "reviews" aligns with quality control techniques.
765 | Business Environment | A project team learns about a new compliance requirement from an international entity that may impact the baseline business case for the project. They learn this right after the project charter is completed and the project sponsor has signed. How should the project manager proceed? | Ignore the issue, as the new requirement is NOT part of the project's documented scope. | Ensure the requirement is documented in the risk register, then ask for further guidance from all stakeholders. | Research the requirement and possible consequences, then give the sponsor a recommendation. | Address the requirement through the creation of a quality management plan. | C | The context of this scenario requires the project manager to influence the organization (sponsor) and recommend the next steps after reviewing and understanding compliance requirements and consequences.
766 | Resource | A Canadian start-up company announces to the press its imminent launch in the European Union (EU) and Latin America. Soon afterward, the compliance team recommends delaying the launch by six (6) months to avoid substantial penalties related to a new set of EU regulations. Which approach could the project manager take to advance the launch project while preparing the compliance measures? | Replan the predictive project as a Large-Scale Scrum life cycle and use story points to estimate approval milestones. | Split work affected by the regulations into an agile track and replan unaffected work in the predictive schedule. | Estimate the impact of penalties on the project, increase the contingency reserve accordingly, and resume the project as planned. | Run a SWOT analysis to weigh priorities between compliance and consumer needs, and resume the project if the result favors consumers. | B | The agile track is correct because a launch project would include time-sensitive milestones; thus, the work is more suited to the waterfall. However, the compliance work should run concurrently with gathering more information to support the launch.
767 | Procurement | Two (2) months into a three (3)-year mobile telecom roll-out, the project manager discovers that approximately fifteen percent (15%) of the equipment is prohibited for delivery because of an embargo. The procurement contract does NOT cover the embargo case, but the company could incur severe penalties for incomplete delivery. What is the appropriate solution for the situation? | Accept the client's penalties, close the project, and cease business in the country. | Explore insurance and contingency options to cover the cost of the risk. | Add an agile track to explore and plan the delivery of alternative equipment. | Compare the penalty costs of delivering or not delivering and choose the lower one. | C | The project has contractually committed to deliver infrastructure to the customer. Failure to account for the embargo is the fault of the vendor, NOT the client. Adding an agile track is the only choice to fulfill the committed deliverables.
768 | Resource | The legal team informs the product owner that another company owns a patent for an innovation used in the agile team's product, which is now 75% complete. What should the product owner do to determine the appropriate way forward? | Work with the legal department to find markets where the patent is NOT registered. | Continue work on the product after removing the patented component. | Terminate the project immediately to prevent any further sunken costs. | Perform marginal economics analysis and identify minimum releasable features. | D | A foundational assumption to release the product has become a "show-stopper". Marginal economic analysis determines if there is a viable way forward. Identifying minimal releasable features can mitigate the economic loss.
769 | Business Environment | A new regulation requires consumer warnings on labels, but a company's product package is too small to fit the additional information. The regulatory specification does NOT provide a solution, so the agile team decides to solve the problem by displaying the information on a fold-out flap. The start of mass production of the new labels, the project's next milestone, is scheduled to begin in five days. What should the agile team do next? | Update the sprint backlog to reflect the additional product label requirement. | Contact the compliance team to determine the validity of the selected format. | Develop a prototype and submit it to the label manufacturer for approval. | Develop a prototype and submit it to the steering committee for approval. | B | Without validating compliance with the solution before developing it, the team would waste effort at best and, at worst, put the organization at risk of non-compliance penalties.
770 | Resource | A project manager leaves the company and is replaced. The new project manager is excited to start guiding the team toward project success. What should the new project manager do first? | Review the project diary and look for notes made by the former project manager. | Revisit the project budget and schedule to determine if extra time is required. | Modify the project schedule, adding a new activity related to the knowledge transfer process. | Review the project charter to identify goals and deliverables. | D | The project charter is one of the most important project documents. It defines many aspects of the project that are critical to the new project manager's understanding of the project strategy and tactical execution.
771 | Scope | Project N is a business merger in a highly regulated industry. The project sponsor and a high-level executive have requested changes disregarding legal requirements. What should be the first step in the project manager's response? | Immediately schedule a meeting with the stakeholders to review the situation. | Review the organization's lessons learned database for precedents and direction. | Send the change control board (CCB) a change request. | Check with the organization's relevant legal practitioner for guidance | D | Checking with your trusted legal representative is the best first step before going to the CCB because the project is in a highly regulated industry.
772 | Risk | A new law is expected within the next six (6) months that will affect a business' product line. The next product is launching and should be completed within three (3) months. Unfortunately, the new product will NOT meet the proposed law's requirements. How should the project manager respond to this potential problem? | Schedule a meeting with the sponsor and key stakeholders to discuss risks. Then, using the meeting results, revise the assumption log and project charter. | Schedule a meeting with the sponsor and key stakeholders to warn them about the law. Then, advise them to cancel the project until the legislation is finalized. | Revise the risk management plan. Then, move ahead with planning the project. | Move ahead with the project, following the plan. Then, ensure on-time completion so the product will NOT be affected by any possible rule change. | A | This new law can have a profound effect on the project. It will certainly lead to new potential risks, new assumptions, and a possible charter change.
773 | Scope | A project has the following characteristics: It is in the execution stage. A new law requires immediate compliance. This law will impact the project's scope, schedule, and cost. What are three possible actions to ensure compliance? | Initiate avoidance of the risk. | Escalate the issue to senior management. | Update the issue log. E) Begin the change request process. | Ensure the project management plan is updated. | B | A change request must be submitted since compliance is mandatory and impacts scope, schedule, and cost. Other possible actions are updating the issue log and escalating the issue to senior management to find a timely workaround, which could eventually be resolved as a change.
774 | Cost | At the end of an agile project, all stories are completed on schedule, and all tests passed, but the customer does NOT consider the product a success. Which is the most effective way to prevent this outcome in future projects? | Ensure that the test plan includes non-functional requirements in the backlog. | Collect customer feedback on incremental release demos and user tests. | Agree with the customer on success criteria to be included in the Definition of Done. | Ensure that the customer approves the product vision before developing the backlog. | B | Continuous and incremental customer/user feedback is the best way to ensure that the product addresses identified and non-identified needs throughout development.
775 | Procurement | An energy infrastructure vendor delivers a complex solution proof of concept to a new strategic customer. The predictive project should be completed in 10 weeks, but there will be a long list of outstanding items, and some depend on external events with uncertain scheduling. How should the project manager handle the outstanding items? | Add resources and crash the schedule to complete outstanding tasks. | Plan five agile iterations to complete the tasks as soon as conditions allow. | Transfer the outstanding items to the next project with the customer. | De-scope the outstanding tasks and remove them from the invoice. | B | Five (5) sprints can cover the ten (10) week window, and flexibility gives the best chance to complete work in an ad-hoc manner.
776 | Scope | A project is completed, but the project manager and project team members are being asked to do the following: Troubleshoot and resolve technical issues, Evaluate new requirements, Make minor adjustments. The project manager needs to ensure that the product developed by the project now has operational support. What should the project manager do? | Procure project acceptance. | Since the product is still under development, continue to fulfill the requests. | Contact the project team, dismiss them from the project, and find a new project. | Execute the project hand-off. | D | In the Close Project or Phase process, the project team formally transitions the final product, service, or result to the production support team. The receiving group signs documentation, agreeing to accept the final product, service, or result.
777 | Resource | Project team members spend much time helping maintenance and operations staff with a recently commissioned project component. The project manager must validate that the component was signed off and ownership transferred. Which three (3) documents should the project manager use for this decision? | Procurement agreements, stakeholder engagement plan, and organizational process assets updates | Final report, project document updates, and organizational process assets updates | Procurement agreements, project document updates, and organizational process assets updates | Final report, organizational process assets updates, and procurement agreements | B | When closing the project, the project manager reviews the project management plan to ensure that all project work is completed and the project has met its objectives. The project documents are updated accordingly.
778 | Scope | Review the following steps. 1. A project has been successfully delivered. 2. The project manager is executing formal closure. 3. ______________________________________. What is step 3? | The project manager should reallocate the unused funds. | The project manager should obtain stakeholder acceptance. | The project manager should update the bid documents. | The project manager should reassign the project team. | B | Accepted deliverables that the customer or sponsor formally signed off during scope validation are then forwarded to the Close Project or Phase process. Formal documentation is then signed by the customer or sponsor acknowledging final acceptance of the project's deliverables.
779 | Scope | Review the following project characteristics: The project is in the initiation phase. Due to lack of funding, the project is terminated. The project manager must close the project. What is the first action the project manager should take? | Determine the potential impact of terminating the project by performing a risk analysis. | Rely on the communications management plan to properly inform all stakeholders. | Examine the organization's project closure guidelines. | Close all project procurement processes. | C | Project closure guidelines or requirements will contain the organization's procedures to follow.
780 | Scope | After a project ends, the project manager and project team members are still being asked to do the following: Evaluate new requirements, Make minor modifications, Solve technical issues. The project manager wants to ensure the product or service developed by the project now has operational support. What should the project manager do? | Review the acceptance criteria and get acceptance. | Continue to fulfill the requests as the product is still being developed. | Formally disband the project team and find a new project. | Complete the hand-off of the project. | D | Project closure and hand-off will transfer knowledge to production and/or operations.
781 | Scope | A client brings a project manager into a project during the project's execution stage. The project manager reviews the project scope for cost- estimating purposes and notices that some deliverables were missed in the work breakdown structure (WBS). Which step should the manager take next? | Ask the project management office (PMO) to approve additional funds for this work. | Include the work in the WBS, per the 100% rule, and recalculate the total project cost. | Determine whether these deliverables are necessary by verifying with experts in the field. | Verify with the stakeholders to see if these missed deliverables should be added. | B | The 100% rule states that any work package in the WBS should consist of 100% of all work for that work package. Since the WBS is a work package (the project), and since it should contain all work in scope, any missing work packages should be added to the WBS and the total project cost recalculated.
782 | Resource | A project manager has completed the following steps: Finished a major IT deployment project, Confirmed with the release manager that all systems are working, Confirmed the quality assurance team has verified that functionality, Informed the customer. Which next step should the project manager take? | Add the lessons learned to the organization's knowledge base. | Ensure that the procurement plan is closed out. | Review, verify and complete the release documentation. | Update the risk register, stakeholders, and team members. | A | During project closeout, lessons learned and knowledge gained throughout the project are transferred to the lessons learned repository for use by future projects. This is an important step in organizational process assets updates.
783 | Scope | Review the following project characteristics: A sponsor approves a project. The project manager invites selected team members, key stakeholders, and the sponsor to a meeting. The primary purpose of the meeting is to create a document that will guide the team in defining the main project deliverables. What will be the final output of this meeting? | Requirements management plan | Milestone list | Work breakdown structure (WBS) dictionary | Scope management plan | D | The scope management plan is a component of the project management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. This document guides the team in defining the main project deliverables, which aligns with the purpose of the meeting described in the question.
784 | Resource | A medical equipment vendor is running a hybrid project that includes some custom software development by an agile team. The team's progress is good, but slow customer approval causes unnecessary delays. The customer insists that approval can only be given after repeating all the test cases in the target environment. How can the project manager accelerate the approvals and build customer trust simultaneously? | Propose new terms for team members to work aside from the customer testers to run tests in their environment. | Invite the customer to send representatives to witness the team's testing to pre-approve the tests. | Allow the team to progress at their pace while the customer continues to test and approve earlier builds. | Work out an arrangement with the customer to defer as many tests as possible to the final release. | A | Agile seeks to maximize transparency between supplier and customer and optimize to remove unnecessary work. Combining teams to remove work duplication is the best option. Witnessing only would NOT remove duplicated work; deferring tests is always bad practice because defects are NOT detected at the earliest possible point, and unsynchronized progression between the teams could cause rework if defe
785 | Stakeholder | An organizational change program has met with internal resistance, a previously identified risk. A logistics manager is particularly affected due to the reduction of the team size and the rate of change driven by agile planning of the predictive implementation. The manager's supervisor formally requested the change program to delay implementation for the logistics team. What should the project manager do next in response to this request? | Review the risk register and implement the relevant risk response for the case. | Request that the sponsor escalate the strategic issue to the executive committee. | Work with the program sponsor to re-prioritize the program backlog sequence. | Perform root-cause analysis on the key factors causing the manager's resistance. | A | Stakeholder resistance was anticipated, and multiple risk responses are likely to exist, so reviewing the risk register is the correct response. Agile planning would enable frequent retrospectives to refine the risk responses, which could be more flexible than a fully predictive response.
786 | Cost | A project team collected sensitive client data during the early stages of a project to help develop the project management plan. The team is now working on deliverables for the project when the compliance manager discovers a data breach and alerts the team to a compliance issue. Which document should the project manager review first? | Issue log | Statement of work (SOW) | Business case | Risk register | A | After a new compliance issue is raised, the issue log should be reviewed and updated, as needed, before taking action.
787 | Risk | The team working on Project A has resolved a technical issue, and the project is moving forward. The project manager has been warned that the same issue will probably arise on similar projects in the future. What should the project manager do first when responding to this warning? | Create a risk report and keep the report current. | Ensure that the issue log is updated and update the lessons learned register. | Notify the project sponsor about the warning. | Ensure that the lessons learned register is updated. | B | Update the issue log to reflect the resolution of the issue. Then, update the lessons learned register about potential risks for future projects.
788 | Schedule | While reviewing the issue log, the project manager noticed that tasks assigned to two (2) team members were quite behind schedule. What should the project manager do? | Notify the responsible team members of the need to complete the overdue tasks quickly to avoid introducing extra project risks. | Document the issue, escalate to the project sponsor, and ask how they would like it resolved. | Tell the team members behind schedule that they should explain why tasks were delayed and how they will get back on schedule. | Work with the relevant team members to review the delayed tasks and decide on strategies for resolution. | D | The project manager needs to be proactive, review the activities with the team members, and identify resolution strategies.
789 | Resource | Project team members are busier than usual. They indicate that they do NOT have the time to update the lessons learned repository because of other project responsibilities. How should the project manager respond? | File a change request to the project management office (PMO) to change how often lessons learned are collected. | Ensure there is an agenda item for discussion of lessons learned from project activities as part of all project meetings. | Bring in a consultant to collect lessons learned to help reduce the burden on the project team. | Require submission of lessons learned documentation after the customer accepts each project deliverable. | B | The lessons learned repository must be present throughout the project, using different facilitating techniques.
790 | Scope | A large project includes functional groups in four (4) countries, a steering committee, and a project sponsor. As the project approaches completion, the project manager must prepare the closeout documents. How should the project manager obtain appropriate sign-off on accepting project deliverables? | All of the parties involved should be asked to sign off. | The four managers from the four countries should be asked to sign off. | The steering committee should be asked to sign off. | The project sponsor should be asked to sign off. | D | Since the sponsor provided the resources for the project, it is their responsibility to sign off on the project deliverables officially.
791 | Schedule | After six (6) iterations, significant variations have occurred to the project scope and schedule. These are due to the customer's technology regulations and security policies, which are regularly reviewed. The project manager suggests a new approach to the next iteration to avoid possible delays. What should the project manager do first? | Research new technology trends and management tools that have been successful on similar projects. | Rank the importance of each improvement item, then implement actions identified during the last retrospective. | Use a backlog refinement meeting and include the customer's change requests in the discussion. | Engage in a cost-benefit analysis that can help predict the profits that could be realized using new technology for the next phase. | B | The retrospective reviews lessons learned and suggest corrective actions for the next iterations.
792 | Risk | A new wildlife reserve project will have a staff of approximately 80 experts, builders, and logistics workers exposed to various safety risks. The project manager wants a scalable approach combining flexibility and team dynamics with traditional safeguards. Which option could be used to tailor a hybrid project of this nature? | Behavior-Driven Development | Crystal Methods | eXtreme Programming (XP) | Monte Carlo Simulation | B | Other than XP, which is NOT scalable, Crystal Methods is the only option defined as a hybrid tailoring methodology.
793 | Risk | A medium-sized company is expanding into a new market. However, the company does NOT have previous experience in that market. A project manager needs to collect requirements. Which two tools or techniques should the project manager use? | Create requirements traceability matrix | Prototypes | Product analysis | Expert judgment | B | Experts are a source of experience and knowledge. Given the increased risks of a new and potentially complex market, using expert judgment is recommended. Prototypes are an excellent way to gain a better understanding of the product and to gather requirements.
794 | Cost | In a hybrid product design project, the team encounters a 3D printer malfunction resulting in costly losses of titanium supplies. When the production team tells the agile programming team about the problem, it becomes clear that mistranslated data sheets create problems for both teams. However, the Agile team resolved their problems a month before the malfunction. What could the Agile team have done to prevent the current malfunction? | Deprioritized the stories impacted by information in the data sheets | Summarized their retrospective conclusions on information radiators | Asked the project sponsor to halt the project pending translation corrections | Formally requested a change of equipment supplier for the project Correct Answers & Explanations | B | The root problem is that impactful information in the agile team was NOT passed to the predictive team in time to prevent the malfunction. Broadcasting retrospective lessons learned is the best way to reach the broadest group promptly. PMP PRACTICE TEST 5
795 | Scope | A project manager recently joined a new project with the following characteristics: Tight deadlines Global virtual team Fixed budget. During the planning stage, the project manager wants to avoid scope creep and keep the team focused on delivering a product that meets requirements. The project manager should ensure __________. (Fill in the blank with the correct response.) | that stakeholders do NOT directly interact with the development team leads | that the development team leads generate detailed requirements | that any changes to scope go through the formal approval process | that daily standups occur, with all development teams | C | Following the formal change control process is the best way to control unnecessary project changes.
796 | Risk | A project sponsor requests that an element of a product be swapped for the equivalent supplied by a local manufacturer to have a more sustainable supply chain. Which action should the project manager take? | Halt current production and initiate the Perform Integrated Change Control process. | Refer to the Perform Integrated Change Control process to examine the issue further. | Refuse to fulfill the request because it will lead to scope creep. | Promptly implement the change and submit a change request for formal documentation. | B | Submitting a change request starts the Perform Integrated Change Control process. Once the change request is submitted, the project manager and team analyze the impact of the change on the project. They can verify whether an element in the product leads to customers' health issues. Whatever it is, the issue or concern should be investigated before action.
797 | Risk | The lengthy analysis needed to assess the impact of new European Union (EU) regulations will likely delay a worldwide product launch. Perishable ingredients and factory bookings are at risk of being lost. The executive committee decided to postpone the launch in the EU but maintain launch dates in all non-EU countries. How should the project manager re-plan the project to support both launches? | Replan the project as a fully agile set of iterations and ensure that fixed milestones are documented on the burn-down chart. | Use the contingency budget to cover sunken costs for the EU launch and adjust plans for the non-EU launch. | Embed a set of iterations to analyze and develop the EU product, while adjusting plans for the non-EU launch. | Plan analysis activities and tollgates for the EU launch and crash the schedule for the non-EU launch. | C | Two (2) launch workstreams will need to run in parallel to avoid delay to the non-EU launch. The lack of known requirements makes it impossible to plan the EU launch with a predictive approach. Existing milestones must be maintained to avoid loss.
798 | Resource | A multi-year, hybrid pharmaceutical project adds new fixed-date activities for the team to run Machine Learning (ML) processing of medical scans. An agile team of doctors uses the output from the ML analysis to determine the next steps in a patient case. The project manager has updated the scope statement and schedule. In which three other documents should the project manager record this new process? Choose three: | Risk Register E) Resource Management Plan | Definition of Ready | Sprint Backlog | Stakeholder Register | B | The Definition of Ready is updated to ensure the ML output triggers the agile team's analysis. The risk register is updated to plan for risks relating to adapting and learning new technology and working methods. The resource management plan is updated because the machines running the ML routines are resources necessary to complete the work.
799 | Schedule | A project's workload is increasing significantly, and the resource level is NOT sufficient. Management outsources some major tasks to keep the project on schedule. What should the project manager do in this scenario? | Review the communications management plan. | Revise the organizational chart. | Escalate to the project sponsor. | Revise the procurement management plan. | D | The procurement management plan needs to be updated since it captures the process of documenting project procurement decisions, specifying the approach, and identifying potential sellers. The key benefit of this process is determining whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire it.
800 | Scope | A textile development project needs a specialized resource to work for 900 hours. The company has decided to outsource these hours. Because of internal policies, all potential service providers must be given the same information about the requirements. Which action should the project manager take to ensure this? | Conduct a bidder conference with the service providers. | Hold direct negotiations with each service provider. | Ensure the procurement management plan is sent to each service provider. | Add each of the service providers to the stakeholder register. | A | A bidder conference is a meeting between the buyer and prospective service providers before proposal submittal. Conferences ensure that all prospective bidders have a clear and common understanding of the procurement, and NO bidders receive preferential treatment.
801 | Procurement | Because a deliverable does NOT meet the agreed-upon quality specifications, it is rejected by the customer. Team members find that the deliverable fails to meet expectations because of a problem with vendor- provided parts. The vendor says that they will NOT correct the problem. Before deciding on the next steps, what should the project manager do? | Check the service level agreement (SLA) established with the vendor. | Review the procurement management plan and contract agreements. | Check the internal quality assurance reports. | Review the resource management plan and document lessons learned. | B | A contract is a mutually binding agreement that obligates the seller to provide specific products, services, or results, obligates the buyer to compensate the seller, and represents a legal relationship subject to remedy in the courts.
802 | Resource | Several team members are transferred to another project near the end of a manufacturing project. To complete the work, the project manager needs to acquire additional resource support from a new supplier but is concerned about the cost risk of using a new supplier at this advanced project stage. Now, the project manager needs to work with the procurement team to establish specifications and type of contract to be used. What should be done? | Recommend a fixed price incentive fee (FPIF) contract. | Recommend a cost-plus incentive fee (CPIF) contract. | Recommend a firm fixed price (FFP) contract. | Recommend a time and material (TM) contract. | A | A fixed price incentive fee contract (FPIF) is a type of contract where the buyer pays the seller a set amount (as de f i ned by the contract), and the seller can earn an additional amount if the seller meets de f i ned performance criteria.
803 | Resource | The agile team surpassed the planned number of stories in the last three agile iterations. How can the project manager be sure all the work performed is truly complete? | Check results against the Definition of Done. | Ask the team to cross-check other members' work. | Ask the product owner if the results are satisfactory. | Check the results of all the tests performed. | A | The Definition of Done lists all criteria that must be met to consider a task/story completed.
804 | Resource | A hybrid project combines IT integration and software development tasks. The predictive and agile teams work in silos, resulting in misaligned deliverable scheduling. Which two measures would enable the teams to synchronize their deliveries better? Choose two: | Alter the story size to ensure complete integration to the IT build requirements. | Break down IT work packages into more granular tasks to align with the software releases. E) Define common milestones and an overall dependency network to be used by both teams. | Use the IT predictive schedule to limit the features the software team starts to develop. | Create a common Kanban board to queue and track the progress of both teams' deliverables. | D | Common visibility of work in progress would enable better-aligned work planning. Common milestones and dependency integration across the two tracks will promote synchronized delivery. The other approaches are wrong because story size should always be as small as possible; agile progress should NOT be reduced to match the predictive schedule; otherwise, the project would have to be fully predictive
805 | General | Company G aims to increase customer satisfaction within four (4) months and initiates a project to meet this goal. The project manager needs to identify best practices. Which method should the project manager use to accomplish this? | Benchmarking | Facilitation | Emotional intelligence | Affinity diagram | A | Benchmarking should be used to identify best practices.
806 | Integration | A project manager begins to prepare the project management plan after receiving the project charter. There is NO historical information in the project management office (PMO). What next step should the project manager take in this scenario? | Utilize analogous estimating. | Seek advice from experts in the field. | Organize an initial kick-off call. | Request that the project sponsor provide input. | B | If NO historical information is available, consulting with subject matter experts is the next best thing a project manager can do to prepare the project plan.
807 | Scope | Company ABC's IT transformation project has three (3) deliverables, and they have the following characteristics, according to the project team: Deliverable 2 has strictly scheduled milestones, with no expected variation in the timeline. Requirements for deliverables 1 and 3 will change quickly during development. Which project life cycle should the project manager use for this project? | Select a fully agile project model with a common user story and three- week sprints. | Select a hybrid project model; position deliverable 2 as a single agile sprint embedded in an overall waterfall project. | Select a waterfall project model for deliverables, with firm milestones and change control procedures. | Select a hybrid project model; position deliverable 2 as a single waterfall phase embedded in an overall agile project. | D | In this project, two (2) deliverables (1 and 3) have unknown durations or changing requirement sets—both of which are appropriate conditions for using the agile life cycle. Deliverable 2 requires strict schedule control and external dependencies, which require a traditional or waterfall project life cycle.
808 | Scope | What is the main purpose of the project scope statement? | To document the project boundaries | To define project objectives | To outline project constraints | To list project deliverables | A | The main purpose of the project scope statement is to document the project boundaries, including what is and is not included in the project scope.
809 | Process | Which project management process group is responsible for formally authorizing a new project? | Planning | Initiating | Executing | Monitoring and Controlling | B | The Initiating process group is responsible for formally authorizing a new project by developing the project charter.
810 | Process | What is the purpose of a project management plan? | To define project scope | To authorize the project | To integrate and consolidate all subsidiary plans | To identify project stakeholders | C | The purpose of a project management plan is to integrate and consolidate all subsidiary plans and baselines from the planning processes.
811 | Cost | Which of the following is NOT a type of project cost estimate? | Parametric Estimate | Definitive Estimate | Actual Cost Estimate | Rough Order of Magnitude (ROM) | C | Actual Cost Estimate is not a type of project cost estimate. The three main types are Rough Order of Magnitude (ROM), Budgetary Estimate, and Definitive Estimate.
812 | Communications | What is the main purpose of a project kickoff meeting? | To introduce team members | To align stakeholders and set expectations | To review project objectives | To discuss project risks | B | The main purpose of a project kickoff meeting is to align stakeholders and set expectations for the project.
813 | Communications | What is the primary purpose of a project status report? | To identify project risks | To document project lessons learned | To request project changes | To communicate project progress | D | The primary purpose of a project status report is to communicate project progress to stakeholders.
814 | Integration | What is the main purpose of a project lessons learned document? | To assign blame for project issues | To identify project successes | To improve future project performance | To document project failures | C | The main purpose of a project lessons learned document is to improve future project performance by capturing and sharing knowledge gained during the project.
815 | Scope | Which of the following is NOT a type of project schedule? | Gantt chart | Critical path method | Work breakdown structure | Network diagram | C | The Work Breakdown Structure (WBS) is not a type of project schedule. It is a deliverable-oriented decomposition of the project scope.
816 | Integration | What is the primary purpose of a project change control board? | To implement project changes | To document project changes | To identify project changes | To approve project changes | D | The primary purpose of a project change control board is to review, evaluate, and approve or reject proposed changes to the project.
817 | Quality | Which of the following is NOT a type of project quality control tool? | Control chart | Pareto diagram | Fishbone diagram | Scatter diagram | C | The Fishbone diagram (also known as Ishikawa or cause-and- effect diagram) is not a quality control tool. It is a quality management tool used for root cause analysis.
818 | Communications | What is the primary purpose of a project communication management plan? | To define communication requirements | To identify communication channels | To document communication strategies | To establish communication protocols | C | The primary purpose of a project communication management plan is to document the approach and strategies for effective project communications.
819 | Resource | What is the main purpose of a project resource histogram? | To identify resource conflicts | To allocate project resources | To visualize resource utilization | To estimate resource costs | C | The main purpose of a project resource histogram is to visualize resource utilization over time, showing peaks and valleys in resource demand.
820 | Risk | Which of the following is NOT a type of project cost management tool? | Budget forecasting | Risk assessment | Earned value management | Cost variance analysis | B | Risk assessment is not a specific cost management tool. It is part of the risk management process.
821 | Resource | What is the primary purpose of a project team charter? | To identify team objectives | To establish team ground rules | To define team roles and responsibilities | To document team performance criteria | B | The primary purpose of a project team charter is to establish team ground rules, including communication protocols and decision- making processes.
822 | Risk | What is the main purpose of a project risk breakdown structure? | To categorize project risks | To quantify project risks | To prioritize project risks | To respond to project risks | A | The main purpose of a project risk breakdown structure is to categorize and organize identified project risks into logical groups.
823 | Scope | Which of the following is NOT a type of project quality assurance technique? | Quality inspection | Process analysis | Quality audit | Peer review | A | Quality inspection is not a quality assurance technique. It is a quality control technique used to verify deliverables meet specified requirements.
824 | General | What is the primary purpose of a project management information system (PMIS)? | To store project documents | To track project progress | To facilitate project communication | To support project decision-making | D | The primary purpose of a project management information system (PMIS) is to support project decision-making by providing timely and accurate information.
825 | Resource | A project manager is working on multiple projects. One project has new team members and is in early stages. The other projects are in various states of execution for the next few weeks. How can the project manager develop the new project team over the next few weeks? | Suggest that the team engage in multiple team-building events to normalize the team | Help team members create a set of agreed rules for working, or social contract, that encourages team cohesion | Engage in face-to-face personal conversations with each team member to build relationships | Keep the team informed by sending short daily project status updates | B | Creating a social contract—or a set of agreed rules for working—will allow the team to normalize and be self-servicing when you are unavailable. The other choices do NOT encourage the team members to develop independently and as a team.
826 | Communications | A project manager needs stakeholder involvement in order to identify strategic and operational assumptions and constraints. Unfortunately, the project manager is having difficulty obtaining consistent input due to lack of participation. In which two ways can the project manager encourage the stakeholder to participate and collaborate? | Timebox meetings | Be a servant leader | Use effective facilitation techniques | Use political awareness techniques | D | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures effective participation, so that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements ach
827 | Cost | A project team is small, and the team members have known each other for a long time. The team's project is in the execution stage. Recently, a team member told the new project manager that another team member has been complaining about how the project is being managed. How should this new project manager respond? | Hold a team morale-building event to improve team culture | Speak to the team members individually and ask them how they would like to deal with the situation | Schedule a team meeting to discuss the current team charter and ground rules, especially around communication and teamwork expectations | Review the current stakeholder engagement plan to identify how to resolve this difficulty | C | A team meeting is the best solution because it encourages every team member to participate and results in a clear set of guidelines for the team.
828 | Resource | A new project team is setting early priorities, and they plan to gain the customer's trust by delivering value as quickly as possible. Team member C mentions that they have worked with the project sponsor on other projects. How should the project manager connect these two facts and create an advantage for the project team? | Ask team member C to tell the whole team everything they know about the sponsor so that the team can work better | Discuss whether team member C has a conflict of interest in order to maintain an ethical standard | Explore how team member C can use personal influence with the sponsor to increase the project's potential for benefits realization | Make team member C the project leader since they already know the sponsor | C | Personal influence is a leadership skill that enables project teams and individuals to use existing relationships, building on them to further project activities and goals. In this case, team member C has an existing relationship that may help the project team to understand more quickly the needs of the project sponsor.
829 | Resource | A project's daily standup meetings are long, often lasting more than two hours. The project team uses the standup meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily standup meetings? | Coach team members towards shortening standup meetings to 10-15 minutes and improve their method for identifying solutions | Allow the meetings to remain long but ensure that the time is productive by using an agenda and recording minutes | Timebox each speaker using a stopwatch in standup meetings | Nominate a team member to manage obstacles and schedule meetings to discuss possible solutions | A | Daily standups are important meetings for agile teams. The project manager should coach the team in how a daily standup meeting is run and what is discussed. Teams run their own standups, and when run well, they can be very useful. Daily standups are typically 10-15 mins and three questions are answered: 1) What did you do since the last standup? 2) What will you do today? 3) Are there any impedim
830 | Resource | Leaders of high-performing project teams __________ team members' skills and knowledge and keep team members __________ throughout the project. (Fill in the blanks with the correct set of responses.) | leverage, rewarded | identify, aware | nurture, motivated | reward, scheduled | C | The primary goal of a project manager in relation to supporting a high-performing project team is to ensure that the team has the right skills and knowledge to complete the work and to keep them motivated to do their best work. These actions potentially optimize project outcomes.
831 | Stakeholder | A project manager is having difficulty obtaining consistent input from stakeholders and needs their input to identify assumptions and constraints. How can the project manager improve stakeholder engagement? | Research effective meeting management techniques | Institute checklist policies | Use political awareness techniques | Make use of effective facilitation techniques | D | Facilitation is the ability to effectively guide a group event to a successful decision, solution, or conclusion. A facilitator ensures effective participation, that participants achieve a mutual understanding, that all contributions are considered, that conclusions or results have full buy-in according to the decision process established for the project, and that the actions and agreements achiev
832 | People | The agile team is composed of highly skilled product design engineers. Their reputation for quality and speed has earned them new duties in concept development for new products, but team output in this new role has fallen steeply compared to their design work. Which two measures are most effective to improve team productivity in this case? | Prolong the iterations to adjust to new tasks | Hire more T-shaped profiles into the team E) Boost motivation with a team building event | Seek creative thinkers to mentor the team | Plan a creativity spike in the next iteration | C | The key problem of the team is that specialists are outside of their comfort zone. Mentoring and diversifying the team so that it is more cross-functional is the most efficient measure. Relying on the team's existing skill set to perform a spike or boosting their motivation or prolonging iterations will NOT address the root problem of specialization.
833 | Resource | The agile team excels at solving technical problems, but when the product owner requests creative or business-related ideas, the team falls silent. Is this a problem? | Yes, specialist teams are prone to higher error rates | No, the team performs better without useless distractions | No, specialist teams are more effective than generalists | Yes, lack of diversity will limit the team's adaptability | D | T-shaped skills are desirable in agile team members. Having a broad set of skills enables people to work more independently and with greater ability to adapt to changing needs.
834 | Resource | A governmental anti-money laundering software project needs a solution to collaborate with a remote agile team of four (4) people in another country. Spontaneous verbal communication between the teams must be supported. All the remote team's workstations and Kanban boards must be visible at all times. Which virtual team collaboration solution is most appropriate? | On-demand video conferencing | Workstation screen mirroring | Information radiator monitors | Always-on fishbowl windows | D | This is a project where confidentiality and security are critical —thus, permanent monitoring of remote resources is necessary. Only the fishbowl window solution would have the required field of view on a permanent basis. Radiators only display content, on-demand video conferencing would NOT be a permanent video feed, and mirroring only displays one (1) computer screen, NOT the environment.
835 | Resource | A project manager experienced in predictive methods is taking on an agile project for the first time. To help in making a successful transition, the project manager makes a list of situations that may arise from inadequate action as a servant leader. Which three situations would be on this list? | Team members avoid direct communication with other departments | Team members raise impediments they are unable to eliminate | Team members avoid taking on challenging tasks | High performers in the team move to more senior positions E) Project stakeholders' express skepticism of agile methods | C | Servant leaders must promote professional development through challenges and help team members build bridges with external groups. They also educate stakeholders on the business value of agile methodology.
836 | Resource | An agile team needs to decide who should represent them in the Scrum of Scrums. Which criteria should a project manager use to select the best- suited team member? | How well the member applies their depth of expertise | How convincing the member is as a public speaker | How well the member knows the work in the other teams | How long they have been working with Agile methods | C | The most important factor to effectively collaborate between teams in a Scrum of Scrums is to understand the work across all teams. This knowledge promotes effective coordination to identify and resolve dependencies and impediments. The other qualities are mainly important within the team (expertise and influence).
837 | Cost | The company has hired a new Architectural Excellence board with a mission to promote new programming paradigms. The agile team continues to work on new and existing software products. How should the project manager deal with this new development? | Negotiate a quiet period with the board to prevent disruption to the team's work | Speak with the product owner to add this change to the backlog | Inform the agile team that resulting changes will be postponed as long as possible | Be patient and wait until the board gives the team explicit instructions, then decide | B | An action needs to be taken in this scenario, NOT a deferral of any kind. The product owner needs to be involved, and this change needs to be added to the backlog. Backlog refinement is controlled by the product owner but requires a team effort. The product owner also can change the Definition of Done or include the changes in the acceptance criteria.
838 | Scope | A project manager develops a project management plan and schedule based on an agreed-upon project lifecycle of 16 months. Later, due to changing business requirements, the project sponsor requests completion within nine (9) months. How should the project manager respond to this proposed change? | Work with key stakeholders and project team members to discuss the business requirements | Modify the original project schedule to meet the revised deadline | Perform an impact evaluation of this change request and evaluate the change in scope | Meet individually with project team members to discuss which aspects of the project can be removed from the scope | C | To execute the project more quickly, the project team should discuss with the stakeholders if there can be any reduction of scope and find out the way to complete activities at the individual level within a shorter time, if possible.
839 | Resource | A project manager needs to ensure that the team delivers business value within the required timelines. The project manager recently learned that key stakeholders are worried that the current release plan will NOT meet urgent business needs. How can the project manager effectively respond to stakeholder concerns? | Consult with the stakeholders and team members to identify the minimum viable product (MVP) needed for launch | Monitor progress using a burndown chart after modifying the schedule baseline to meet stakeholder requirements | Renegotiate scope with the project sponsor after examining the work breakdown structure (WBS) | Determine the schedule performance index (SPI), then escalate the schedule risk to the project sponsor | A | Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need.
840 | Risk | A customer indicates that they would like to add a functionality to a product in development. Although this request is made during the execution stage of the project, the project manager determines that the cost for the addition would be small. The additional functionality, if successful, would increase the opportunity for profit. What should the project manager do next? | Identify an already-developed feature that could be combined with the new functionality and use the combination to meet the customer's request | Move forward, using the project's management reserve to add the requested functionality | Submit a change request and then evaluate the impact to the project | Acknowledge that the functionality would offer a great opportunity but determine that the proposed addition is out of scope | C | If the customer asks the project manager to make a change, regardless of how small or little impact, the change needs to go through Perform Integrated Change Control. The first step would be to submit a change request and then analyze the impact.
841 | Resource | During one daily standup meeting, team members suggest that rework is being caused because there seems to be too much work. How should the project manager respond to this? | Request that team members explicitly implement time boxing or spikes | Replace the under-performing team members | Try using a Kanban board for reviews | Investigate to determine whether this is a time or quality issue | D | Rework can often be caused by trying to do too much in too little time—or it can be an issue of the quality of work. If time is the issue, then time boxing or spikes are great techniques to focus work efforts. If quality is the issue, then you need to assess resources, materials, skill level, and so on. But you need to understand what is causing the rework first.
842 | Risk | A project manager for a construction firm meets with stakeholders. All stakeholders agree on a 20-month lifecycle for a project. After work has begun, the project manager learns that stakeholders would like project completion within no more than 16 months. Which step should the project manager NOT take? | Reduce the scope and crash the schedule | Add team members to work more quickly | Advise against modifying the timeline | Negotiate with stakeholders to reduce project requirements | A | If it is possible to reduce the requirements for a project with the sponsor and key stakeholders, this is preferred over crashing, fast- tracking, change-control, and other methods which will most likely increase risk and create issues with a shortened timeframe.
843 | Cost | A travel company wants to create smartphone applications for their users. Competitors are racing to do the same. The product owner's vision describes several versions of the app: Basic, Basic Ad-free, Pro, and Premium. Which project approach is best suited to the company's needs? | Predictive | Iterative | Incremental | Waterfall | C | The product bundling goes from least number of features (Basic) to the highest (Premium). An incremental approach allows to release the Basic product quickly to mitigate competitive time pressure, and gradually release each bundle by adding the next set of features.
844 | Cost | An efficient agile team in a large corporation generated ideas and added innovative features to the backlog. After the additional features are tested and complete, the portfolio owner rejects all of them. What is the most likely reason this situation happened? | The product owner did NOT sufficiently align the ideas with the portfolio product owner | The team did NOT make use of the normal quality control processes | The portfolio owner refuses to pay for the team's unplanned work | The team would be entitled to intellectual property rights on the features | A | The product owner is responsible for ensuring that the product meets business objectives, which could be set by a portfolio product owner.
845 | Risk | A project manager for a major annual international sporting event is reviewing data collected after the second of six planned project phases and sees that the team is performing poorly. The project uses a hybrid management model, with a project manager and decentralized decision- making at the team level. The project manager learns that several critical elements are behind schedule, and some delivered services are not operating correctly, resulting in rework and more delays. Also, team members might be enjoying working with the sports teams and being in the media spotlight a bit too much. What should the project manager do? | Log the performance issues in the issue log and assign team members to identify and execute solutions | Coach team members about prioritizing work over having fun | Continue to allow the team to make decisions and self-organize around work | Review performance data and reinforce project goals with the team at the soonest opportunity | D | Some real warning signs are present in this scenario—delays, rework, poor quality, and the team's distracted work ethic. Though it is early in the project time line, these problems could worsen or compound. Coaching or doing nothing are risky decisions. It is time to intervene in a way that still enables the team to make decisions. Option B, in which the project manager meets with the team to revi
846 | Resource | A project manager with limited experience managing globally distributed team members is appointed to a project with team members who are all from another country and speak a different native language. To successfully manage this project, the project manager needs to have cultural sensitivity. What of the following actions should the project manager NOT take? | Request a different assignment, citing the language barrier as an obstacle | Enroll in language and culture lessons to learn about this country | Hire a professional coach to learn how to be a more successful leader | Read books about cultural sensitivity in leadership | A | Great leaders have a growth mindset. Always aim to capitalize on cultural differences, focus on developing and sustaining the project team throughout the project life cycle, and promote working together interdependently in a climate of mutual trust. In this case, you can NOT assume that there is a language barrier, as the team members may be bilingual. This answer also does NOT demonstrate a growt
847 | Risk | Several unforeseen impediments suddenly appear on the Kanban board in a hybrid project. Each team member has reported one or more different problems relating to a regulatory specification issued by the predictive track. Which parameter is likely to be highest in the risk assessment? | Connectivity | Manageability | Dormancy | Controllability | A | The risks are all related to a common source—the specification—so connectivity ranks high per the definition "Where a risk is connected to many other risks, connectivity is high". Manageability and controllability are INCORRECT because the risk factor depends on an external regulator. Dormancy is low because the risks were detected immediately after the specification was issued.
848 | People | Several items remain in the Kanban blocked column despite the team's efforts to resolve the issues. The retrospective reveals that all of the impediments relate to mandatory corporate business processes, which introduce wait times. What should the project manager do next? | Dedicate the next iteration to team training on the business processes to help them work more autonomously | Work with the team to increase the story point estimates in the backlog to account for the business process delays | Act as a servant leader to resolve the pending business process issues while the team attends a team-building event | Work with process owners to streamline procedure and secure the team coaching on the processes | D | The servant leader should work within the organization to simplify processes affecting the team as much as possible. However, large companies typically need internal processes, so these can rarely be eliminated altogether.
849 | Schedule | A longstanding, key team member in a virtual team has been unmotivated for weeks after the death of a family member. Because of this, several project activities are behind schedule, impacting the project's critical path. How should the project manager handle this situation? | Ask the functional manager for additional support on the project, including assignment of a new resource | Discuss the situation with the team member and work with them to identify a workable solution | Replace the team member | Escalate this situation as an HR issue and ask other team members to work overtime | B | A project manager is a servant leader. Servant leadership means listening and acting with empathy. Especially in virtual teams, facilitating servant leadership can be a challenge. Replacing the key team member is a unilateral action that project team members and others may perceive as drastic, considering the circumstances. Asking others, such as HR or the functional manager, to intervene is a goo
850 | Resource | A project manager in a virtual team realizes, during the third iteration of product development, that the team dashboard that shows progress on work is faulty and is NOT showing updates. Which action should the project manager take? | Rank the need to fix the dashboard according to the business value for upcoming iterations | Document the issue as a new project risk and propose a solution | Keep the team working and send daily email updates to the team | Get the dashboard fixed | D | In an agile virtual team, the project manager needs to keep work visible so that the team can see progress. This is essential. Changing the way the team works together in the middle of a project can be very disruptive. In this case, they are lucky that a problem did NOT arise. The project manager needs to protect the team against impediments and allow them to focus on their work.
851 | Risk | Project D is working virtually because of a recent natural disaster. Several activities are delayed because a project team member has NOT been working for the past week. This impacts the critical path. How should the project manager respond to this problem? | Discuss the situation with the team member's functional manager and enable them to manage the team member | Remind the team member about responsibility and accountability | Ask a team member who knows this person well to try and find the missing team member and report back | Obtain a new resource to complete the needed tasks until you can speak to the team member directly | D | The team member has been away from work after a natural disaster. In addition to that, the team is working virtually, so communication is already different than when everyone was co-located in the office. Empathy is required here. Take action without being intrusive or asking others to intervene. There could be many reasons for the absence, and while the team member is your responsibility, complet
852 | Schedule | During an iteration, a project team working in country B encounters problems that may cause a delay in completion of task B. Teams in country A need task B to be completed on time in order to meet their schedules. These teams work together virtually. What can the project manager do to resolve this problem? | Increase the iteration length, and add additional resources to the project team, so that they can meet the appropriate deadlines | Ask the team in country B to work harder to complete on time, in order to avoid delaying the work of other teams | Ask the teams to collaborate virtually to find a solution to avert the potential delay | Ask team members to perform to the best of their abilities during the iteration and engage in a retrospective after completion of the iteration | C | "May cause a delay" does NOT mean the task completion will be delayed. To improve the probability of success, the team should collaborate and find a solution. They know their work best, and despite working virtually, they should be able to find a solution.
853 | Cost | A new project manager needs to deliver a high-stakes agile project. The vendor working with the team is in another country. Though this vendor has delivered excellent quality work on time in the past, they are currently behind schedule. The team explains to the project manager that their attempts to get the vendor back on schedule have failed. They have sent emails and phoned, but the vendor only gives vague, noncommittal responses. The product owner insists that this vendor is essential to the success of the project and an important partner of the business. Which action should the project manager take? | Contact the vendor and be direct about the consequences of their actions and delays | Ask the product owner to use personal influence to get the vendor back on schedule | Work with procurement to amend the vendor's service agreement, with specific terms and conditions for work | Create a virtual workspace for the team so that everyone is aware of and accountable for their tasks and aware of due dates. Include the product owner | D | Communication in virtual teams can be challenging. Being direct may NOT leave a good first impression and revising a service agreement may be perceived as hostile by the vendor. This vendor is critical to the success of the project and important to the business, and the team may be getting demoralized by their unsuccessful attempts to manage the vendor. Be attentive of these factors using active l
854 | General | During project execution, a customer asks to replace a piece of planned hardware with more features and a lower price. What should the project manager do? | Purchase the hardware as it will reduce the project cost | Confirm with the project team that the new features are available in the hardware | Seek approval from the procurement manager | Evaluate the new features to ensure they align with the customer's business needs | D | Before accepting a change to replace hardware, the project manager should first evaluate if the new features align with the customer's business needs. This ensures the change will provide value and meet project objectives.
855 | Resource | A project manager is leading a project to implement a process improvement software system that was developed in-house. The system was piloted with the finance team before its full rollout. Because of a misalignment with core processes, adoption across the organization was less than 50%. Which three actions should the project manager have performed to realize the project benefits? | Conducted a full needs assessment in the design phase | Developed a detailed change management plan that also included training | Involved the marketing and sales teams in collecting feedback from customers | Ensured wider stakeholder engagement to gain greater buy-in | D | To improve adoption of the new system, the project manager should have ensured wider stakeholder engagement, conducted a thorough needs assessment, and developed a change management plan with training. These actions would have helped align the system with user needs and prepared users for the change.
856 | People | A project that aims to deliver real-time capabilities for customers to track their shipment status is in progress. The project manager continues to find that team members argue over several user stories. What should the project manager do to resolve this situation? | Validate the business values and capabilities mapped to the user stories to ensure alignment | Ask the product manager to clarify the requirements of the user stories | Review the project charter regularly with the team members | Send a request to the business sponsor to clarify the user stories | A | When team members are arguing over user stories, the project manager should validate that the stories align with business values and capabilities. This helps ensure the team is focused on delivering value and resolves conflicts about priorities.
857 | Business Environment | While planning a global solution delivery in a multinational organization, the project manager and team drafted all work items and defined the priorities and methodologies for implementation. During one of the daily meetings, a team member expresses concern about the technology being used and proposes a new one that will be more aligned with the data privacy policies of the country. What should the project manager do first? | Ask the architecture owner to assess the team member's proposal and evaluate its readiness | Check with the customer and ask if they are comfortable using the newly proposed technology | Review the organizational process assets and share the latest policies with the team | Get support from the information technology (IT) department regarding the feasibility of using the new technology | C | When concerns about compliance arise, the project manager should first review organizational process assets and policies to ensure the team has the latest information. This allows the team to assess if the proposed technology aligns with organizational policies.
858 | Resource | A project manager has been assigned a project that involves a virtual, multicultural team, including representatives from various countries. The project manager needs to prepare a kick-off meeting. What should the project manager do to prepare for the meeting? | Consider various time zones, communication capabilities, and possible constraints | Set rules and regulations that must be followed during the project | Ask the sponsor for different resources to facilitate the project | Set up the project sponsor's language as the official project communication language | A | When preparing for a kick-off meeting with a virtual, multicultural team, the project manager should consider time zones, communication capabilities, and potential constraints. This ensures the meeting is accessible and effective for all team members.
859 | Risk | A project manager is assigned a complex project with legal, regulatory, and contractual requirements that are not finalized. The project manager is challenged by the lack of access to the sponsor, who is also the product owner. Concerns exist regarding a delay in completing the legal and regulatory requirements. What should the project manager do? | Delay the legal, regulatory, and contractual requirements, which were mandated before the product launch, until the end of the project, and before the go-live date | Focus on the project deliverables instead, as it is not the project manager's responsibility to fulfill these requirements | Contact the product owner and highlight the project risks related to the delay in fulfilling these requirements on time | Set up a meeting with the product owner and the company's legal department regarding the project status and review the progress of fulfilling these requirements | D | To address delays in legal and regulatory requirements, the project manager should set up a meeting with the product owner and legal department. This allows for a review of the requirements and progress, helping to address the delays and potential impacts on the project.
860 | Resource | In a global, virtual project, the project manager encounters a few issues with team meetings. Some stakeholders do not participate, others complain about the scheduling, and others do not accept the meeting invitation. What should the project manager do to address this concern? | Reschedule meetings to different times and dates according to time zones | Send a communication to the team's managers and ask for support | Review the organizational culture and structure to coordinate meetings properly | Inform the project sponsor of the situation and ask for support | C | When facing issues with global, virtual team meetings, the project manager should first review the organizational culture and structure. This helps in understanding the context and coordinating meetings in a way that aligns with the organization's norms and practices.
861 | Business Environment | A project manager is part of a project management focus group working on implementing project management change measures across the organization so that the benefits of projects can be more effective and successful. Which of the following describes the main process(es) for the focus group to consider in order for effective and successful change to take place within projects in the organization? | An effective Individual change process for team members | An effective organization change process of projects | An effective regulatory change process of the industry | Effective Organization change process of projects and Individual change process for team members | D | To implement effective project management change measures, the focus group should consider both organizational change processes for projects and individual change processes for team members. This comprehensive approach addresses changes at both the organizational and individual levels.
862 | Communications | The sales and marketing director at company A reports a 40% drop in revenue and significant increase in returns for Widget version 6.0. Customers are complaining directly to customer service and the social media teams report a high rate of negative feedback. The project team is already working on Widget version 6.1, which is a small set of upgrades and bug fixes. The director gets in touch with the team, requesting a full disclosure of the version 6.0 and 6.1 requirements. How should the project manager interact with this stakeholder? | Review the customer and market research—both qualitative and quantitative—that supported the business case for the 6.0 project. Begin by discussing the stakeholder's role in the research | Remind them that they were consulted about the agreed product requirements for versions 6.0 and 6.1; also remind the stakeholder and that the responsible and accountable stakeholders approved version 6.0 before release | Let them know that you also are disappointed, but this risk was documented and listed as a probable customer/market reaction for a major version release | Ask the team to perform the final demo for version 6.0 again for the director's information | A | When facing concerns about a product release, the project manager should review the customer and market research that supported the business case. This approach provides context for the decisions made and involves the stakeholder in understanding the rationale behind the project.
863 | Scope | A project has a quality management plan in place. This plan states that project deliverables must be reviewed for quality at least five (5) business days before the deadline. Four deliverables have failed the quality requirement. What should the project manager do? | Contact the project sponsor and request advice | Generate a cause-and-effect diagram for analysis | Rewrite relevant portions of the quality management plan | Inquire regarding the feasibility of an internal audit of the project | B | When multiple deliverables fail quality requirements, the project manager should generate a cause-and-effect diagram for analysis. This tool helps identify root causes of the quality issues and guides corrective actions.
864 | Risk | The project sponsor is NOT convinced that an agile track should be used in a new R&D project because the company needs to be certain that specific features will be ready for mass production by a specific date. Which three agile methods can ensure that the sponsor's needs can be fulfilled in a hybrid project approach? | Incremental development reduces risk of quality delays | Requirement priorities are confirmed at each iteration | A product roadmap can provide a detailed breakdown | Impact mapping can be used to group related stories | B | These agile methods can help ensure specific features are ready by a certain date: confirming requirement priorities at each iteration, using incremental development to reduce quality risks, and using impact mapping to group related stories. These approaches provide flexibility while maintaining focus on key deliverables.
865 | Quality | While monitoring progress of the agile team, the project manager notices that an expert member's output is much lower compared with that of junior team members. This is a surprise, as the expert works diligently on the most complex tasks and always produces defect-free results. Which is the most likely explanation for the developer's low output? | Younger team members are normally more productive | The expert works faster and reports fewer hours than the junior members | The expert runs more tests and therefore completes fewer stories | The story point estimates on the expert's work are consistently too low | D | The most likely explanation for the expert's seemingly low output is that the story point estimates for their complex tasks are consistently too low. This underestimation makes their productivity appear lower compared to junior members working on simpler tasks.
866 | Communications | The Project Management Office wants to offer constant reporting across the dozens of agile projects running concurrently. They want to use information radiators to share progress status and key lessons learned. How can this best be achieved? | Place monitors displaying combined feature burn-up charts and a digest of retrospectives | Set up an internal Wiki page which all agile teams update in real time and users consult on demand | Use fishbowl windows to show all project teams' Kanban boards and charts in real time | Place webcams to broadcast all Kanban boards and cycle the images sequentially on the radiator | A | To provide constant reporting across multiple agile projects, the best approach is to use monitors displaying combined feature burn-up charts and retrospective digests. This provides a visual, up-to-date overview of progress and lessons learned across projects.
867 | Cost | The last three agile iterations showed a trend of increasingly prolonged test work. Which activity should the project manager plan to address the root cause? | Practice a paired testing policy | Plan an iteration of testing only | Adopt test automation tools | Plan more backlog refinement | D | To address prolonged test work, the project manager should plan more backlog refinement. This helps break down complex stories into smaller, more manageable pieces, which can reduce testing time and complexity.
868 | Resource | A project team is working with an overseas contractor based in a country that has three official languages, and every contractor on the team is multilingual. Team meetings continue to be held in the commonly shared language, but during project work meetings, contractors speak to each other in a different language. When the project manager brings this up in the next team meeting, the contractors express regret, but they explain that they work better when they can communicate freely with each other. How should the project manager respond first? | Require everyone to speak the same language all of the time, even though this will slow the pace of work | Let the team discuss language requirements and make ground rules for team communication | Escalate this as an issue to the human resources department | Obtain formal training or translation services | B | The best approach is to let the team discuss and establish ground rules for communication. This promotes team autonomy, respects cultural differences, and allows the team to find a solution that balances efficiency with effective communication.
869 | Cost | After three agile iterations showed a trend of increasingly prolonged test work, the team performed an intensive backlog refinement. What metrics would show that the problem was effectively addressed? | Speed of impediment resolution | Increase in value per story | Decrease in backlog item count | Stories completed per iteration | D | After intensive backlog refinement, an increase in stories completed per iteration would indicate that the problem of prolonged test work has been effectively addressed. This metric shows that the team is able to complete more work in each iteration due to better-defined and smaller stories.
870 | Risk | Before the next iteration begins, project team B meets about an unexpected challenge which threatens to delay the current phase. The task in the next iteration CANNOT be completed because of this challenge. Another team within the project is depending on timely completion of Task 1 in order to fulfill their work. How should the project manager resolve this issue? | Let team members know you want them to do their best under difficult circumstances, and make sure to note the iteration's challenges in the next retrospective | Meet with the product owner to prioritize the iteration backlog, so that it does NOT impact other teams or obligations | Meet with both teams separately and ask them to figure out a way to meet the required deadlines and complete the project on time | Increase the number of team members for the project team and increase the iteration length, ensuring that the work will be completed according to schedule | B | When facing an unexpected challenge that threatens to delay work depended on by another team, the project manager should meet with the product owner to reprioritize the iteration backlog. This ensures that critical work impacting other teams is addressed first.
871 | Schedule | During a meeting, a project manager learns that a business result needs to be delivered in four (4) weeks, although the original schedule stated sixteen (16) weeks. The project manager also hears that there is NO available technical resource. The project manager knows the technical resource manager because they worked together on a previous project. What is the first thing the project manager should do? | Notify the project sponsor about the lack of a technical resource | Immediately escalate the issue to decision makers in the organization | Check with the technical resource manager to see if there is an available technical resource | Hire an outside party to meet the need for a technical resource | C | The first step should be to check with the technical resource manager about resource availability. This direct approach leverages existing relationships and is the quickest way to determine if the resource constraint can be addressed internally.
872 | Business Environment | A project manager has been working on an internal project for the organization's project management office (PMO). The project was initially sponsored by a PMO leader who has since been replaced. The new leader does not see much value in the project. What should the project manager do? | Set up a second kick-off meeting with the new PMO leader and the project team | Use the benefits the project manager has been tracking throughout the project to prove the project's value | Continue working on the project since it is already approved and in progress, and inform the new PMO leader | Use the previous data to obtain sponsorship from the new PMO leader because the project was effective | B | When a new leader questions a project's value, the project manager should use the tracked benefits to demonstrate the project's value. This provides concrete evidence of the project's worth and helps justify its continuation.
873 | Cost | In an agile project, the project status indicates that the project is 95% completed. During an iteration review, the stakeholders were concerned about the business value being delivered. What should the project manager do to ensure the project is properly aligned? | Communicate with the stakeholders to mitigate their concerns | Ask the project sponsor to review the project goals accordingly | Request the business analyst to adjust the project goals accordingly | Ask the product owner to review the backlog regarding business value | D | When stakeholders express concern about business value in an agile project, the project manager should ask the product owner to review the backlog regarding business value. The product owner is responsible for maximizing value and can ensure the backlog aligns with business needs.
874 | Cost | After the transition and completion of a large equipment installation project, the project manager requests the customer to add some operational cost to the project budget for team-building activities. The project was completed under budget, contingency reserves were not spent, and the team-building activities will ensure the operational team's optimal performance. What should the project manager do? | Perform the integrated change control process | Reject the request and close the project financials | Approve the expenditure to ensure customer satisfaction | Document the request in the lessons learned repository | B | The project manager should reject the request to add operational costs to the project budget after project completion. Project financials should be closed, and operational costs should be handled separately from the project budget.
875 | Resource | A project manager manages a project where a third-party provider implements a custom solution. The project manager needs to ensure that the local team will have the capability to support the solution. What should the project manager ensure? | The requirements for supporting the custom solution are recorded in the lessons learned register | The requirements for maintaining the custom solution are included in the issue log | The local team accepts and signs the transition plan before closing the project | The technical documents are complete and placed in a shared repository | C | To ensure the local team can support the custom solution, the project manager should ensure that the local team accepts and signs the transition plan before closing the project. This formal handover ensures proper knowledge transfer and readiness for ongoing support.
876 | Cost | A project manager for a building project has been informed that a required permit from the local government has not yet been obtained. Applying for the permit will delay project delivery by 21 days for US$40,000. The fine for not having the permit is US$1,900 a day. What should the project manager do? | As the cost of non-compliance is less than the cost of compliance, the project manager should delay the project and obtain the permit | As the cost of compliance is less than the cost of non-compliance, the project manager should deliver the project as planned | As the cost of non-compliance is less than the cost of compliance, the project manager should deliver the project as planned | As the cost of compliance is less than the cost of non-compliance, the project manager should delay the project and obtain the permit | C | In this case, the cost of non-compliance ($39,900 in fines) is less than the cost of compliance ($40,000 plus 21 days delay). Therefore, from a cost and schedule perspective, the project manager should deliver the project as planned and pay the fine.
877 | Resource | During a design workshop, the engineers asked the project manager about the safety and environmental prerequisites for the new robot's operating procedures. What should the project manager do? | Hire a specialized engineer to support the design team | Look into lessons learned documentation for similar projects | Run a benchmark with similar plants to capture their compliance constraints | Provide the team with the organizational process assets in the project charter | D | The project manager should provide the team with the organizational process assets in the project charter. These assets typically include internal policies and guidelines related to safety and environmental prerequisites.
878 | Risk | A project team recently experienced delays due to noncompliance which have made the project schedule less flexible and increased the risk to cost and poor quality. The team is brainstorming about ways to avoid this in the future. What is the most far-reaching implication for the organization if this noncompliance is not resolved? | Slower response to system | Unhappy clients or end users | Fines and penalties | Business survival and continuity | D | The most far-reaching implication of unresolved noncompliance issues is the threat to business survival and continuity. While other options like fines or unhappy clients are important, they are less severe than the potential long-term impact on the organization's ability to operate.
879 | Risk | At the midway point of a project, the project manager was informed of a market movement that would make the project results useless to the client. This information could cause the project to be canceled or at least a big change in the scope and desired outcome. What should the project manager do next? | Discuss transparently with the project sponsor, offering support on the strategy evaluation if needed | Halt the project immediately, as the project manager knows it will be useless to the client | Prepare all status reports and demos to keep the client focused on successful project execution | Continue working on the project execution, as the business strategy is not the project manager's responsibility | A | When faced with a significant market change that could impact the project's value, the project manager should openly discuss the situation with the project sponsor. This allows for a collaborative evaluation of the project's strategic alignment and potential adjustments.
880 | Resource | During project closure, the team considers the final sprint retrospective unnecessary because there are no remaining sprints. What could be a possible helpful outcome of holding this sprint retrospective? | Promotion opportunities for the team members | Improvement in velocity if the same team is formed in the future | Information that could be useful for future projects | Tips for adapting to working together if that happens in the near future | C | Even though the project is ending, conducting a final sprint retrospective can provide valuable information for future projects. This practice supports continuous improvement and organizational learning.
881 | Resource | A project manager is working on a large business transformation project. All of the build deliverables were signed off, and the project manager managed the transition to BAU (Business as Usual). Which of the following are important operational readiness considerations for the project manager? | A cheat sheet for core functionality is provided, and self-training is encouraged | Responsibility and accountability are formally handed over to operational teams | The project team remains responsible for operational support during BAU | Formal training and access to documentation should be provided to all users | D | To ensure operational readiness, it's crucial to provide formal training and documentation to users and formally hand over responsibility to operational teams. These actions support a smooth transition from project to business- as-usual operations.
882 | Risk | A project steering group has decided to change the vendor that will deliver a project component. Which of the following activities should be included in the handover? | The old vendor should provide training for the new one and assist with the transition | Both vendors should provide additional incentives for staff during the transition | The new vendor should shadow the old vendor to ensure knowledge transfer | The new vendor should take over activities as per the existing project plan | A | When changing vendors, it's important to ensure proper knowledge transfer. Having the old vendor provide training and the new vendor shadow them facilitates a smooth transition and reduces the risk of knowledge loss.
883 | Resource | A project manager is experiencing issues with the functional manager of a project team member. The functional manager has given the team member another assignment and has told the team member that the previous project should be a lower priority. What should the project manager do? | Request additional resources for your project | Communicate the importance of the project to the team | Refer the functional manager to the project charter | Escalate the issue to senior management | C | The project charter will provide insights into the business case and benefits of doing the project. Thus, the project manager should refer the functional manager to the project charter.
884 | Resource | A project manager notices that a critical team member has lost interest in the project. How should the project manager address this issue? | Increase the team member's salary | Escalate this issue to the human resources (HR) manager | Replace the team member with a more interested team member | Schedule a meeting with the team member to identify the cause | D | The project manager should first determine the real cause of the team member's lack of interest. Then, the project manager will be able to motivate them appropriately.
885 | General | What approach eases the burden on the IT department by empowering the business to mature new implementations and kick off the process of creating eventual solutions? | Use a predictive approach | Use an ideation practice | Use a hybrid approach on any new implementation | Use an agile approach by showcasing output incrementally | B | This approach eases the burden on the IT department by empowering the business to mature ideas and kick off the process of creating eventual solutions. It eliminates the effort and often-lengthy time frames associated with pitching an underdeveloped idea to IT.
886 | General | A project manager is managing an agile project. The PMO manager is not familiar with agile delivery. Which of the following statements describes the agile approach? | Customer collaboration over following a plan | Responding to change over following a plan | Customer collaboration over comprehensive testing | Responding to change over processes and tools | B | The main characteristic of Agile delivery is that it embraces change over strictly following a detailed plan.
887 | Procurement | A project manager has just taken over an ongoing project. The previous project manager resigned from the organization. During a review of the project documentation, the project manager realizes major deviations in the procurement process the previous project manager used to engage service providers currently working on the project. What should the project manager do next? | Contact the service providers with the facts and determine how to resolve the issue | Call the previous project manager to understand the rationale for the abnormal procurement process | Flag the abnormal procurement process as a critical issue for the attention of senior management | Report the service providers and the previous project manager to the organization's ethics committee | C | The project manager must first escalate any major issues internally to senior management or PMO for prompt investigations.
888 | Cost | A project manager recently joined a new organization. The project sponsor is a Subject Matter Expert and wants to manage the scope by delivering in small increments and changing the scope based on feedback. Which of the following approaches should be the recommended option? | Waterfall | Scrum | Predictive | Kanban | B | It is the perfect situation for delivery using Scrum. The Sponsor has the authority and knowledge to manage the Product Backlog and wants the flexibility to change the scope based on feedback on small increments delivered to users.
889 | Cost | A project runs over the allocated budget and still has many items in the backlog. After each sprint, the team has released updated deliverables, and users are already getting value from them. What should the project manager do in this situation? | Set the expectation that the committed work must be finished on time | Request additional budget based on an updated estimation of the remaining backlog items | Remove the deliverables from the backlog that were not part of the project charter | Measure user satisfaction and present the results to the steering committee | D | Measuring user satisfaction can be a proxy for understanding whether the team has achieved a minimally viable product. If they have and the budget is exhausted, it makes sense to end the project.
890 | Cost | A project manager has developed a schedule for a project involving various departments. The project manager met with each team member to develop a work breakdown structure (WBS). However, after the WBS was finalized, the project manager discovered some redundant tasks. What should the project manager have done to avoid this issue? | Organized group sessions for all team members to review the WBS together | Improved communication channels with all team members | Enlisted the help of subject matter experts (SMEs) to provide scheduling guidance | Prepared a task assignment matrix to represent the WBS | A | All the project planning activities should be discussed during the joint planning sessions. During these sessions, team members will share their approaches, and this will minimize activities' overlap and increase awareness among the team members.
891 | Scope | A project manager is involved in a project where requirements are constantly evolving. What should the project manager do to achieve success? | Provide regular updates and request deliverable-based approvals from the product owner | Work with the team to ensure they are on track and delivering on schedule | Maintain a comfortable working atmosphere to improve team cohesion | Ensure documentation and processes are filed appropriately and update the product owner | A | The project manager is dealing with a project with an evolving scope. Such projects require the manager to constantly engage with the product owner for feedback and sign off on project deliverables.
892 | Schedule | Project manager B has been assigned to take over a project from Project Manager A. Project Manager A informs Project Manager B that the project is on schedule only because Project Manager A constantly pushes the team to perform. What is the first action Project Manager B should take as the new project manager? | Determine a management strategy | Check the risk status | Tell the team the new objectives | Check the cost performance | A | As a new project manager taking over a project, the first step should be to determine an appropriate management strategy based on the current project situation and team dynamics.
893 | Cost | A digital transformation project has reached its end. A customer complained about missing requirements. What approach should the project manager take to address the customer's concern? | Take a sign-off on the current requirement and treat the scope gap as a new requirement | Use the Ideation approach to address the problem | Do not accept the new changes and close the current project | Accept the new changes and request an extension | B | The Ideation approach can help address the customer's concern by empowering the business to mature ideas and kick off the process of creating eventual solutions, eliminating the effort and often- lengthy time frames associated with pitching an underdeveloped idea to IT.
894 | Quality | An operation support project, though the support work is going smooth, a customer is always complaining that they do not have any visibility on the quality of support work. How should this customer's concern be addressed? | Plan for a recursive governance meeting with the customer to present the progress and publish the data in a shared folder for future review | Request the customer to appoint a manager from their area to review day-to-day activities and agreements reached during all discussions | Inform the customer that every day after the most important discussions have taken place, one team member will oversee updating him | Prepare relevant reports and send them to the customer daily and publish the reports in a shared folder for future review | A | This approach provides regular visibility to the customer on the quality of support work and allows for future reference, addressing the customer's concern about lack of visibility.
895 | Resource | An agile project team has not completed the tasks within the current iteration. During a meeting, the project sponsor gives the team a final date for task completion. How should the project manager proceed? | Advise the project sponsor that the team manages work within iterations | Appoint a team leader to take responsibility for the team's iteration planning | Request that a functional manager becomes a team lead to ensure processes are followed | Advise the team to comply with the new schedule provided by the project sponsor | A | In the agile approach, the team takes responsibility for its work and process. The project manager should inform the sponsor about this aspect of agile project management.
896 | General | As part of a temporary assignment, a project manager is leading a business project. During a daily status meeting, it is discovered that the project manager's former department has not completed a task. It is delaying the current iteration. What should the project manager do? | Invite the project team to a swarming session to define a solution | Leverage the network of the former department and ask for help | Create an entry in the impediment board and assign it | Escalate the issue to the product owner to define the next steps | B | Utilizing existing relationships and networks can be an effective way to address issues and get help, especially when dealing with a former department.
897 | General | A project manager in a manufacturing company was notified of a failure of the delivered machinery during the initial tests. The machine failed to comply with standard design specifications, resulting in malfunctions and safety concerns. What should the project manager do first to address the issue? | Assess the environmental and individual factors | Review the initial testing procedure and execution | Evaluate the technical documentation of the machine | Check the communications between the stakeholders | B | As a starting point, the project manager needs a thorough understanding of the task and the environment it is conducted in. Reviewing the initial testing procedure and execution will provide crucial information about what went wrong.
898 | Scope | A new project manager is assigned to a project in the execution phase. The project just completed the deliverables for the first phase. During a workshop to review the scope for the second phase of the project, a couple of stakeholders complained that they were not informed of the benefits already delivered. What should the project manager do to resolve this issue? | Escalate the issue to the sponsor because the question came from some senior stakeholders Correct Answers & Explanations | Escalate the issue to the steering committee because the sponsor should have informed stakeholders | Record the issue in the issue log, discuss it with the change manager, and update the communications management plan | Record the issue in the register, review the stakeholder matrix, and update the risk management plan | C | This approach addresses the root cause of the issue, which is poor stakeholder assessment and/or communication plan. The project manager should take responsibility for resolving communication issues and update the plan accordingly. PMP PRACTICE TEST 6
899 | Cost | A company has hired a project manager to implement an adaptive project framework. The project has made some progress, but the team is frustrated because the client does not provide feedback or participate in defining acceptance criteria. What could have caused this situation? | Development team has no experience in managing an adaptive project. | Development team has not produced a complete prototype. | Client plans to implement the project and does not need to participate. | Client does not understand the importance of their involvement. | D | In adaptive project frameworks, client involvement is crucial. The situation described suggests that the client does not understand the importance of their participation in providing feedback and defining acceptance criteria.
900 | Risk | A project manager was just given a new project to handle. She is working on the project documents and, after reading the Project Charter, is compiling the risks as she sees them. Once she completes the list, when should it be reviewed? | When starting the project and as each risk is closed. | While organizing, preparing, and carrying out the work. | During weekly meetings, as new risks are identified and added. | Regularly and throughout the project. | D | Risks should be reviewed regularly and throughout the project lifecycle, as new risks may emerge and existing risks may change in impact or probability over time.
901 | Risk | A project manager for a large government organization decides to save money by changing the local implementation partner and is considering using offshore resources instead. What are the main risks associated with using offshore resources? | Offshore resources may need detailed documentation due to time and cultural differences E) Offshore resources may not have the same business domain knowledge as the previous vendor | Offshore resources may need more effort in planning and managing project budgets | Offshore resources may need more supervision due to time and cultural differences | Offshore resources may need longer onboarding due to geopolitical differences | C | These are the main risks associated with using offshore resources, as they involve challenges related to time zones, cultural differences, budget management, and potential geopolitical complexities.
902 | Resource | Which one of the following is not a Resource-Based Power in relation to mega projects? | Recruiting on a contractual basis | Recruitment via Direct Control | Recruitment based on secondment | Recruiting expert talents | B | Recruitment via direct control is not typically considered a resource-based power in mega projects. The other options are valid resource-based powers in such projects.
903 | Cost | A team is working on a new product development project using a hybrid approach. After the fourth sprint, they learn that the exchange rate for imported goods will increase significantly. What should the project manager do in order to make sure the final product gets launched on time and as defined? | Review the backlog to see the impact of a budget increase. | Work with the stakeholders to develop incremental budgeting approaches. | Spend the extra money and plan to compensate for it in the next sprint. | Reduce the product's specifications to use less imported material. | B | In a hybrid approach, working with stakeholders to develop incremental budgeting approaches is the best solution to address unexpected cost increases while ensuring the project stays on track.
904 | Cost | A team is working on a new project and the sponsor is not approving the budget increase needed for the current iteration. What should the project manager do to address this concern? | Spend the extra money and plan to compensate in the next sprint. | Submit a change request to get formal approval for a budget increase. | Explain to the sponsor the risk of not having the budget approval. | Work with the stakeholders to develop flexible budgeting approaches. | D | When facing budget approval issues, working with stakeholders to develop flexible budgeting approaches is the best solution to address the concern while maintaining project progress.
905 | Schedule | A project manager identified that a task on the critical path is behind schedule. Higher management will not approve any more budget for more resources and tools for project use. Project manager has to use his/her approved resources. What will be the best suitable practice for the project manager? | What-if scenario analysis | Fast-tracking | Crashing | Resource leveling | B | Fast-tracking, which involves performing activities in parallel rather than sequentially, is the best practice when a task on the critical path is behind schedule and no additional resources are available.
906 | Stakeholder | A project manager is working on a complex project with a very high environmental impact. The organization's PMO approved the project, and is now in the planning phase. The project sponsor gave the project manager a list of all project stakeholders. What will be the next activity in the Stakeholder Management Plan? | Analyze | Engage | Monitor | Identify | A | After receiving the list of stakeholders, the next step in stakeholder management is to analyze these stakeholders to understand their influence, interest, and potential impact on the project.
907 | Risk | The change control board (CCB) approves a customer's requested design change. The project manager then discovers that the change will cause a three-month project delay. What should the project manager have done to avoid this? | Thoroughly assessed the request in accordance with the risk management plan | Redefined the project scope to include the new design | Fast-tracked and crashed the schedule | Increased the authorized budget and requested additional resources | A | To avoid unexpected delays after approving a change request, the project manager should have thoroughly assessed the request in accordance with the risk management plan, considering all potential impacts on the project schedule.
908 | Risk | A project manager is assigned to a very complex and technical project. The project manager is currently working on the resources plan and intends to recommend to the project sponsor that external resources should be used instead. What risks can be mitigated using one or more vendors to deliver project components? | Financial | Technical | Scope E) Schedule | Political | A | Using vendors can help mitigate technical, political, and financial risks in complex projects by leveraging external expertise and resources.
909 | Risk | What is the difference between Risks and Issues? | Risks are uncertain, whereas Issues are certain. | Risks and Issues are both uncertain. | Risks and Issues are both certain. | The risk may not happen when an issue has occurred. | A | Risks are potential future events with uncertainty, while issues are current problems that have already occurred. A risk may or may not happen, but an issue is a certainty that needs to be addressed.
910 | Risk | A project manager decided to involve a third party to manage project risk given that they had more experience than the current project team. What response strategy did the project manager apply to address overall project risk? | Reduce | Avoid | Exploit | Transfer | D | The project manager decided to involve a third party to manage project risk, which is an example of the "Transfer" risk response strategy. This strategy involves shifting the ownership and management of a risk to another party who is better equipped to handle it.
911 | Scope | A company has an existing contract to maintain and enhance a client's customer database. The company's legal department informs the project manager that a new piece of legislation requiring stricter protection of customer information might soon be signed into law. The law will require additional security features to be implemented into the database the project manager maintains. These features are not included in the scope of the current contract. What should the project manager do? | Ask the legal department to raise the issue in the next contract negotiation with the customer. | Update the risk register to include this issue and discuss the appropriate risk response plans with the project sponsor and client. | Seek the project sponsor's support to influence the client to amend the contract immediately. | Wait until the legal requirements are finalized so the change in scope can be concretely defined. | B | The risk register should be regularly reviewed, and including this issue in the risk register will ensure that it is monitored. Discussing appropriate risk response plans with the project sponsor and client is a proactive approach to addressing potential changes in legal requirements that may affect the project. This allows for early planning and preparation rather than waiting until the law is fi
912 | Resource | In a critical project to the organization, one of the contractors complains that approvals are lengthy and difficult to handle. The contractor mentioned this as it may affect the project schedule. What should the project manager do next? | Add this risk to the risk register to be monitored and reviewed. | Discuss this with the team to find options to mitigate the risk. | Hire additional resources for the team to mitigate this risk. | Escalate the risk to upper management as critical for timely delivery. | B | The project manager should first discuss the issue with the team to brainstorm potential solutions and mitigation strategies. This collaborative approach allows for diverse perspectives and may lead to innovative solutions to address the approval process concerns without immediately escalating or adding resources.
913 | Risk | A project manager is working on requirement management in a pharmaceutical company. Which improvement should the project manager's organization expect as an outcome of the project? | Increased costs | Reduced quality | Reduced risks | Increased schedule | C | Improved requirement management typically leads to reduced risks in pharmaceutical projects. By better defining and managing requirements, the project is less likely to encounter unexpected issues or misalignments, thus reducing overall project risks.
914 | Scope | During the testing phase of a project, a team member finds that some requirements were not met. If the project now adds work to meet the requirements, it may cause a large time and cost overrun. What should the project manager do first? | Call for a stakeholder meeting. | Perform an impact analysis. | Escalate the issue to top management. | Update the risk register. | B | Before taking any action, the project manager should first assess the impact of the unmet requirements on the project's time, cost, and scope. This analysis will provide crucial information needed to make informed decisions about how to proceed and what options are available.
915 | Resource | The development of a project requires incremental delivery of the product. Project delivery involves the efforts of both local and remote team members. What communication strategy should be used in this situation? | Implement the communications plan to ensure communications relative to project delivery are performed following the plan. | Ensure each country team sends detailed status reports to the project manager | Send daily email updates between each of the country teams | Schedule one-on-one biweekly calls with each country team | A | Following an established communications plan ensures that all team members, both local and remote, are informed and engaged in the project's incremental delivery process. This structured approach helps maintain consistency and clarity in project communications.
916 | Resource | At an agile project meeting, a team member gives an update on the status of their important task. A new team member interrupts them when they hear their task mentioned and gives a status update before the first team member has finished their update. What should the scrum master do? | Privately talk to the team member after the meeting. | Interrupt the new team member and let the original speaker continue. | Discuss protocol with the team at the conclusion of the meeting. | Interrupt the new team member to discuss protocol. | C | Addressing the interruption at the end of the meeting allows the scrum master to reinforce proper meeting etiquette for the entire team without singling out the new member or disrupting the flow of the current meeting. This approach maintains a positive team dynamic while educating all members on proper protocol.
917 | Communications | A strategic project has been launched, and a project manager has been assigned. As the project progresses and the team delivers successfully, a key stakeholder calls the project manager and complains about not receiving progress updates. What should the project manager do first? | Ensure the key stakeholder is copied on the weekly project status emails. | Send the key stakeholder a copy of the latest project status report. | Review and update the project communications management plan. | Invite the key stakeholder to the next project meeting. | C | The project manager should first review and update the communications management plan to ensure all key stakeholders are included and receiving appropriate updates. This systematic approach addresses the root cause of the communication gap rather than just providing a one-time solution.
918 | Communications | A project manager is in the execution phase of a project. A newly identified stakeholder continuously bypasses the project manager to get feedback from the project sponsor directly, thus escalating pressure and frustration for all team members. What should the project manager do next? | Call a project meeting of all stakeholders to discuss the matter and develop a suitable action plan. | Meet with this stakeholder to update the engagement plan and understand their communication needs. | Meet the project sponsor and confirm that the project manager must be the single point of contact. | Email the communications management plan to the stakeholder concerned and point out that they agreed. | B | By meeting with the stakeholder directly, the project manager can understand their specific needs and concerns, update the engagement plan accordingly, and establish a more effective communication channel. This approach addresses the issue at its source and helps prevent future bypassing of the project manager.
919 | Communications | At the end of the first phase of a stadium expansion project, the project manager realizes they may be running behind schedule for the next phase. The delay is due to new safety requirements that must be considered. It information only came to the project manager after contacting the site supervisor. What should the project manager do to avoid situations like this? | Trigger the change management process to accommodate the new safety requirements. | Implement a communications monitoring check to ensure information needs are met to anticipate issues. | Improve project communications to ensure an appropriate approach for sharing relevant project updates. | Arrange a project review meeting with all relevant stakeholders to check if any other requirements have been missed. | C | Improving overall project communications is the most comprehensive solution to prevent similar situations in the future. This approach ensures that all relevant information, including new safety requirements, is shared appropriately and timely among all project stakeholders.
920 | Communications | Three weeks into the execution of a project, the project manager realizes that their communication with a key stakeholder has been via phone calls only. The stakeholder is copied in the project's email thread which all stakeholders unanimously specified as the only means of communication. How should the project manager address the situation? | Ask the stakeholder if they prefer the email thread or phone contact. | Document phone conversations and email the document to all stakeholders. | Continue communicating with all stakeholders via the email thread. | Keep records of all phone conversations with the stakeholder. | C | Since all stakeholders, including the one in question, unanimously agreed to use the email thread as the primary communication method, the project manager should adhere to this agreement. Consistency in communication methods helps maintain clarity and ensures all stakeholders receive the same information.
921 | Communications | A client's project sponsor assigns a contact person to the project manager. Additional intermediate reports and details are being asked for by the contact person, increasing the overhead of preparing the progress reports. However, during a monthly status meeting, the client's project sponsor complains of non-receipt of progress reports. What should the project manager do to address this situation? | Meet the project sponsor and confirm that the project manager must be the single point of contact. | Email the communications management plan to the stakeholder concerned and point out that they agreed. | Call a project meeting of all stakeholders to discuss the matter and develop a suitable action plan. | Meet with this stakeholder to update the engagement plan and understand their communication needs. | C | By bringing together the project sponsor and the contact person, the project manager can address the communication gaps directly. This meeting allows for clarification of roles, responsibilities, and communication expectations, ensuring that all parties are aligned on the reporting process.
922 | Resource | A project to launch a new product to the market is starting its third iteration out of six. During iteration planning, the customer explains that another company is launching a similar product soon. What should the project manager do first? | Assist the team in redefining a minimum viable product (MVP) to deliver it before the competitor. | Increase the capacity of the team to complete delivery before the competitor. | Register an issue and detail it in the status report. | Ask the customer to reduce the backlog to deliver the product before the competitor. | A | Redefining the MVP allows the team to focus on delivering core functionality quickly in response to the competitive threat. This agile approach helps the project adapt to the new market conditions while still providing value to the customer.
923 | Communications | After nine months, a project concludes its first phase by releasing a new product to its customer. The client provides feedback stating that many key features are missing. What should the project manager do? | Start the project again using an agile life cycle and propose creating a minimum viable product (MVP) during three months. | Move to an agile life cycle using shorter iterations so the team can evaluate value with the stakeholders and prioritize accordingly. | Evaluate the missing features with the client and plan to include them in the next 9-month project phase. | Request more funding to reduce the release cycle from nine to six months so the team can deliver value sooner. | D | Improving overall project communications is the most effective way to prevent similar situations in the future. This approach ensures that important information, such as new safety requirements, is shared promptly and appropriately among all project stakeholders.
924 | Communications | A scrum team is using a hybrid approach with 2-week sprints. The minimum viable product (MVP) release is at the end of the current sprint, and the team has completed the must and should feature; however, some of the other priority features are still in development. The project manager is preparing the monthly report for the steering committee. What should the project manager recommend? | Update the project management plan to include only the features completed in the release. | Estimate the effort required and submit a change request to add more resources to the team. | Organize the sprint review and release the MVP only with the completed features. | Reschedule the MVP release review until all the agreed-on features have been completed. | C | By meeting directly with the stakeholder, the project manager can understand their specific needs and concerns, update the engagement plan accordingly, and establish a more effective communication channel. This approach addresses the issue at its source and helps prevent future bypassing of the project manager.
925 | People | A delivery team member is complaining about the workload and the number of top priorities they are handling. Another team member is complaining that they cannot do their work due to the lack of progress from this team member. They are both frustrated and low-performing because of this dispute. What should the project manager do to improve team performance? | Find common ground between the two team members so that they know they have areas of agreement. | Initiate conflict-solving techniques to avoid situations that get out of control. | Recognize that emotions are part of this issue and address them first. | Utilize stakeholder engagement tools and escalate the situation. | A | Finding common ground helps to reduce conflict and improve collaboration between team members. By focusing on areas of agreement, the project manager can help build a more positive and productive working relationship between the team members.
926 | Resource | During the last five daily standups, a team member on a hybrid (predictive- agile) project has been vague about what they have done and will do. What should the project manager do next? | Review in the retrospective meeting what has been achieved and implement corrective action. | Raise the issue of task accountability with the team and stakeholders at the next iteration review meeting. | Facilitate a meeting with the team and stakeholders to review the risks and impediments faced by the project. | Meet with the team member to ensure they understand the accountability responsibilities and to discuss any obstacles. | D | A one-on-one meeting allows the project manager to address the issue directly with the team member, understand any underlying problems, and reinforce accountability expectations. This approach is more targeted and less likely to cause embarrassment compared to addressing the issue in a group setting.
927 | Cost | A construction company is implementing a new strategic project with a fixed budget. While analyzing the project, the overall cost is increasing because more materials are being used than the materials detailed in the original scope. The team members have not been reporting the acquisition of new materials because they are new to the company. What should the project manager have done to prevent this? | Allocated time for emphasizing the importance of the change control process to the team members | Reviewed variations in the project cost baseline since the beginning of the project | Rejected the inclusion of new engineers in a strategic project for the company | Registered the risk of a cost deviation in the risk matrix | A | By educating team members about the importance of the change control process, the project manager can prevent unauthorized changes and ensure that all material acquisitions are properly documented and approved. This proactive approach helps maintain cost control and prevents scope creep.
928 | Resource | Discussions during weekly project team meetings are frequently dominated by a senior team member who tends to talk over other team members and openly criticize their points of view. It is causing demoralization of the other team members and resulting in a lack of engagement during the meetings. What should the project manager do to address this issue? | Enforce the existing ground rules for team behavior. | Remove the senior team member from the weekly meeting. | Organize a team-building activity that encourages finding solutions together. | Escalate the behavior of the senior team member to the functional manager. | A | Enforcing existing ground rules is the most appropriate action as it addresses the issue without singling out the senior team member. This approach maintains team cohesion while reinforcing expected behaviors for all team members.
929 | Resource | A project manager is working with remote team members who are acting independently. What should the project manager do to promote collaboration among team members? | Ask each team member to complete a daily update task log. | Include the team members in all emails regarding the project. | Call team members individually to collect information and provide updates weekly. | Promote regular meetings using video conferencing. | D | Regular video conferencing meetings can help foster collaboration among remote team members by providing face-to-face interaction and real-time communication. This approach helps build team cohesion and encourages more active participation from all team members.
930 | Resource | A global, cross-functional team has been assembled to deliver a multinational initiative. What should the project manager do to ensure full team participation throughout the project? | Ensure software is delivered in multiple languages. | Coordinate time zone information and agree to meeting times. | Translate the project documentation. | Provide guidance on common tools and practices. | B | For a global, cross-functional team, coordinating time zones and agreeing on meeting times is crucial to ensure full participation. This approach shows consideration for all team members and helps create a more inclusive project environment.
931 | Schedule | A project is underway with team members from two different countries. Due to cultural differences, there are complaints from both sides. One side reports that team members on the other side are too slow to respond and often have scheduled days off. The other side believes in a good work/life balance and thinks more consideration is needed before making decisions. What should the project manager do? | Revisit the communications management plan and update it if needed. | Investigate the root cause of misunderstandings. | Remind team members to understand the cultural differences. | Review the team charter with team members. | D | Reviewing the team charter can help address cultural differences by reminding team members of agreed-upon norms, values, and working practices. This approach can help bridge cultural gaps and promote better understanding and collaboration within the team.
932 | Resource | A large transformation project has moved its project management office (PMO) to a virtual environment. The PMO team has had performance issues regarding their daily tasks, which are now affecting the project. Which three actions should the project manager take to improve the performance of the PMO team? Choose three: | Hire a new senior manager for the virtual teams to improve collaboration between departments. E) Suggest that management dissolves the virtual team or moves the PMO to a colocated area. | Nurture confidence among the PMO team members by providing them with the required training on project management tools. | Provide access to communication tools to help the virtual teams connect better with the stakeholders. | Build a collaborative environment by having regular connections among the PMO team members. | D | To improve the performance of a virtual PMO team, the project manager should focus on three key areas: Building collaboration: Regular connections among team members help create a sense of unity and shared purpose, which is crucial for virtual teams. Nurturing confidence: Providing training on project management tools ensures that team members have the necessary skills to perform their tasks effec
933 | Resource | An agile team has a good track record of consistently delivering product features on time but recently identified a huge gap in its architecture understanding, resulting in rework. Which agile response should be used to address this issue? | Increment planning | Daily standup | Demonstration to stakeholders | Team retrospective | D | A team retrospective is the most appropriate agile response to address the issue of a gap in architecture understanding. During the retrospective, the team can perform a brainstorming session to identify what went wrong and what corrective actions can be taken to improve their understanding and prevent similar issues in the future.
934 | Resource | A project manager is managing a project for a successful startup. The startup has shown exponential growth with multiple benefits to the team members, including flexible work hours and a work-from-home policy. During the last retrospective, one of the team members noted that the team velocity improved when the team was physically gathered in the project room. What should the project manager do? | Update the team charter to promote colocation. | Update the resource management plan to promote colocation. | Refine the backlog to improve team velocity. | Suggest an update to the company policies to senior management. | A | Behaviors that improve the team's performance should be fostered and added to the team charter when necessary. Since the team velocity improved when physically gathered, updating the team charter to promote colocation is the most appropriate action to capitalize on this observation.
935 | Schedule | At the first meeting about a road construction project, the project manager reminds the team of the importance of observing all rules when carrying out their duties and interacting with stakeholders. Later in the project, team members come to meetings late and do not follow other ground rules. To ensure the project outcomes and schedule are not affected, what should the project manager do next? | Address the issue with the specific team members who violated the ground rules. | Promote all team members who do not violate any ground rules. | Allow the team to investigate any team members who violate the ground rules. | Remove the team members who violated the ground rules. | A | Conflict should be addressed first, usually privately, using a direct, collaborative approach. Addressing the issue with the specific team members who violated the ground rules is the most appropriate action to ensure project outcomes and schedule are not affected while maintaining a healthy team spirit.
936 | Resource | A company engaged an international virtual team due to lacking locally skilled resources. What should the project manager do to ensure this virtual team remains engaged? | Ensure the entire virtual team is invited to the kick-off meeting for a common understanding. | Consistently monitor the virtual team's performance against expectations. | Adopt a communications management plan used successfully for virtual teams previously. | Plan for regular meetings with the virtual team in their home office. | B | To ensure the virtual team remains engaged, the project manager should consistently monitor their performance against expectations. This approach allows for timely identification of any issues or challenges and enables the project manager to provide necessary support or adjustments to keep the team engaged and productive.
937 | Resource | A project manager is working on a new project. Two key project resources disagree with a requirement. The project manager wants to understand both points of view, but one resource is unwilling to meet with the manager. What should the project manager do? | Review the organizational process assets (OPAs). | Escalate the issue to the project sponsor. | Refer to the team's ground rules and project vision. | Accept the position of senior project resource. | C | The project manager must obtain an agreement on how the team should proceed, and this can be found in the established ground rules. They must also obtain consensus and use this information to resolve conflicts in alignment with the project vision. Referring to these established guidelines is the most appropriate action in this situation.
938 | Resource | A project manager is managing a project using a hybrid approach. During the project, some team members left but were replaced with other resources. However, at the beginning of another sprint, the project manager realized that a specific skill was missing, and the only resource with this skill had left the team months earlier. What should the project manager have done to avoid this? | Ensured the team members transferred their knowledge within the team | Ensured team members had at least one skill in common | Ensured the team skills were aligned with the project tasks every time a team member was replaced | Ensured review of the communications management plan to avoid the lack of information flow | C | The project manager should have ensured the team skills were aligned with the project tasks every time a team member was replaced. This proactive approach would have helped identify and address any skill gaps before they became problematic.
939 | Resource | A project manager realizes that the team needs training on a specific technology required in the project. What should the project manager do to mitigate this risk? | Contract with an expert provider to do the work that uses that specific technology | Create an item in the risk log and notify the sponsor | Assess the team's knowledge of the technology and look for recommended training options | Fix any training gaps as they arise during the project | C | To mitigate the risk of lacking specific technology skills, the project manager should first assess the team's current knowledge and then look for appropriate training options. This approach addresses the skill gap directly and efficiently.
940 | Cost | A project manager is assigned to a new project and begins building the team. The project manager quickly discovers that some team members are concerned with personal development, whereas others lack the technical skills required to perform the necessary work. What should the project manager do first? | Schedule a team workshop with the customer to demonstrate the product objectives | Work with the functional manager of each team area to provide substitute team members who better align with project objectives | Analyze the skills of each team member against the project requirements to identify gaps and develop action plans to fulfill the gaps | Initiate the first sprint and let the team self-organize to solve the identified gaps | C | The project manager should first analyze the skills of each team member against the project requirements to identify gaps. This allows for the development of targeted action plans to address both personal development concerns and technical skill deficiencies.
941 | Resource | During an iteration review, a stakeholder suggests speeding up development by using an off-the-shelf, open-source product. The project team has analyzed the open source product suitability and determined that it would speed up development, but it needs to be piloted for better understanding and requires additional user skills. What should the project manager do next? | Consult the product manager for the next steps | Initiate change management for budget impacts | Review the cost management plan | Request training for the project team | D | Since the open-source product requires additional user skills, the project manager should prioritize training for the project team. This ensures the team can effectively use and implement the new technology.
942 | Scope | A project manager is assigned to a top innovation project that has visibility with the company executives. One of the project requirements recently changed, requiring new, innovative technology. During a status meeting, a team member confirms they are certified in this new technology. What should the project manager do? | Hire a new resource and ask the team member to train the resource on the new task as needed | Ask the team member to continue the current job assignment while taking on the new assignment as time allows | Reassign the team member to the task to support their growth at the organization and acquire a resource to replace the team member's old role | Escalate a request to determine if the team member can be assigned to the new assignment | C | Reassigning the certified team member to the new task supports their professional growth and utilizes their skills effectively. Acquiring a replacement for their old role ensures continuity in other project areas.
943 | Resource | A team member unfamiliar with the subject matter struggles to complete a complex deliverable. What should the agile project manager do to ensure the team member can take on a similar challenge in the future? | Replace the team member with a more experienced team member who will improve the team's velocity | Ask the team member to avoid taking on stories on this subject matter until the person is comfortable with the subject matter | Ensure the team member receives adequate training and is comfortable with the subject matter | Encourage the team member to take on more stories on this subject matter until they are completely comfortable | C | Providing adequate training and ensuring the team member becomes comfortable with the subject matter is the best approach to prepare them for future similar challenges. This supports their growth and improves team capability.
944 | Scope | As part of a project deliverable, a project manager demonstrates how to use one of the products to a subset of a client's employees. The employee- manager complains that a workshop would have been more effective for training. What should the project manager have done to prevent this situation? | Consulted the client's project sponsor on the best system training method | Provided a contingency reserve for additional training | Included this risk in the risk management plan | Ensured that the scope management plan specified the type of training to be conducted | D | The project manager should have ensured that the scope management plan specified the type of training to be conducted. This would have clarified expectations and prevented misunderstandings about the training method.
945 | Scope | A project manager is unsure if the team has the critical skills to implement a key feature of an upcoming deliverable. In order to mitigate the risk of sprint failure, what should the project manager do? | Ask for support from the sponsor to replace the low performers on the team with new team members with a specific skill set | Negotiate with the stakeholder to postpone this key feature to a later release while finding a better alternative | Use the next retrospective to assess the skill gap and propose a training or scope outsourcing strategy | Embrace the risk and accept the failure, if it happens, and motivate the team toward better performance in the future | C | Using the next retrospective to assess the skill gap and propose a training or scope outsourcing strategy is the most proactive and collaborative approach to address the potential risk of sprint failure.
946 | Resource | A midsize project has the objective of developing an innovative product with changing requirements. The project manager realizes that the cost of quality increases substantially when a few resources are unavailable for two weeks per month during the project's duration. However, the team velocity is stable. What should the project manager do to address this issue? | Provide cross-training | Increase the sprint duration | Increase the testing effort | Add resources to the team | A | Providing cross-training is the best solution to address the issue of increased quality costs due to resource unavailability. This approach maintains team velocity while improving flexibility and reducing dependence on specific resources.
947 | Cost | After some meetings, the team facilitator realizes the team members are working together for the first time. They are having difficulties communicating and collaborating. The team facilitator wants to understand each individual's behavior and tailor the leadership style to the team's needs. Which tools or techniques should the team facilitator use in this situation? | Personality assessments and one-to-one coaching | Cultural assessments and weekly teleconferences | Weekly teleconferences and technical assessments | Technical assessments and cultural assessments | A | Personality assessments and one-to-one coaching are the most effective tools for understanding individual behaviors and tailoring leadership styles to the team's needs, especially for a newly formed team facing communication and collaboration challenges.
948 | Resource | A team is transitioning from a predictive to an agile approach. Which two obstacles will the team encounter? | Management provides freedom for the team to decide and management expects the team to keep their performance level | Management would like the team to learn and adapt and management provides freedom for the team to decide | Management support is lacking for team empowerment and management continues to control the processes of delivery | Management continues to control the processes of delivery and management expects the team to keep their performance level | C | When transitioning from a predictive to an agile approach, common obstacles include lack of management support for team empowerment and continued management control over delivery processes, which are contrary to agile principles.
949 | Resource | When reviewing the project team's performance, the project manager realizes that the team's velocity is not fast enough to meet the next review gate goal. What should the project manager do? | Prioritize the contents of the backlog and remove some stories | Increase the sprint duration to allow the team more time | Create a change request to modify the review gate goals | Use the standup meeting to assess impediments and problems | D | The daily standup meeting is the most appropriate and immediate way to assess impediments and problems affecting the team's velocity. This allows for quick identification and resolution of issues that may be slowing down the team's progress.
950 | Resource | A project team working on a change-driven project continually misses the release time lines. The project manager identifies an experienced team member assigned multiple projects. What should the project manager do? | Ask the functional manager to assign a dedicated team member to this project | Adjust the schedule and issue a change request | Discuss this with the team at the next retrospective and find a solution | Report the issue to the project sponsor | A | Requesting a dedicated team member from the functional manager is the best solution to address the issue of missed release timelines due to a team member being assigned to multiple projects. This ensures full commitment and focus on the project.
951 | Stakeholder | In a kick-off meeting, the sponsor informs the project team that he has insufficient time to discuss this project soon. The sponsor would like to assign another stakeholder to this project as a replacement. What should the project manager do? | Request the full attention of the sponsor and escalate this issue to the project management office (PMO) | Set up a meeting with the replacement sponsor as soon as possible to discuss the upcoming agenda | Negotiate meeting times with the sponsor to catch up and facilitate decision-making | Request that the replacement be an individual with decision-making capabilities | C | The project manager should attempt to maintain engagement with the original sponsor by negotiating meeting times. This approach ensures continuity in project leadership and maintains the sponsor's involvement in critical decision-making.
952 | Scope | A company is working on a hybrid project in which the deliverables have quality issues at the end of one of the sprints. Which action should the project manager take? | Apply value stream mapping | Look for a clear set of working agreements | Review the definition of done (DoD) | Use a plan-driven approach | C | In a hybrid project with quality issues at the end of a sprint, reviewing the Definition of Done (DoD) is crucial. This ensures that all team members have a clear understanding of what constitutes a completed, high-quality deliverable.
953 | Resource | Halfway through a year-long project, a hardware supplier sends a project manager notice of an intent to increase prices due to fluctuating exchange rates. The project manager is unsure of their negotiating authority. Which document should the project manager reference? | Procurement management plan | Project charter | Communication strategy | Risk register | A | The procurement management plan is the most appropriate document to reference for negotiating authority in procurement-related matters, such as price increases from suppliers.
954 | Stakeholder | A project manager has been assigned to an important project with stakeholders with different expectations. Some stakeholders also have a high degree of influence on the project. How should the project manager handle this situation? | Control the degree of stakeholder influence to better align with the project objectives | Manage the stakeholders carefully and apply stakeholder expectations without impacting the project objectives | Include the influential stakeholders' requirements and ensure other stakeholders are aligned with the project goals | Elicit and negotiate stakeholder requirements according to each stakeholder's influence | D | The project manager should elicit and negotiate stakeholder requirements based on each stakeholder's influence. This approach allows for balancing different expectations while considering the varying degrees of stakeholder influence on the project.
955 | Communications | In a software development project, a stakeholder wants to add a major requirement that they feel will greatly benefit the project. However, this requirement is not aligned with the project objectives that the business owner has documented. What should the project manager do next? | Fast-track the project and suggest the new requirement to the business owner | Include the additional requirement in the project and inform the business owner | Ensure the stakeholder understands the purpose of the project | Encourage the stakeholder to follow the written business requirements | C | The project manager should first ensure that the stakeholder understands the project's purpose and objectives. This helps align the stakeholder's expectations with the project's goals before considering any major requirement changes.
956 | Stakeholder | During the execution phase of a project, a new director who joined the management team introduced a mandatory compliance requirement impacting all project tasks. The team is aware of the compliance requirement. What should the project manager do first? | Perform a quantitative risk analysis | Update the stakeholder register | Perform a qualitative risk analysis | Update the communications management plan | B | The first step should be to update the stakeholder register to include the new director and their compliance requirement. This ensures that all stakeholders and their requirements are properly documented and considered in project planning.
957 | Communications | A company initiated a project to build a new hydropower plant. Analysis was performed to determine regulatory, safety, and security issues. After the analysis, it was obvious that some of the features to achieve compliance may be very hard to implement. Stakeholders' opinions about the importance of compliance are different and not well argued. What should the project manager do? | Optimize the alignment between stakeholders' expectations and project objectives | Escalate the concerns regarding compliance and the different stakeholders' opinions to the sponsor | Review the stakeholder engagement plan | Increase stakeholder awareness about compliance | D | Increasing stakeholder awareness about compliance is crucial when there are differing opinions about its importance. This helps create a common understanding and can lead to better-informed decisions about implementing compliance features.
958 | Stakeholder | An ongoing project has a high degree of change. In order to evaluate how the security team will influence the project's performance, what should the project manager do? | Analyze political and power structures | Manage stakeholders' expectations | Create a stakeholder engagement assessment matrix | Create a communications management plan | C | Creating a stakeholder engagement assessment matrix is the best tool to evaluate how the security team will influence the project's performance. This matrix helps in understanding and planning for stakeholder engagement levels and their potential impact on the project.
959 | Cost | The team detects a misunderstanding about one critical deliverable in a review meeting. What should the project manager do to resolve this misunderstanding? | Ask the product owner to clarify the deliverable | Ask the sponsor to clarify the deliverable | Ask the customer to clarify the deliverable | Ask the team to discuss the issue and reach a consensus | D | When there's a misunderstanding about a critical deliverable, asking the team to discuss the issue and reach a consensus is the best approach. This promotes collaboration and ensures that all team members have a shared understanding of the deliverable.
960 | Resource | A project manager observes that team members are not collaborating or being proactive. What should the project manager have done at the beginning of the project to achieve a better project environment? | Split the project into more iterations | Conducted an assessment of team dynamics | Assigned all tasks at the beginning of the project | Held additional team meetings | B | To achieve a better project environment from the beginning, the project manager should have conducted an assessment of team dynamics. This would have helped identify and address collaboration and proactivity issues early on.
961 | People | A highly skilled subject matter expert (SME) is working on a government project. About 30% of the deliverables will be executed using an agile approach, and the SME is asked to join the team. However, the SME does not want to work on the agile iterations because working on a team demotivates and slows the SME down. The SME mainly wants to achieve the highest-quality output possible. Which approach should the project manager take to reconcile the SME's skills and motivation, the agile team structure, and project goals? | Request that the SME conduct the retrospective meetings as an objective observer | Propose that the SME combine the product owner and team facilitator roles | Require the SME to receive mentoring to improve their attitude | Recommend that the SME develop more emotional intelligence by integrating with the team | B | Proposing that the SME combine the product owner and team facilitator roles is the best approach to reconcile the SME's skills and motivation with the agile team structure and project goals. This allows the SME to contribute their expertise while also facilitating team progress.
962 | Resource | A specialized team member has just received news that they must leave the office for several weeks. They have approximately two workdays until they leave, then they will become unavailable through any communication channels. There is a key deadline approaching. What should the agile project manager do? | Ask the team member to host a special team meeting | Ask the team member to work with their peers to share knowledge | Ask the team member to identify their specialist tasks | Ask the team member to complete as much as they can now | B | When a specialized team member is leaving, the best approach is to ask them to work with their peers to share knowledge. This ensures that critical information and skills are transferred to the remaining team members before the specialist's departure.
963 | People | During the meeting, two team members who worked on the same tasks argue about who's fault was that the task was late. None of them want to be perceived as the one who caused the delay. What is the most likely cause of this issue? | Conflicting Priorities | Personal Competition | Personnel Selection | Unclear Responsibilities | D | The most likely cause of team members arguing about who's at fault for a late task is unclear responsibilities. When roles and responsibilities are not well-defined, it can lead to confusion and conflict over task ownership and accountability.
964 | Schedule | A distributed team just finished an iteration that completed complex tasks ahead of schedule. During a retrospective, a new member interrupts and asks everyone to reiterate their role and what they have worked on in previous iterations. What should the project manager do? | Ask the functional manager of the new team member to review the onboarding process | Ask each team member to explain their role and what they worked on in the previous iteration | Refer the new team member to the project management plan | Inform the team member that this would be best handled in another meeting | D | When a new team member interrupts a retrospective with questions about roles and previous work, the best action is to inform them that this would be better handled in another meeting. This maintains the focus of the retrospective while ensuring the new member's questions are addressed at an appropriate time.
965 | Resource | A project manager wants to establish an incentive and rewards strategy for the project team. What approach should be taken? | Check on budget availability in order to determine specific reward amounts | Provide an opportunity for publicly presenting the outcomes | Ask the Human Resources department which incentives should be provided | Identify the specific needs of each team member to determine incentives | D | Not all rewards are money based. We need to understand individual preferences when recognizing and motivating.
966 | People | A project manager is working on a long-term project in a complex environment. The project manager's focus is on maintaining healthy teamwork and collaboration. What conflict resolution strategy should be used within the project team? | Accommodating | Compromising | Problem-solving | Consultation | C | It is recommended to avoid the conflict or problem by solving it before it becomes an issue that could impact the teamwork and environment.
967 | Resource | What are the four team-building leadership styles? | Visionary, affiliative, coaching, and directive | Visionary, affiliative, coaching, and pace-setting | Visionary, affiliative, coaching, and participative | Visionary, affiliative, coaching, and high waters | C | Visionary, affiliative, coaching, and participative are all related to team-building leadership styles. Pace-setting, directive, and high waters are non-team builder leadership styles, focusing more on achievements than relationships.
968 | Resource | A project manager manages a hybrid project and has requested a senior team member to perform a quantitative risk analysis. The team member responds that they do not have the knowledge to perform such an analysis. What should the project manager do? | Perform the quantitative risk analysis for the team member | Contact the project management office (PMO) and request them to assign another team member who has the knowledge to perform this task to the team | Help the team member to perform the quantitative risk analysis through coaching, mentoring, and training | Escalate the issue to the functional manager | C | In a hybrid project, the Project Manager is a servant leader and should do everything to support the team. In this case, if the Project Manager is not skilled in performing qualitative risk analysis, the project manager is expected to arrange training, mentoring, and coaching from experts to help the team member perform the expected task.
969 | Resource | A lengthy, ongoing project exhausts a project team. Due to deadline issues, the project manager needs to encourage team members. What should the project manager do? | Request additional resources | Discuss the situation with the team | Provide more recognition and rewards to team members | Review the project charter and propose extending the project schedule | C | More recognition: The project manager notes he needs a way to encourage team members. Recognition is a method to enhance the engagement of team members.
970 | Resource | A project manager works for a company involved in complex turnkey projects. During a close team assessment, the project manager finds that the team does not have experience adjusting to frequent changes in project requirements and communications. What should the project manager do to ensure great team performance? | Let the sponsor communicate with the team to improve performance | Communicate with stakeholders regularly to avoid frequent changes | Encourage more communication with the team | Provide training to the team on using a hybrid approach | D | Little experience with a hybrid approach is very critical; hence, addressing the change in methodology with the team through capacity building will be the first to yield results out of the listed impediments.
971 | Resource | An agile team is doing an excellent job of focusing on high-priority items and completing them in less time than required. Which key performance indicator (KPI) should demonstrate this information to the project manager? | The number of user stories from the backlog that are completed per iteration | The number of action items coming out of the end-of-iteration retrospective | The number of defects or missed requirements identified by the product owner | The team staying within the Kanban board work-in-progress limits | D | Kanban boards are the only answer out of the below that measure lead time and manage non-value added work through limiting via work-in-progress limits.
972 | Resource | A project manager should plan specific development activities for team members to improve project performance and outcomes. What should the project manager do first? | Question the team members' development needs | Appraise team members' individual performance | Analyze the team members' capabilities | Evaluate project performance | B | A project manager needs to conduct a formal or informal performance assessment of the team and implement team development strategies like team building and colocation. The project manager should care about developing the specific competencies of individual team members, which are vital for the successful implementation of specific activities assigned to those team members.
973 | Risk | The project manager of a large team notices that team members are not interacting together, which is impacting project performance and the quality of the project outcome. What should the project manager do to help grow team dynamics? | Conduct face-to-face group meetings to understand what the issues are | Refer to the lessons learned to understand how other projects handled similar issues | Notify the project team members' supervisors about the lack of cooperation | Add the lack of team communication as a risk in the risk register and monitor the situation | A | To have effective results and improve customer satisfaction, the project manager should continuously nurture team members by listening to their comments and giving feedback regularly. It will help to understand what is going on.
974 | Resource | A large-scale project has been consistently progressing. However, the team recently encountered difficulties completing complex stories and maintaining velocity. What should the project manager do to enhance the team's performance? | Perform a root cause analysis | Focus on servant leadership | Improve team communications | Seek insight from an experienced mentor | C | Agile teams use stand-ups to micro-commit to each other, uncover problems, and ensure the work flows smoothly through the team.
975 | Resource | A project is in the implementation phase. A new project manager discovers that the team members have no previous experience with the technology used for the project. However, they are experienced functional managers from various fields. What should the project manager do first to ensure the team's successful performance? | Appraise individual team member skills and assign new roles, respectively | Proactively develop team skills and competencies | Ask the sponsor to replace team members with experienced ones | Identify the risks associated with team members' inexperience | A | To ensure the project's success, which is already in the implementation phase, the project manager only can use the existing resources as best as possible. At first, the project manager needs to assess the team capabilities and only think about their development and team building.
976 | Risk | A new project manager has taken over an ongoing project. Progress reports show that the project is within the allocated budget and schedule. However, a key supplier has indicated that they cannot supply critical materials as scheduled. What should the project manager do first? | Take legal action against the defaulting supplier | Submit a change request to the change control board (CCB) | Review the performance against the project baseline | Document and update the risk register | C | The project manager should first investigate the performance against the project baseline to determine if the critical materials' delay will impact the project schedule.
977 | Resource | A project team's performance has declined for the last three iterations. Some team members are disappointed and raise their concerns during the retrospective meeting. What should the project manager do? | Focus on remediation, not merely on correcting symptoms | Compare the team's performance against other project teams | Motivate the team to perform better | Identify potential failure points based on the iteration workload | A | Root cause analysis is designed to identify and correct the fundamental cause of a problem. It helps focus remediation not merely on correcting symptoms but on preventing the recurrence of problems. This type of analysis is especially useful for proactively forecasting probable events before they occur.
978 | Cost | On an agile project, a team member has been taking smaller, easier user stories from the backlog, not necessarily those with the highest priority. How should this be addressed? | Direct the team member to take specific, more challenging user stories in the next iteration | Retrain the team member on the core technologies used to build the product to address the skill gap | Remind the team that the highest priority items must be taken from the backlog first | Meet with the team member to understand the reason and tailor the workload approach, if required | D | The project manager needs to understand the root cause before taking action.
979 | Scope | While gathering requirements for the project scope, the project manager realizes that some stakeholder requirements conflict. What should the project manager do to define a clear scope? | Escalate to the project sponsor to make a decision | Follow the recommendation of the technical consultant | Assist affected stakeholders in reaching a consensus | Conduct a meeting with the disagreeing parties only | C | The project manager must proactively reach a consensus between the project team and stakeholders. All parties should be involved so that a consensus can be reached. The project manager must use all necessary communication techniques to gather and ensure clear requirements.
980 | People | Due to the complex nature of a predictive project, an organization decides to use an agile approach for a project phase. A team member does not understand the agile approach and keeps allocating tasks to the other team members. After a while, the team cannot adjust, and conflicts arise, delaying the deliverables. What should the project manager do? | Replace the team member with someone who has agile experience | Reaffirm the principles and roles of agile to create structures that the team can use | Take control of the sprint backlog and assign tasks to the team members | Wait until the team can finally resolve the conflict and reorganize | B | When agile values and ground rules are understood and applied, the team can adjust and resolve conflicts more effectively.
981 | Cost | A project manager has been assigned to a new project with multiple stakeholders. Each stakeholder has provided their expectations for the project, and the project manager realizes some of the expectations conflicts. What should the project manager ensure? | Create a project hierarchy to manage the stakeholders' expectations | The goals and expectations of the key stakeholders are met | Review the conflict management plan for the stakeholders | Update the stakeholder register with the stakeholders' expectations | B | Properly identifying and prioritizing project stakeholders will help the project manager manage the expectations and objectives of the project.
982 | People | A senior team manager is having challenges with a team member due to conflicts with the rest of the team, such as high absence and failure to deliver on tasks. The senior team manager asks the project manager for advice on handling this team member. What should the project manager do? | Listen to the senior team manager, mentor them, and have them decide what to do | Ask for a one-on-one meeting with the team member and try to resolve the conflict | Check the team member's performance and responsibility assignment matrix to ensure correct information | Request a meeting with the senior team manager and team member and act as a mediator to resolve the conflict | A | The best way to lead a senior team member is by active listening and delegating the decision under their control. To enhance project performance, the project manager must practice monitoring and providing feedback to team members, resolving difficulties, and managing team change.
983 | People | A project manager notices that conflicts are occurring in every sprint. After an investigation, the project manager discovers that the team needs to be trained in agile techniques to address these conflicts. Which perspective should the project manager use in this scenario? | Process level | Quality and performance | Team dynamics | Product level | D | Agile transformation occurs when an organization completely adopts an Agile methodology. The process level is the perspective that helps us identify how we are doing with agile and remember the basic ingredients of agile.
984 | People | In the early stages of team formation, a project manager is unable to focus on the main tasks because team members are constantly asking for help to resolve conflicts regarding the interpretation of the client's requirements. What should the project manager do? | Spend time resolving these conflicts with the team | Empower the team to resolve conflicts among themselves | Use the conflict resolution committee to help resolve these conflicts | Escalate the conflicts to the program manager | A | The project manager should resolve the issues first before escalating to the next level. This is the best choice in the early stages of team formation.
985 | Cost | Company A is moving from a predictive approach to an agile one. After the second incremental release of project X, the product owner expressed disappointment with the prototype results and wanted to escalate the project to upper management and request a new team. Because of this, the team members start blaming each other and the new agile approach for the product owner's perception of the project. How should the project manager resolve the team's differences? | Follow the conflict resolution process documented in the project charter | Review the definition of done (DoD) with the product owner and determine the cause of the gap | Revisit the project vision with the team to ensure the project goal is understood | Use retrospective sessions to allow the team to determine the cause of the dispute | D | In a retrospective, the team reviews what happened during the iteration and determines improvements for moving forward. This is the best approach to resolve team differences in an agile environment.
986 | People | At the beginning of an agile project, the project manager develops the project charter with the team. They are unable to agree on the team values. What should the project manager discuss with the team to address the conflict? | Respecting the timebox | A group norm | Sustainable pace | Project ceremonies | B | Team values, such as sustainable pace and core hours, are part of the team's social contract or charter. Group norms are one of the elements that can be addressed when developing a team charter.
987 | Resource | You are the project manager in an organization that is implementing agile delivery. You have experience as a scrum master and will perform this role in addition to the project management responsibilities. One of the team members wants to know the main focus of a servant leader. What will be your response? | Client satisfaction and value-delivered demonstration | Stakeholders' expectation management and communication | Growth and well-being of people and communities they belong to | Productivity and efficiency to achieve commitments made | C | A servant leader seeks leadership opportunities to serve others. They measure success through the growth, development, and well- being of team members and the communities they belong to.
988 | Resource | What would be the most effective approach to motivate your team members? | Providing financial incentives to all the team members | Providing behavior-specific incentives to team members | Providing the same incentives to all the team members | Providing formal awards and recognition to the team | B | Apart from performance, employee behavior is key for rewarding and recognizing employees. Rewarding employees with good behavior motivates other team members and goes a long way in building and retaining a healthy team.
989 | Resource | Select three ways to improve and practice leadership skills. | Use democracy for all team decisions | Treat each team member the same way | Ask for feedback and analyze the results | Be actively involved in the project tasks E) Engage the team in the project process | C | These three options are effective ways to improve and practice leadership skills. They involve active participation, seeking feedback, and engaging the team in the project process.
990 | Resource | A project is being executed. The project's life cycle is defined as predictive; however, a major deliverable will be handed over incrementally to the customer. The assigned resources are experienced and reliable and willing to make decisions that the project manager made after each incremental delivery on other projects. What should the project manager do? | Consult the product owner about letting the resources make decisions Correct Answers & Explanations | Support the team's decisions and transfer the decision-making responsibility to them | Inform the team that although this is a hybrid environment, the project manager must still be responsible for making decisions | Schedule a steering committee meeting and obtain their approval on the request | B | In an Agile or Hybrid environment, the servant leader must empower the team based on its strengths around a purpose/goal and eliminate organizational impediments to delivering results. Supporting the team's decisions and transferring decision-making responsibility aligns with this approach. Conclusion This comprehensive PMP Exam Prep guide provides aspiring project management professionals with th